## Important Information
Detailed WBS for Top Online Tattoo Selling App
PROJECT TITLE |  |  | Online Tattoo Selling App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Suresh Carpenter
CLIENT NAME |  |  | Claudio
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | User & Admin
Business Need | To have a platform where end users will be able to find the service & tatoos and will be able to use their appointment services.
How to achieve? | As a solution to the problem we will be providing an app, where end user will be able to see a list of tattoos, select one of theirs desired tattoos and book an appointment.
User Types and Their Platforms | User Type1 | User
User Type2
| User Type3 | Admin
User Type4
User Type5
Tech Stack | Platform 1 | Flutter/ React Native
| Platform 2 | Node Js
Platform 3
Platform 4
| Admin | Web Based
Backend (API)
| Database | Mongo DB, MySQL
| Back-end | PHP (Laravel)

## User
Mobile App Flow for User Type 1
|  |  | 16 | 13 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
| Splash Screen | Launch screen of the application which will have the business logo and name
Authentication | User SIgn Up |  Users will be able to signup on the platform, Users will have to enter the below details on the App.  User Name User will have to enter the user first and last name on the platform.  Email address The User will get the option to sign up on the platform using their Email Address.  OTP Verification Once they Enters the E-mail Address, they will receive the OTP to verify the Email account.  Password Once the User adds their email address on the platform the, Users will be able to create the password for their account, the User can create the password in Characters, Special characters, Upper case, Lower case, Numbers on the platform | 2 | 1
| User SIgn In |  Users will able to login on the platform using their login credentials that they have used at the signup on the App.  User ID  Password | 2 | 1
| Forgot Password |  When Users click on the reset option they will get a code on the registered Email ID, after that they will be able to create a new password |  | 0
Homescreen | View Tattoos & Services | • Users will be able to finds services & Products by entering the name on the App. • A search bar with filter option will be available to users to find any service or tattoo. Filter like Service, product, location, price, style type will be available. • Users will view all the listed service, they will click on the tattoos section and view the below details on the platform. o Service/Product Provider Name and Details o Details (Listed Services/tattoos Name and Price) o Select a style (Style is realism, minimalist, water color, Japanese, traditional, neo traditional, etc.) o Description along with images o Prepare a design on the selected body location o Service Location | 3 | 2
| Checkout & Online Payment | • Users will be able to view their saved service or tattoo using this section of the App. • Users will get option for pay & checkout for their cart items. • Users can add more quantity to their product or service if needed. • User will get an option to check, whether in they have to select their payment method and enter their delivery address to confirm their appointment | 2 | 2
| Notifications |  Users will receive the notifications on the App.  Users will get the updates via notification on the App | 1 | 1
| My Account |  Profile: - Users will be able to view/edit their profile details: - Name, Email, Address and Phone Number.  View Appointments:- users can view their Appointment history using this section of the App.  Manage Payments:- Users will be able to manage their payments method using this section.  Change password: - Users will be able to change their password.  Logout: - Users will be able to logout from the App | 3 | 3
Notification |  | • User will be able to receive the notifications in their mobile notification window. • Users will be able to receive and view the messages sent by the driver on the application. • Users will be able to view driver’s name, vehicle name and vehicle number. • Users will receive updates on the taxi arrival along with time | 1 | 1
Setting |  | About Us  Users will be able to view the content and details about the services of the company.  Users will be able to view the below options on the App.  Policy Privacy  Terms Of Use  Users will click the above options and view all the details. Contact Us  If users will face any issue, Users will be able to connect with team by adding the below details.  Name  Email Address  Subject | 2 | 2

## Admin
Admin Flow
|  |  | 14 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
Users Management |  |  Admin will be able to manage Users from the admin panel.  Admin will be able to View/Delete/Add any particular Users from the admin panel.  Admin will be able to create and share the Login credentials to the end-users | 3
Manage Category/filter |  |  Admin will be able to manage the Services or product category from the admin panel.  Admin will be able add and remove the Services category from the admin panel | 2
Appointment Management |  |  Admin will be able to view and manage all of the Appointments using this section of the admin panel.  Admin can view all the details associated with the Appointment including seller and buyer user | 3
Manage Notifications |  |  Admin will be able manage notification from the admin panel.  Admin will share the new updates with the users from the admin panel | 2
Contact Us Management |  |  Admin will be able to manage the contact us from the admin panel.  Admin can view all the issues of the Users and Vendors from the admin panel.  Admin can provide the resolution to the Users based on the issues | 2
General Management |  |  Manage About Us  Manage Terms and Conditions  Manage FAQ and Social Media Platform  Contents and Images of the App Note: All the third party API’s that are required in development would be provided by Lucio | 2

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Online Tattoo Selling App | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-22 | 2024-04-09
[8 empty] | Total Project Effort (in person days) | 53
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 43
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-22 | 2024-02-02 | 1 | 10 |  | 2024-03-01
2 | UI/UX (User Type1) | 2024-01-23 | 2024-02-01 | 0 | 8 | Design
7 | User Type1_Mobile Application | 2024-03-25 | 2024-04-03 | 16 | 8
11 | Admin | 2024-03-04 | 2024-04-09 | 27 | 14
14 | QA Testing | 2024-03-12 | 2024-03-21 | 8 | 11
15 | UAT Testing | 2024-04-02 | 2024-03-27 | 20 | 1
16 | GO-LIVE | 2024-03-29 | 2024-03-29 | 1 | 1
Backend Technology - JAVA
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Note on E12: ====== ID#AAAA7hGge00 Kashish (2023-10-19 07:10:32) Sum of Total Development Effort Days needs to be entered by TL.