## Important Information
Detailed WBS for Beauty Parlour Service
PROJECT TITLE |  |  | Beauty parlour
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Praveen
CLIENT NAME |  |  | Chantal
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End user
Business Need | To develop a platform where end user can book beauty parlor service.
How to achieve? | The platform makes it simple to book beauty parlor appointments. Users can easily schedule and customize their appointments and will visit the parlor and get real-time updates.
User Types and Their Platforms | End user | Application
| Admin | Admin Panel (Web-based)
Tech Stack | Platform 1 | Flutter/React Native
| Admin | Node.js / PHP (Laravel)
| Backend (API) | Node js
| Database | MongoDB
| Back-end | PHP (Laravel)

## UserType1_Mobile App
Mobile App Flow for User Type 1
|  |  | 13 | 10
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
 Splash Screen |  | • Launch screen of the application which will have the business logo and name.
Athuentication |  Register / Sign-up | This functionality would allow users to create an account by entering the below details: -  Name  Mobile Number/E-mail ID  Password  Confirm Password | 1 | 0.5
|  Login | • This functionality would be used by users to log in to the application using below credentials: -  Mobile Number/E-mail ID  Password | 1 | 0.5
|  Forgot Password | • This functionality would allow users to recover their password which would be verified through OTP which would be received on e-mail ID or mobile number | 1 | 0.5
 Home page |  | • User will able to view following elements in home page. o Home screen o Search o Service o My booked services o Rating and Views o My menu o Notifications
|  Home screen: | • The home screen of the beauty salon app showcases a search bar, featured services, and dynamic content. Icons for My Cart, My Menu, and Notifications facilitate easy access. The footer navigation ensures quick and user-friendly interactions | 1 | 1
|  Search | • User will be able to search any beauty parlor treatment services using this section, as per there need. • They will able see the result and can click to particular services they want. | 1 | 1
|  Services | • Users will be able to view all the listed services with the below details, they will select service and book the appointment on the App o Service Name o Description o Book Appointment (calendar view) o User will able to book the online service and make payment online. Note- For booking any appointment, users will have to Sign up/Sign in on the platform. | 2 | 1.5
|  My booked services | • User will able see present, upcoming and past service which they have booked. • They also cancel the service if they want. • Users will be able to rebook the appointment for the same service on the app, in case want to postpone. • End user can also rate the service. | 2 | 2
|  Rating and Views | • Users can see the feedback and ratings of other customers. user can also upload the images as a feedback. | 1 | 0.5
|  Notification | • Users will receive all the notification related to application. • Appointment Booked Notifications. • Any type of refund etc. | 1 | 1
|  My menu | o My Account  Profile- Users will be able to view/edit their profile details: - Name, Email address & Phone Number.  Change Password- Users will be able to change their password.  Service Booking History- Users will be able to view appointment booked history and upcoming booking details on the App.  Logout- Users will be able to logout from the App. o About Us o Terms and Conditions o Privacy Policy o Contact Us | 2 | 1.5

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days)

## WebPanel (hidden)
WebPanel Flow
0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days)

## Admin
Admin Flow
7
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
 Users Management |  | • Admin will be able to view/search the list of all users of the platform. • Admin will be able to activate or deactivate the account of the users. • Admin will be able to view the complete profile of the user using this option. | 1
 Manage Services |  | • Admin will be able to manage Services from the admin panel. • Admin will be able to View/Search/Add/Remove the Services from the admin panel. • Admin will be able to manage (Add/Remove/Edit) service charge (Price) and details from the admin panel. | 1
 Manage Booking & Availability |  | • Admin will be able to manage and view user’s booking details from the admin panel. • Admin will be able to manage the booking availability time from the admin panel. • Admin will be able to view user’s booking daily basis in the calendar from the admin pane. • Admin will be able to book appointments for the clients from the admin panel. • Admin will be able to change the user’s booked appointment times from the admin panel. • Admin will be able to view the wait list of the clients to book appointments if any cancellations will happen, Admin will book the appointment of the waiting list clients from the admin panel. | 1
Ø Notification Management |  | • Admin will be able manage notifications from the admin panel. • Admin will share the new updates from the admin panel. | 1
 Contact Us Management |  | • Admin will be able to manage & view the user’s issues from the admin panel. • Admin will provide the resolution to the Users based on their issues. | 1
 General Management |  | • Manage About Us, Terms & Condition. • Manage App Images and Content. | 1
Ø Logout |  | • Admin will able to logout the panel | 1

## Gantt_Chart Summary
Draft Project Schedule
[9 empty] | Development Start Date | Development End Date
Draft Gantt Chart -Beauty parlour | [8 empty] | 2024-02-15 | 2024-03-11
[9 empty] | Total Project Effort (in person days) | 34
[9 empty] | Total Duration (in business days) | 18
Sl. No. | Tasks | Start_Date | End_Date | Duration (days) | Component (Design Page and API) Numbers
1 | FSD Creation and Approval | 2024-02-15 | 2024-02-19 | 3 | 0 |  |  | 2024-02-20
2 | UI/UX (End user) | 2024-02-15 | 2024-02-20 | 4 | 13 | No of Screen Designs | Design
7 | End user_Mobile Application | 2024-02-21 | 2024-03-08 | 13 | 15 | No of Components
11 | API | 2024-02-21 | 2024-03-06 | 10 | 25 | No of API's
12 | Admin | 2024-02-21 | 2024-03-01 | 7 | 22 | No of Admin Component
14 | QA Testing | 2024-02-21 | 2024-03-11 | 13 | 0
15 | UAT Testing | 2024-02-22 | 2024-03-12 | 13 | 0
16 | GO-LIVE | 2024-03-13 | 2024-03-14 | 2 | 0
Formulas:
Start_Date = WORKDAY([Start_Date, row above],1,)
Start_Date = WORKDAY([End_Date, row above],1,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)