## Important Information
Detailed WBS of Cleaning Service Application V1.0
PROJECT TITLE |  |  | Cleaning Service Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Chetna Kashyap
CLIENT NAME |  |  | Samer Taleb
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | Users, Employee and Admin
Business Need | Client want to develop an application, which will be for different organization where user have to view the information of the service. Users can also request for the services from the admin.
How to achieve? | Application help the users to provide the platform where user can view the information and ask for service by service request form.
User Types and Their Platforms | End Users | Application
| Employee | Application
| Admin | Web back end panel
Tech Stack | Application | Flutter/React Native
Web Panel
| Back-end | PHP (Laravel)/Node.Js
| Back-end | PHP (Laravel)

## End users_Mobile App
Mobile App Flow for End users
TOTAL DAYS |  |  |  | 11 | 11
Actors | Modules | Sub - Modules | Notes | API (in days) | Mobile App Development (in days)
| Splash Screen |  | Users will be able to view splash screen with organization logo in the app.
| Authentication |  | Sign Up The Users will be able to sign up on the platform by using their: - Users Name: Users have to insert their mobile number while sign up their profile. - Email: The Users will get the option to sign up on the platform using their Email Address. - Password: Once the Users adds their email address on the platform the Users will be able to create the password for their account, the Users can create the in Characters, Special characters, Upper case, Lower case, Numbers on the platform. - OTP Verification: Once the Enters the E-mail Address, he will receive the OTP to verify the Email account. Login - The Users will be able to Login on the platform using their login credentials that they have created during the sign up process. The Users can use the following credentials such as the: - Email Address - Password Forget Password - If users forget the password then simply users clicking on forgot password link and where users has to fill the email id. - After entering the email id users will get an OTP on the email that users has to fill into the OTP field. - After filling the OTP users redirect to create new password Screen where users can recreate the password. | 1 | 2
| Home screen |  | Users will be able to view the Information of the cleaning services on the home screen. - Users will be able to view the listing of the cleaning services of the home screen which will be:- - Painting - Cleaning - Resurfacing - Carpet cleaning - When users click on any particular services. Users will redirect to service description screen. | 2 | 2
| Service Description screen |  | Users will be able to view the cleaning service details on the home screen. - Users will be able to view the details which will be:- - Service name - Service image - Service fees - Service details - Service provider details. - Users will be able to book the services by filling the request form. | 2 | 2
| Request Form |  | Users will be able to view the below mentioned section in the request form which will be:- o Your Name o Your phone number o Your email Address o Location o How to you hear about us? o How can we help you? o Services need by you o Submit button - Users will have to choose the date and time on the request form screen. - Users have to fill the above details and after filling the details admin will receive the notification. Notes: - After submission of the form. Admin will receive the request and accordingly, admin will assign the task to the employee. | 2 | 1
| Contact US |  | Users will be able to view the contact us form on the contact us screen. - Users will be able to view the contact us details of the admin on the contact us screen. | 1 | 1
| About Us |  | Users will be able to view the about the organization on the about us screen. - Users will be able to view the details about admin on the about us screen. | 1 | 1
| Account |  | Users will be able to add/edit their profile like Profile: - Users will be able to view /edit his profile details like: - Name, Email, Phone Number. - Change password: - Users will be able to change his password. - Listing of the services : - Users will be able to view the services which has been taken by the users. - Logout: - Users can logout the application. - Delete - Users can delete the account permanently by clicking on delete button. Notes: - After receiving the confirmation on the payment. Users will receive the notification on the payment confirmation. | 2 | 2

## userstype1_Website (hidden)
Website Flow for <UserType1>
TOTAL DAYS |  |  |  | 0 | 0
Actors | Modules | Sub - Modules | Notes | API Development (in days) | Website Development (in days)

## Employee_Mobile App
Mobile App Flow for Employee
TOTAL DAYS |  |  |  | 7 | 9
Actors | Modules | Sub - Modules | Notes | API (in days) | Mobile App Development (in days)
| Splash Screen |  | Employees will be able to view splash screen with organization logo in the app.
| Authentication |  | Sign Up The Employees will be able to sign up on the platform by using their: - Employees Name: Employees have to insert their mobile number while sign up their profile. - Email: The Employees will get the option to sign up on the platform using their Email Address. - Password: Once the Employees adds their email address on the platform the Employees will be able to create the password for their account, the Employees can create the in Characters, Special characters, Upper case, Lower case, Numbers on the platform. - OTP Verification: Once the Enters the E-mail Address, he will receive the OTP to verify the Email account. Login - The Employees will be able to Login on the platform using their login credentials that they have created during the sign up process. The Employees can use the following credentials such as the: - Email Address - Password Forget Password - If employees forget the password then simply employees clicking on forgot password link and where employees has to fill the email id. - After entering the email id employees will get an OTP on the email that employees has to fill into the OTP field. - After filling the OTP employees redirect to create new password Screen where employees can recreate the password. | 1 | 2
| Home Screeen |  | Employee will be able to view the listing of the task assign to them on the home screen. - Employee will be able to view accept and reject button on the home screen. Where users can accept the service and reject the service as per their convenient. - Employee will be able to view the below details on the home screen which will be:- - Users name - Users location - Service need by particular users - Time and date. - Confirm location button - When employee reach the assigned location, then employee will click on confirm location button. - After clicking on confirm location button, employee will redirect to camera screen where employee will clicks the image and upload that image on the application. - After completion of the project or task. Employee will click on done button. - When employee will receive the payment from users. Then employee will click on payment done button. After clicking on done button users will receive the confirmation and admin will be receive the confirmation as well. | 4 | 5
| Account |  | Employee will be able to add/edit their profile like - Profile: - Employees will be able to view /edit his profile details like: - Name, Email, Phone Number. - Change password: - Employees will be able to change his password. - Listing of the services: - Employees will be able to view the services which has given by the employee. - Logout: - Employees can logout the application. - Delete - Employees can delete the account permanently by clicking on delete button. | 2 | 2

## UserType2_Website (hidden)
Website Flow for <UserType2>
TOTAL DAYS |  |  |  | 0 | 0
Actors | Modules | Sub - Modules | Notes | API Development (in days) | Website Development (in days)

## WebPanel (hidden)
WebPanel Flow
TOTAL DAYS |  |  |  | 0
Actors | Modules | Sub - Modules | Notes | TeacherPanel Development (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
TOTAL DAYS |  |  |  | 0
Actors | Modules | Sub - Modules | Notes | Sub-Admin Development

## Admin
Web Flow for Admin
TOTAL DAYS |  |  |  | 6
Actors | Modules | Sub - Modules | Notes | Development
| Users Management |  | Admin will be able to manage the User. - Admin will be able to view/search the list of the Users. - Admin will be able to View/Delete/Activate/Deactivate any particular user. | 1
| Employee Management |  | Admin will be able to manage the Employee from the back end. - Admin will be able to view/search the list of the Employee from the back end. - Admin will be able to View/Delete/Activate/Deactivate any particular employee from the back end. | 2
| Service Management |  | Admin will be able to view the services from the back end. - Admin will be able to add/delete/edit the details of the services from the back end. - Admin will be able to assign the task to the employee from the back end. | 1
| Information Management |  | Admin will be able to manage the Information from the back end. - Admin will be able to view/search the list of the services from the back end. - Admin will be able to view the transaction details from the back end. | 1
| Content Management |  | Admin will be able to add/edit and delete the content in the app. - Manage About Us - Admin will be able to manage contact us | 1

## Gantt_Chart Summary
Draftt Gantt Chart - Cleaning Service Application | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-17 | 2024-03-19
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days) |  |  | Total Project Effort (in person days) | 54
1 | FSD Creation and Approval | 2024-01-17 | 2024-01-30 | 1 | 10 |  | 2024-01-30 | Total Duration (in business days) | 45
2 | UI/UX (End Users) | 2024-01-18 | 2024-01-26 | 0 | 7 | Design
3 | UI/UX (Employee) | 2024-01-18 | 2024-01-26 | 0 | 7 | Design
4 | UserType1_Mobile Application | 2024-01-31 | 2024-02-12 | 1 | 9
5 | UserType2_Mobile Application | 2024-02-16 | 2024-02-28 | 12 | 9
6 | API+Admin | 2024-01-31 | 2024-02-19 | 14 | 22
7 | QA Testing | 2024-02-08 | 2024-03-08 | 22 | 22
8 | UAT Testing | 2024-02-29 | 2024-03-14 | 1 | 11
9 | GO-LIVE | 2024-03-18 | 2024-03-19 | 1 | 2
Note on E11: ====== ID#AAAAphdgHag Kashish (2023-02-02 10:00:44) Sum of Total Development Effort Days needs to be entered by TL.