## Important Information
Detailed WBS of SoulMate Application V1.0
PROJECT TITLE |  |  | SoulMate Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Aashi
CLIENT NAME |  |  | Nicholas
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | Users and Admin
Business Need | To have a platform where ends users will read the stories by selecting the genre on the platform.
How to achieve? | As a solution, we are providing an application that will fulfill the need of end users where they will register. They can read stories and their chapters by picking the genre of the story, they will also collect the daily rewards and complete their daily check-in tasks on the application. Revenue Model - The client will generate revenue through the purchase of the diamond.
User Types and Their Platforms | App | Scorers
| App | Users
| Admin | Web-Based Panel
Tech Stack | App | React Native/ Flutter
| Back-end | Node Js
| Back-end | PHP (Laravel)

## End Users_Mobile App
Mobile App Flow for Scorers
TOTAL DAYS |  |  |  | 14 | 27
Actors | Modules | Sub - Modules | Notes | API (in days) | Mobile App Development (in days)
| Splash Screen |  | Users will be able to view the splash screen of the app with the company logo. |  | 0
| Users Signup |  |  Users will be able to signup on the platform, Users will have to enter the below details on the application.  User Full Name User will have to enter the user first and last name on the platform.  Email address The User will get the option to sign up on the platform using their Email Address.  OTP Verification Once they Enters the E-mail Address, they will receive the OTP to verify the Email account.  Password Once the User adds their email address on the platform the, Users will be able to create the password for their account, the User can create the password in Characters, Special characters, Upper case, Lower case, Numbers on the platform. | 1 | 2
| Login |  |  Users will able to login on the platform using their login credentials  Users ID  Password. | 1 | 2
| Forgot Password |  |  Users will be able to reset the password of their users account.  When Users click on the reset option they will get a code on the registered Email ID, after that they will be able to create a | 0 | 1
| Home Screen |  |  Users will be able to view the below options on the home screen.  More Stories  Browse by Genre  Diamonds  Settings  Notifications  My Account | 0 | 3
| Stories |  |  User will be able to select and read the stories on the app.  Users will be able to read the stories by select the Genre (Fiction/ Horror/ Historical/ Fantasy/ Romance/ Thriller/ Comedy) and they can view all the listed stories on the application.  When users will select and read the stories, they need to select the below details.  Play as a (Male or Female)  Select Skin Tone  Select Character Image  What should we call you (Character Name)  Stories will contain the below details.  Story Name and Image  View Story Genre  Background Image and Music  Story Content  Chapters Name and Content  In between reading the stories, users will get a choice option (Premium or Non-premium), if they will select the Premium option, they need to apply the diamonds to deeper into the stories on the app.  According to the chapters stories contents, background music and images will be changed and users need to choose the character again on the app. Note- if the users will not have enough diamonds they will be able to purchase the diamonds on the app. Note- Once users will complete the chapter of the stories, they will receive a star on the app. | 4 | 6
| Diamonds |  |  Users will be able to view their diamonds count on the app.  Users will be able to collect their daily rewards (Free 5 diamonds) on the app.  Users will be able to redeem their diamonds when they will be reading the stories on the app.  Users will be able to buy the diamonds through the In-app purchase on the app. | 2 | 3
| Daily Check-in |  |  Users will be able to view the below types of tasks in daily check-in on the app.  Make Two Choices  Finish a Chapter  Collect Dialy Rewards  Users will be able to view their achievements (like Completed One Story, Finish 10 chapters) on the Note- Once the users will complete their daily check-in task done checkbox will be showing on the app. | 2 | 3
| Settings |  |  Users will be able to view and manage the below options of the settings.  Notifications (On or Off)  Music (On or Off)  Interested in (Men/ Women/ Both)  Adult theme (Or or Off)  Help and Legal (View the terms and conditions)  Appearance (Select the Mode- Dark/ Light/ System setting) | 2 | 3
| Notifications |  |  Users will receive the below types of notifications on the app.  Stars Received  Chapter Completed  New Updates Notifications | 1 | 2
| My Account |  |  Profile: - Users will be able to view/edit their profile details: - Name, Email and Phone Number.  Change password: - Users will be able to change their password.  My Stars: - Users will be able to view all the earned stars on the app.  My Progress: - User will be able to track their story progress on the app.  Help Center: - If users will face any issue, Users will be able to Help Center with team by Email.  Logout: - Users will be able to logout from the application.  Delete Account: - Users will be able to delete their account from the application. | 1 | 2

## Admin
Web Flow for Admin
TOTAL DAYS |  |  |  | 14
Actors | Modules | Sub - Modules | Notes | Development
| Users Management |  |  Admin will be able to manage Users from the admin panel.  Admin will be able to Search/View/Remove/Add any particular Users from the admin panel. | 2
| Manage Stories and Chapters Contents |  |  Admin will be able to manage Stories and Chapters Contents from the admin panel.  Admin will be able to manage the Genre (Fiction/ Horror/ Historical/ Fantasy/ Romance/ Thriller/ Comedy) of the stories from the admin panel.  Admin will be able to manage the below details of the story and their chapters from the admin panel.  Add Story Name and Image  Select Story Genre  Define Story Chapters  Add Background Images and Music  Add Story and Chapter Content  Add Chapters Name  Admin will be able to define and manage the choice options (Premium or Non-premium) from the admin panel. | 3
| Track Progress |  |  Admin will be able to track the users progress from the admin panel. | 2
| Manage Diamonds |  |  Admin will be able to manage Diamonds and their prices from the admin panel. | 2
| Notifications Management |  |  Admin will be able to manage the notifications from the admin panel.  Admin will share all the updates from the admin panel. | 2
| Help Center Management |  |  Admin will be able to manage and view all the issues of the Users from the admin panel.  Admin will provide the resolution to the Users based on their issues. | 2
| General Management |  |  Manage About Us  Manage Terms and Condition  Manage Content & FAQ Note: All the third party API’s that are required in development would be provided by Nicholas. | 1

## Gantt_Chart Summary
Draftt Gantt Chart - SoulMate Application | [8 empty] | Development Start Date | Development End Date
[9 empty] | 2023-07-03 | 2023-09-15
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days) |  |  |  | Total Project Effort (in person days) | 55
1 | FSD Creation and Approval | 2023-07-03 | 2023-07-17 | 1 | 10 |  |  |  | Total Duration (in business days) | 55
2 | UI/UX (User Type1) | 2023-07-04 | 2023-07-03 | 0 | 0 | Design | 1 | 2023-07-03
8 | User and Driver_Mobile Application | 2023-07-04 | 2023-08-09 | 1 | 27
12 | API+Admin | 2023-07-04 | 2023-08-10 | 28 | 28
15 | QA Testing | 2023-07-13 | 2023-09-04 | 37 | 38
16 | UAT Testing | 2023-08-03 | 2023-09-11 | 1 | 28
17 | GO-LIVE | 2023-09-13 | 2023-09-15 | 1 | 2