## Important Information
Detailed WBS for <Fundraiser Lottery Application>
PROJECT TITLE |  |  | Fundraiser Lottery Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Priyanshi
CLIENT NAME |  |  | James
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End Users
Business Need | The business need is developed a mobile application for end user to view their Fundraiser lottery results.
How to achieve? | We are developing a mobile application for end users who will be able to view list of games which are part of lottery and from game details screen they will be able to view their lottery results.
User Types and Their Platforms | End User | End User Application
Tech Stack | Application | React Native/ Flutter
| Backend (API) | Node Js
| Database | MonogDB/ Mysql
| Back-end | PHP (Laravel)

## End User_Mobile App
Mobile App Flow for User Type 1
|  |  | 10 | 7
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
 Splash Screen |  | • Users will be able to see the splash screen every time opening the application, which includes the company name & Logo. | 1 | 1
 Home Screen |  | This is the home screen of the application from where users will be able to access and navigate to all the functionality of the platform. The home screen will have the below mentioned functionality • Games Listed • Settings | 2 | 1
 Games Listed |  | • Users will be able to view list of games whose results will be showing to user on the platform. • Following will be list of games whose data will be coming through APIs o Football Frenzy o Basketball Slam o Baseball Fever o Soccer Shot o Stock Market Challenge • On tapping any of the games, a game details screen will open and user can read description and a button to view result for that game lottery. • On tapping on button, user will be ask to enter their lottery ticket Unique ID. On entering correct ID the system will fetch the result accordingly. | 5 | 4
 Settings |  | • Privacy Policy (Users can read Privacy policy of using platform) • Terms & Condition (User can read T&Cs of the platform) • Help & Support (User can reach out to admin anytime using this feature) | 2 | 1

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin (hidden)
Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Fundraiser Lottery Application | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2023-12-11 | 2024-02-02
[8 empty] | Total Project Effort (in person days) | 25
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 40
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2023-12-11 | 2023-12-22 | 1 | 10 |  | 2023-12-22
2 | UI/UX (End User) | 2023-12-12 | 2023-12-21 | 0 | 8 | Design
7 | End User_Mobile Application | 2023-12-25 | 2024-01-05 | 1 | 10
11 | API | 2023-12-25 | 2024-01-11 | 14 | 7
14 | QA Testing | 2024-01-02 | 2024-01-24 | 17 | 17
15 | UAT Testing | 2024-01-23 | 2024-01-30 | 1 | 6
16 | GO-LIVE | 2024-02-01 | 2024-02-02 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E12: ====== ID#AAABA5rHf0g Kashish (2023-12-07 12:15:20) Sum of Total Development Effort Days needs to be entered by TL.