## Important Information
Detailed WBS for <Vital Clean Application v1.0>
PROJECT TITLE |  |  | Vital Clean Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Sakshi
CLIENT NAME |  |  | Evelyn
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types
Business Need | Client is looking for an application for his cleaning services. User can register on the application and view different cleaning services. Along with this they can also book the appointment for the cleaning service and pay over the application using different payment methods. User can also view the employees that would be visiting for the service.
How to achieve? | Over this application we will provide users to register and view all the services added by the Admin. User can also schedule the appointment for the service. Admin upon receiving the service request will assign one the employee for the service. User can then view all the details. Employee after finishing the service can click image and share the image with Admin outside the platform. Employee can also check in & out for the service.
User Types and Their Platforms | End User (Customer) | Mobile Application
| Admin | Web Based Panel
Tech Stack | Mobile Application | React Native & Flutter
| Admin | React Js
| Backend (API) | Node Js
| Database | Mongo DB/Mysql
| Back-end | PHP (Laravel)

## End User_Mobile App
Mobile App Flow for End User
|  |  | 12 | 10
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
 Splash Screen |  | • The launch screen of the Application where end users will be able to view the company’s logo.
 Authentication | • Sign In |  The User will be able to login into the application using the below details: o E-mail ID or Mobile Number o Password or OTP | 1 | 1
| • Sign Up / Register (As Customer) |  User will be able to register using below details: - o First Name & Last Name o E-Mail ID o Mobile Number o Password o Confirm Password o Service Address o Checkbox for Terms and Conditions • OTP Verification  Sign-up process has to be verified through mobile number/email ID | 1 | 1
| • Forgot Password |  Clicking on this user would be redirected to the Forgot Password screen where user need to enter the below details:- o Mobile Number (To receive the OTP for verification). o OTP  After the OTP is verified user would be asked to mention below details in order to change the password:- o New Password o Confirm New Password | 1 | 1
 Home Screen |  | • This screen would be the main screen of the application and would comprise of below details: - o Services o My Appointments o Feedback o Notifications o Profile o Settings | 1 | 1
Services | Service Lisitng | • User would be able see the list of services offered by the company • User can book the any of the services from the list of below listed services o CARPET CLEANING o TILE And GROUT CLEANING o UPHOLSTERY CLEANING o POWER WASHING o PET URINE ODOR REMOVAL o 24/7 FLOOD RESPONSE • User will view the calendar to book the cleaning service. To book service user have to select o The date of service (Calendar view for booking) o Time slots (from list of available slots) • User will be able to view the amount details of the service • User will select the payment mode such as Credit/Debit Card | 2 | 1
|  Checkout | • User will be able to pay for the service • User will get the confirmation of the service • User will be able to see the details of the booking assigned for the service. | 2 | 1
 My Appointments |  | • User can view all the appointments & details along with payment status. | 1 | 1
 Feedback |  | • Once the service has been completed, user would be able to see the feedback form where the set of questions will be given to the user • User will fill and submit the form, so that the company would know about their services | 1 | 1
 Notifications |  | • User will receive Push and general notification on the platform. • User will get reminder about the service confirmation.
 Profile |  | Clicking on this user would be redirected to the screen displaying My Account details with below options: - • Profile (Option to view or update the profile settings) • Password (Option to update the password) • Email (Option to view or update the e-mail ID) • Manage Address (User can edit their service address using this section) • Logout (User will be able to logout from the platform using this feature) | 1 | 1
 Settings Icon |  | • Terms & Condition (User can view terms and conditions using this section) • Privacy Policy (User can read the privacy Policy) • Help & Support (User can reach-out to admin in case of any support needed) | 1 | 1

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
9
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
 Dashboard |  | • Quick links for the given features would be given like:- o User Management o Employee Management o Service & Booking Management o Feedback Management o Payment Management o Content Management | 1
 User Management |  | • This section would be able to view, edit or delete the customers. • Admin would be able to enable and disable the customers. | 1
 Employees Management |  | • Admin can add the name of service person (employee) using this section. Admin can manage all using same. • This section would be able to add, view, edit or delete task to employees and share the details with them offline the platform. • Admin would be able to highlight the assigned tasks of employees as completed or terminate. • Admin can also view, edit the check-in & check-out time of employees. (as employee are updating the admin outside of the platform) • Admin can view all the services assigned to the any user (New or old services assigned) | 1
 Service Management |  | • Admin will be able to view/edit/add/delete the services on the application. • Admin can setup the content for each services such as their description & image. | 1
 Booking Management |  | • Admin will be able to view the services booked by the user • Admin can view all the details of the user like Name, Address & Phone Number • Admin will be able to assign the employee to the service • Employee would be notified for the service • Admin will be able to view the feedback form filled by the user after the service | 1
 Feedback Management |  | • This section would be used by admin panel to view the details of query and respond back to them in the form of notification | 1
 Payment Management |  | • Admin will be able to manage the payment of the services paid by the user • Admin can see all the details of the transaction | 1
 Notification Management |  | • This section would be used by admin panel to push notifications to the front end users. | 1
 Content Management |  | • Admin will be able to manage (Add/View/Edit) the static contents. o About Us o Terms and Conditions o Privacy Policy | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Vital Clean Application | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2023-12-11 | 2024-02-22
[8 empty] | Total Project Effort (in person days) | 35
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 54
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2023-12-11 | 2023-12-22 | 1 | 10 |  | 2023-12-22
2 | UI/UX (End User (Customer)) | 2023-12-12 | 2023-12-15 | 0 | 4 | Design
7 | End User (Customer)_Mobile Application | 2023-12-25 | 2024-01-09 | 1 | 12
11 | API+Admin | 2023-12-25 | 2024-01-11 | 14 | 19
14 | QA Testing | 2024-01-02 | 2024-02-13 | 31 | 31
15 | UAT Testing | 2024-01-23 | 2024-02-19 | 1 | 20
16 | GO-LIVE | 2024-02-21 | 2024-02-22 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E12: Kashish: Sum of Total Development Effort Days needs to be entered by TL.