## Important Information
Detailed WBS for Doctor Appointment Booking App
PROJECT TITLE |  |  | Doctor Appointment Booking Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Chetna Kashyap
CLIENT NAME |  |  | Serge Losyev
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End Users, Doctor's app ,User website & Admin Panel
Business Need | Business need is to have a platform where patients as users will be able to search for doctors on the basis of their specialization and book an appointment.
How to achieve? | We will develop end user application , doctor application, user website and admin panel
User Types and Their Platforms | End User | Customers
| End User | Doctor's
| Admin | Adminstrator
Tech Stack | Application | Flutter/React Native
| Website | HTML/CSS/Angular
| Admin | PHP(Laravel)/Node.js
| Backend (API) | PHP(Laravel)/Node.js/JAVA
| Database | MongoDB/MySQL
| Back-end | PHP (Laravel)

## End Users_Mobile App
Mobile App Flow for End Users
|  |  | 37.5 | 19.5 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
Splash Screen |  | The company logo will be visible on the splash screen. | 0.5
Sign Up / Register Page |  | Users will be able to register on the Application by providing below details:- - Full Name - Email id - Password and Confirm Password. - Terms and Conditions checkbox Users will receive an OTP over his/her email id for verification. - Option to Sign In - If already registered | 1 | 0.5
Login Page |  | o Users will be able to Login into the Application using below details:- - Email id - Password - Forgot Password Hyperlink - Register - If account does not exists. | 0.5 | 0.5
Forgot Password |  | o This option would be used by users in case they forgets their password. o They need to enter the e-mail Id on which the password reset link would be sent to reset the password. | 0.5 | 0.5
Home Screen |  | Landing page of the app home screen displaying below sections or details:- - Logo of the Application. - Menu Tabs - Book an Appointment, Find a Doctor, Specialization, About Us, Contact Us, Sign In/Sign Up - Doctors available in the particular zip code would be visible - Search Bar to search for Doctors using keyword (Name and Specialization) - Carousel Images/advertisements managed by admin - Section displaying options to navigate to Book an Appointment, Find a Doctor and Services. | 6 | 3
Booking an Appointment |  | o This option would be used by patients to book an appointment. o Search Field would be displayed on the Application to search Doctors on the basis of:- - Name - Location - Specialization - Doctor/s list would be displayed on the basis of search List of all the Doctors would be displayed default on home page with below details:- - Doctor Name - Doctor Profile Image - Doctor Qualification - Doctor Specialization - Book An Appointment - View Profile button On clicking the Book an Appointment or View Profile button, user would be redirected to the Doctors Detail Page: - - Doctor Name - Doctor Profile Image - Doctor Qualification - Doctor Specialization - Description about Doctor - Appointment Schedule with Day and Time - Book Now | 20 | 10
Find a Doctor:- |  | This section would be used by users to find doctor on the basis of name and specialization. As per the selection below details would be displayed:- - Doctor Name - Doctor Profile Image - Doctor Qualification - Doctor Specialization - Book An Appointment - View Profile button On clicking the Book an Appointment or View Profile button, user would be redirected to the Doctors Detail Page (defined later in the document).
About Us |  | This section would describe about the Application with text and images. This section would also contain a video | 2 | 1
Contact Us |  | This section would have the Contact Us form to submit the query or feedback. | 1 | 1
My Account |  | Once the user is signed into the Application the Sign In/Sign Up button option would be changed to My Account. Profile to update the below details:- - Name - Mobile Number - E-mail ID (If changed then the same needs to be verified through OTP) - Update Password (Current Password, New Password and Confirm New Password) - Sign Out - Delete Account | 2 | 1
My Appointments |  | This section would be used to view the details of all the appointments (Past and Upcomig) Below details would be displayed for each Appointment:- - Date and Time of booking an appointment - Date and Time of appointment - Doctor Name and Specialization - Consultancy Type (In Person or Video Call) - Patient Name - Self or Relation - Name (If relation is selected) | 4 | 2

## Doctor_Mobile App
Mobile App Flow for Doctors
|  |  | 19.5 | 9.5 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
Splash Screen |  | The company logo will be visible on the splash screen. | 0.5
Sign Up/Register |  | Clicking on the button user would be redirected to the registration screen. Users will be able to register on the Application by providing below details:- - Full Name - Email id - Password and Confirm Password. - Teams and Conditions checkbox - Users will receive an OTP over his/her email id for verification. - Option to Sign In - If already registered. | 1 | 0.5
Sign In |  | Users will be able to Login into the Application using below details: - Email id - Password - Forgot Password Hyperlink - Register - If account does not exists. | 0.5 | 0.5
Forgot Password |  | This option would be used by users in case they forgets their password. They need to enter the e-mail Id on which the password reset link would be sent to reset the password. | 0.5 | 0.5
My Account |  | Once the doctor is signed into the mobile Application the Sign In/Sign Up button option would be changed to My Account. Profile to update the below details:- - Name - Mobile Number - E-mail ID (If changed then the same needs to be verified through OTP) - Update Password (Current Password, New Password and Confirm New Password) - Sign Out - Delete Account | 2 | 1
All Appointments |  | This section would be used to view the details of all the appointments (Past and Upcoming). Below details would be displayed for each Appointment:- - Date and Time of booking an appointment - Date and Time of appointment - Doctor Name and Specialization - Patient Name - Name - Amount of visit | 15 | 7

## End-Users_Website
Website Flow for End-Users
|  |  | 25 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
Landing Page |  | Landing page of the website screen displaying below sections or details:- - Logo of the website. - Menu Tabs - Book an Appointment, Find a Doctor, Specialization, About Us, Contact Us, Sign In/Sign Up - Doctors available in the particular zip code would be visible - Search Bar to search for Doctors using keyword (Name and Specialization) - Carousel Images/advertisements managed by admin - Section displaying options to navigate to Book an Appointment, Find a Doctor and Services. | 3
Sign Up / Register Page |  | Users will be able to register on the website by providing below details:- - Full Name - Email id - Password and Confirm Password. - Terms and Conditions checkbox - Users will receive an OTP over his/her email id for verification. - Option to Sign In - If already registered. | 2
Login Page |  | Users will be able to Login into the Application using below details:- - Email id - Password - Forgot Password Hyperlink - Register - If account does not exists. | 1
Forgot Password |  | This option would be used by users in case they forgets their password. They need to enter the e-mail Id on which the password reset link would be sent to reset the password. | 1
Booking an Appointment |  | This option would be used by patients to book an appointment. Search Field would be displayed on the Application to search Doctors on the basis of:- - Name - Location - Specialization - Doctor/s list would be displayed on the basis of search List of all the Doctors would be displayed default on home page with below details:- - Doctor Name - Doctor Profile Image - Doctor Qualification - Doctor Specialization - Book An Appointment - View Profile button On clicking the Book an Appointment or View Profile button, user would be redirected to the Doctors Detail Page: - - Doctor Name - Doctor Profile Image - Doctor Qualification - Doctor Specialization - Description about Doctor - Appointment Schedule with Day and Time - Book Now | 12
Find a Doctor:- |  | This section would be used by users to find doctor on the basis of name and specialization. As per the selection below details would be displayed:- - Doctor Name - Doctor Profile Image - Doctor Qualification - Doctor Specialization - Book An Appointment - View Profile button On clicking the Book an Appointment or View Profile button, user would be redirected to the Doctors Detail Page (defined later in the document).
About Us |  | This section would describe about the website with text and images. This section would also contain a video. | 1
Contact Us |  | This section would have the Contact Us form to submit the query or feedback. | 1
My Account |  | Once the user is signed into the website the Sign In/Sign Up button option would be changed to My Account. Profile to update the below details:- - Name - Mobile Number - E-mail ID (If changed then the same needs to be verified through OTP) - Update Password (Current Password, New Password and Confirm New Password) - Sign Out - Delete Account | 2
My Appointments |  | This section would be used to view the details of all the appointments (Past and Upcoming). Below details would be displayed for each Appointment:- - Date and Time of booking an appointment - Date and Time of appointment - Doctor Name and Specialization - Consultancy Type (In Person or Video Call) - Patient Name - Self or Relation - Name (If relation is selected) | 2

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
|  |  | 7 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
Login |  | • Admin will be able to Login into the admin web panel using their login credentials. The admin will use the following credentials such as: o User Name o Password | 1
User Management |  | • Admin will be able to manage the User from the backend. • Admin will be able to activate/deactivate the account of the User from the backend | 1
Doctor Profile Management |  | • Admin would be able to add, update and delete the doctor’s details which are displayed on the Application for end users. | 1
Booking Management |  | • Admin will be able to view and manage bookings from the backend. | 3
Content Management |  | • Admin will be able to manage Carousel Images for Mobile and Application • Admin will be able to update and add text for About Us • Admin will be able to update and add text for Terms and Condition | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Appointment Booking Application | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2023-11-03 | 2024-02-27
[8 empty] | Total Project Effort (in person days) | 152
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 83
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2023-11-03 | 2023-11-16 | 1 | 10 |  | 2023-11-21
2 | UI/UX (End User) | 2023-11-06 | 2023-11-21 | 0 | 12 | Design
3 | UI/UX (End User) | 2023-11-06 | 2023-11-17 | 0 | 10 | Design
4 | Website Design (End User) | 2023-11-06 | 2023-11-21 | 0 | 12 | Design
7 | End User_Mobile Application | 2023-11-22 | 2024-01-11 | 1 | 37.5
8 | End User_Mobile Application | 2023-11-23 | 2023-12-19 | 1 | 19.5
9 | End User_Website | 2023-12-08 | 2024-01-11 | 13 | 25
11 | API+Admin | 2023-11-22 | 2023-12-11 | 14 | 36
14 | QA Testing | 2023-11-30 | 2024-02-16 | 57 | 57
15 | UAT Testing | 2023-12-21 | 2024-02-22 | 1 | 46
16 | GO-LIVE | 2024-02-26 | 2024-02-27 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY(WORKDAY(H8,[Lead Days]),1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E16: Kashish: Sum of Total Development Effort Days needs to be entered by TL.