## Important Information
Detailed WBS for Neoteric Platform
PROJECT TITLE |  |  | Neoteric Platform Website
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Chetna¦¦Rishav
CLIENT NAME |  |  | Shirley Muhato
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End Users, Developers & Admin
Business Need | Client needs a website where end users can buy products & developers can create a project to add particular products.Admin will manage the whole platform from the backend.
How to achieve? | We will build a website where end users can buy products ,developers can create a project to add particular products and chat with admin for negotiation.
User Types and Their Platforms | End User & Developer | Website
| Admin | Admin Panel
Tech Stack | Website | HTML/CSS & Bootstrap
| Admin | Node.js / PHP (Laravel)
| Backend (API) | Node.js / PHP (Laravel)
| Database | MongoDB / MySql
| Back-end | PHP (Laravel)

## End-users_Website
Website Flow for End Users
|  | 70.5 | 49.5
Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days)
• Sign Up / Register Page | o Users will be able to register on the website by providing below details:- ▪ Full Name ▪ Email id ▪ Password and Confirm Password. ▪ Terms and Conditions checkbox ▪ Users will receive an OTP over his/her email id for verification. ▪ Option to Sign In - If already registered. | 0.5 | 0.5
• Login Page | o Users will be able to Login into the website using below details:- ▪ Email id ▪ Password ▪ Forgot Password Hyperlink ▪ Register - If account does not exists. | 0.5 | 0.5
• Forgot Password | ▪ This option would be used by users in case they forgets their password. ▪ They need to enter the e-mail Id on which the password reset link would be sent to reset the password. | 0.5 | 0.5
• Home Page | ▪ When user lands on the homepage ,will see list products ▪ Categories will be there like trending products, top deals & recently viewed. ▪ On selecting the product it will redirect to product details page. | 3 | 2
• Search and Filter Products: | Enter platform and initiate search. Apply filters such as name, brand, SKU, color, etc. Browse through search results. | 3 | 3
• Product Selection: | Click on a product for detailed information. Add selected products to the shopping cart. | 1 | 1
• Order History: | User can see all the order’s history. | 1 | 1
• Checkout Process: | Access shopping cart. Review selected items. Proceed to checkout. Enter shipping details. Apply discount codes if available. Choose delivery options. Select payment method (PayPal, credit card). Confirm and place order. | 2 | 2
• Order Tracking: | Receive order confirmation. Access order tracking with Purolator. Receive notifications for delivery updates. | 3 | 3
User Flow for Building Developers and Designers:
• Sign Up / Register Page | o Users will be able to register on the website by providing below details:- ▪ Full Name ▪ Email id ▪ Password and Confirm Password. ▪ Terms and Conditions checkbox ▪ Differentiate between regular customer and building professional account. ▪ Users will receive an OTP over his/her email id for verification. ▪ Option to Sign In - If already registered.
• Login Page | o Users will be able to Login into the website using below details:- ▪ Email id ▪ Password ▪ Forgot Password Hyperlink ▪ Register - If account does not exists.
• Forgot Password | ▪ This option would be used by users in case they forgets their password. ▪ They need to enter the e-mail Id on which the password reset link would be sent to reset the password.
• Home Page: | ▪ Search ▪ My projects. ▪ Book appointment. ▪ Business Analytics. ▪ Notification from admin regarding configured pricing. | 3 | 1
• My projects | ▪ By selecting this option there will be list of projects and an option to create a new project. | 3 | 2
• Book Appointment | ▪ By this option developer can book an appointment to visit the store. | 1 | 1
• Project Creation and Labeling: | Access dashboard after login. Create new projects under client profiles. Label projects for organization. | 2 | 2
• Product Selection for Projects: | Utilize enhanced search and filtering. Add products to specific projects. | 3 | 2
• Pricing Configuration and Checkout: | Request configured pricing. There will be an option for admin and developer to chat for pricing. Apply discount codes. Input budget and lead time for each project. Proceed to checkout and payment. | 2 | 2
• CRM Dashboard and Document Upload: | Access CRM dashboard. Monitor pipelines, budgets, and accumulated spend. Upload documents to client profiles. | 3 | 2
• Order Management: | Manage orders under specific projects. Monitor deposit and customer credit. Save payment details and shipping information. Track order status and receive delivery notifications. | 2 | 2
• Reports and Analytics: | Create reports for orders, pipeline, and budget. Access analytics for website deals and campaigns. | 5 | 3
· Communication and Appointments: | Access customer communications tool portal. Receive deal and reduced pricing campaigns. Book showroom visit appointments. | 2 | 2
| Note:- Integration of Hubspot and QuickBooks | 10
Checkout | Option to schedule delivery, date/time calendar will pop-up. | 4 | 5
Sign Up | ▪ On selection of building professional, it will require specific details like description, budget range, experience, etc. | 1 | 1
Home Page | ▪ My Catalogue. | 3 | 1
My projects | ▪ Different tabs will be there for each project. ▪ Search option between the projects. | 3 | 2
My catalogue | • My catalogue ▪ Catalogue needs to be updated every 3 month. ▪ Notification will be sent for the same. | 3 | 2
Book Appointment | ▪ There will be a calendar to do the same. ▪ Appointment history will be shown. ▪ On approval from admin will receive a notification Appointment confirmed. ▪ Will be marked green. | 4 | 4
Pricing Configuration and Checkout | On approval it will open the chat feature for the particular project Option to upload documents. | 2 | 2

## Admin
Admin Flow
24
Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
• User Management: | Create and manage user accounts. Reset passwords and manage access. | 1
• Product Management: | Add, edit, and remove products from the catalog. Update product information. | 2
Order Management | Monitor and manage all customer orders. Process and fulfill orders. Match customer orders to supplier purchase orders. | 2
• CRM Integration and Document Management: | Monitor and manage CRM data. Access and update client profiles. Review and manage document uploads. | 3
• Discount Code and Payment Management: | Create and manage discount codes. Monitor and manage payment transactions. | 2
• Delivery Management and Customer Communication: | Track delivery status. Coordinate with warehouses. Communicate with customers regarding orders. Approve developer project. On approval can manage their projects by removing and adding products. Can exchange docs on the project chat option, Coordinate with developers | 5
Reporting and Analytics: | Generate reports on product sales, order trends, etc. Analyze CRM data for customer relationships. | 3
• Content Management and User Analytics: | Manage content on the platform. Monitor and analyze user interactions. | 2
• Platform Customization and Audit Trail: | Customize platform features. Maintain an audit trail of key actions. | 2
Appointment Management | Admin will approve the appointments. | 2

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart - Neoteric Platform Website | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2023-12-18 | 2024-05-13
[8 empty] | Total Project Effort (in person days) | 164
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 106
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2023-12-18 | 2023-12-29 | 1 | 10 |  | 2024-01-03
4 | Website Design (End User & Developer) | 2023-12-19 | 2024-01-03 | 0 | 12 | Design
6 | Dashboard/Web Panel Design | 2023-12-19 | 2023-12-28 | 1 | 8 | Design |  |  |  | ;
9 | End User & Developer_Website | 2024-01-04 | 2024-04-10 | 1 | 70.5
11 | API+Admin | 2024-01-04 | 2024-03-27 | 60 | 73.5
14 | QA Testing | 2024-01-12 | 2024-05-02 | 80 | 80
15 | UAT Testing | 2024-02-02 | 2024-05-08 | 75 | 69
16 | GO-LIVE | 2024-05-10 | 2024-05-13 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E13: Kashish: Sum of Total Development Effort Days needs to be entered by TL.