## Important Information
Detailed WBS for Playground Booking Application
PROJECT TITLE |  |  | Playground Booking Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Chetna¦¦Rishav
CLIENT NAME |  |  | Eduardo
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End Users, Sub Admin & Admin
Business Need | Client have different playgrounds where users come to play matches, ground managers are there to collect fees. Client wants a solution where users can book for the matches, pay online or offline.
How to achieve? | We will develop an application where end users can see the playgrounds availability and can book them from the app by making online payment or offline. Sub Admin panel for ground managers to verify the payments and an admin panel to manage the whole platform.
User Types and Their Platforms | End User | Application
| Sub Admin | Web Panel
| Admin | Web Panel
Tech Stack | End User | Flutter / React Native
| Sub Admin | Node.js / PHP (Laravel)
| Admin | Node.js / PHP (Laravel)
| Backend (API) | Node.js / PHP (Laravel)
| Database | MongoDB / MySql
| Back-end | PHP (Laravel)

## EndUser_Mobile App
Mobile App Flow for End User
|  | 22 | 11.5
Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
· Splash Screen | • The company logo will be visible on the splash screen. | 0.5
· Sign Up / Register Page | • Users will be able to register on the Application by providing below details:- • Full Name • Email id • Password and Confirm Password. • Terms and Conditions checkbox • Users will receive an OTP over his/her email id for verification. • Option to Sign In - If already registered. • Location Access • Social sign up | 2 | 1
· Login Page | • Users will be able to Login into the Application using below details:- • Email id • Password • Forgot Password Hyperlink • Register - If account does not exists. • Social Login. | 1 | 0.5
· Forgot Password | • This option would be used by users in case they forgets their password. • They need to enter the e-mail Id on which the password reset link would be sent to reset the password. | 0.5 | 0.5
· Home Screen | • Landing page of the app home screen displays the following sections or details:- • Hamburger Menu -Logo of the Application • Find a Playgrounds • Notifications • My Account • About Us • Contact Us. • Terms & Conditions | 3
· Explore Playgrounds: | • Users browse through a list of available sports playgrounds. • Users will be able to view details such as location, facilities, and availability. | 2 | 1
· View Playground Details: | • Users select a specific playground to view detailed information. • Details include available time slots, rules, and rental fees, terms & conditions. | 2 | 1
· Book Playground: | • Users will be able to choose a suitable time slot and date. • Enter booking details: Name, team name, member details, and match type, etc. • Confirm booking and proceed to payment. | 4 | 2
Payment | • Users make an online payment through the app. • Receive a confirmation with a unique booking ID. | 3 | 2
· Confirmation and Check-in: | • Users receive a confirmation screen with booking details and unique ID. • Show the unique ID to the ground manager during check-in. | 1 | 1
· Notification | • User can see all the required notifications, updates, and alerts here. | 1 | 1
· About Us | • This section would describe about the Application with text and images. | 0.5 | 0.5
· Contact Us | • This section would have the Contact Us form to submit the query or feedback. | 0.5 | 0.5
· My Account | • Profile to update the below details:- • Name • Mobile Number • Profile Picture • E-mail ID (If changed then the same needs to be verified through OTP) • Update Password (Current Password, New Password and Confirm New Password) • Sign Out • Delete Account | 1 | 0.5

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin
Sub-Admin Flow
8
Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days)
· Log In: | • Ground manager logs into the sub-admin panel. | 1
· Verify Unique ID: | • Ground manager accesses a section to verify user bookings. • Enters the unique ID provided by the user during check-in. | 1
· Check Booking Details: | • Confirms the booking details, including team name, members, and match type. | 2
· Verify Payment: | • If the user has paid online, the system confirms the payment status. • If offline payment, confirm the cash collection. | 2
· Record Offline Payments: | • If the user pays offline, the ground manager updates the payment status manually. | 1
· Expense Entry: | • Sub admin will be able to add the entries of the expenses which will be monitored at report creation. | 1

## Admin
Admin Flow
12
Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
· Log In: | o Admin logs into the admin panel. | 1
· Manage Playgrounds: | o View and manage all sports playgrounds, including availability and details. | 2
· Manage Bookings: | o Access a section to view and manage all bookings. o Check payment status and unique IDs. | 1
· Calculate Revenue/Profit: | o The system automatically calculates revenue and profit based on bookings and expenses. | 2
· View Payment Flow: | o Admin monitors the payment flow, distinguishing between online and offline payments. | 2
· System Overview: | o Access a comprehensive dashboard providing an overview of the entire system. | 1
· Notification Management | o Admin will be able to view and manage notifications from the backend. | 1
· Contact Us Management | o Admin will be able to view and manage contact us queries from the backend. | 1
· Content Management | o Admin will be able to update and add text for About Us o Admin will be able to update and add text for Terms and Condition | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart - Playground Booking Application | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2023-12-18 | 2024-03-07
[8 empty] | Total Project Effort (in person days) | 65.5
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 59
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2023-12-18 | 2023-12-29 | 1 | 10 |  | 2024-01-03
2 | UI/UX (End User) | 2023-12-19 | 2024-01-03 | 0 | 12 | Design
7 | End User_Mobile Application | 2024-01-04 | 2024-02-02 | 1 | 22
11 | API+Admin | 2024-01-04 | 2024-02-06 | 24 | 23.5
12 | Sub-Admin | 2024-02-14 | 2024-02-23 | 30 | 8
14 | QA Testing | 2024-01-12 | 2024-02-22 | 30 | 30
15 | UAT Testing | 2024-02-02 | 2024-02-28 | 1 | 19
16 | GO-LIVE | 2024-03-01 | 2024-03-07 | 1 | 5
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E13: Kashish: Sum of Total Development Effort Days needs to be entered by TL.