## Important Information
Detailed WBS for Mental Wellness Event Application
PROJECT TITLE |  |  | Mental Wellness Event Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Rahul Sharma
CLIENT NAME |  |  | Stefanie Hughes
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End Users, Vendor & Admin
Business Need | Client is looking for an application where users can visit and view the live session going on in an event. User will also view different users, speakers and vendors. User can view the vendor products and can interact with them. Admin will be able to stream live sessions going over the stage and manage different users over the app.
How to achieve? | Providing an app for the end users to browse in all of the content, web panel for vendors to showcase products/ad's and a super admin panel to manage the whole platform.
User Types and Their Platforms | End User | Application
| Vendors | Web Panel
| Admin | Web Panel
Tech Stack | Mobile Application | React Native/ Flutter
| Web Panel | Angular/HTML CSS
| Admin | Angular/HTML CSS
| Backend (API) | Node.js/PHP
| Database | MongoDB/MySQL
| Back-end | PHP (Laravel)

## End_User_App
Mobile App Flow for End User
|  |  | 23 | 12 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
Splash Screen |  | • User will view the logo and company name on the application.
Sign-Up |  | • Users can register using their name, email address, mobile number and password on the app. • Users will receive an OTP to verify their email id. • After verification user will be redirected on home screen | 2 | 1
Sign-in |  | • Users can sign in using their Email address and password on the app. • If Users forget their password, users will click forget password link and enter their registered email id. • Users can write the OTP and set a new password | 0 | 0
Home Screen |  | • User will view different features as hamburger/bottom menu on screen such as: Categories Events Messages Carousel Notification Account | 1
Categories |  | • User will be able to view multiple categories and select any one from the list. • After selecting the category it will lead to the seminar screen user have selected. | 2 | 1
Events |  | • User will be able to view list of events and can join any of them after subscribing. • User will pay the subscription amount and will get a unique ID. • On the basis of the unique ID user can join the event. • User can view all the details of the event • Users will be able to view the live streams. Live-stream will include the view of the stage on live basis | 4 | 2
Speakers |  | User will be able to view the details of the speaekr. | 2 | 1
Vendors |  | Users will be able to view the multiple vendors and the products User will be redirected to the vendor website for the purchase Users will be able to send text message to the vendors | 5 | 3
Attendees |  | Users will be able to view the attendees who have joined the event Users will be able to send the text message to the attendees | 2 | 1
Messages |  | • User can view chat history with the vendors and users and chat with them | 3 | 2
Notifications |  | • Users will receive different notification. | 1 | 1
Settings |  | • Users can set the profile settings on the basis of their preference such as password or privacy settings | 1
Log Out |  | • Users will be able to log-out and able to delete their account from the application.

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel
Web Panel Flow for Vendors
|  |  | 16 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)
Landing page |  | • Landing page would have authentication
Sign-Up |  | • Vendors can register using their name, email address, mobile number and password on the Website. • Vendors will receive an OTP to verify their email id. • After verification user will be redirected on home screen | 2
Sign-in |  | • Vendors can sign in using their Email address and password in the Website. • If Vendors forget their password, users will click forget password link and enter their registered email id. • Vendors can write the OTP and set a new password
Home Screen |  | • Vendors will view different features as hamburger/bottom menu on screen such as: Add Products Messages Notifications Account | 2
Add Products/ Advertisement |  | • Vendors will be able to add, view and delete their ads from the carousel. • To advertise vendor can select the subscription based on the duration. • The advertisement will be reviewed by the super admin before publishing it on the carousel. | 6
Messages |  | • Vendor will be able to text with the users | 4
Notifications |  | • Vendors will receive different notification | 1
Settings |  | Vendor will be able to view different settings in this tab | 1

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
|  |  | 17 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
Login |  | • Admin will be able to login into the admin panel using username and password. | 1
Dashboard |  | • Quick links of given feature will be visible such as:- User management Products Management Live Stream Management Speakers Management Notification management Content Management | 1
User Management (End Users & Vendors) |  | • Admin will be able to manage the users from the backend. • Admin will be able to activate/deactivate the account of the users from the backend. | 1
Products Management |  | • Admin will be able to view and delete products. | 2
Event Management |  | • User will be able to add, edit, delete the events. | 2
Live Stream Management |  | • User will be able to start the live stream of the event stage show. | 5
Speakers Management |  | • Admin can add, edit, delete the speakers details along with their bios and handouts. | 3
Notifications Management |  | • Admin can send the notifications to the end users. | 1
Content Management |  | • Admin will be able to manage (Add/View/Edit) the static contents. Terms and Conditions Privacy Policy | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart - Mental Wellness Event Application | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2023-11-20 | 2024-02-21
[8 empty] | Total Project Effort (in person days) | 90
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 68
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2023-11-20 | 2023-12-01 | 1 | 10 |  | 2023-12-06
2 | UI/UX (Application) | 2023-11-21 | 2023-12-06 | 0 | 12 | Design
5 | Website Design (Web Panel) | 2023-11-21 | 2023-12-04 | 1 | 10 | Design
7 | Application_Mobile Application | 2023-12-07 | 2024-01-08 | 1 | 23
10 | Web Panel_Website | 2024-01-08 | 2024-01-29 | 23 | 16
11 | API+Admin | 2023-12-07 | 2024-01-30 | 39 | 29
14 | QA Testing | 2023-12-15 | 2024-02-07 | 39 | 39
15 | UAT Testing | 2024-01-05 | 2024-02-13 | 1 | 28
16 | GO-LIVE | 2024-02-15 | 2024-02-21 | 1 | 5
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E14: Kashish: Sum of Total Development Effort Days needs to be entered by TL.