## Important Information
Detailed WBS for Find A Lawyer App
PROJECT TITLE |  |  | Find A Mobile Lawyer
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Srishti Singh
CLIENT NAME |  |  | Yinka
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End Users & Admin
Business Need | Business need is to have a platform where users will be able to search for Lawyers on the basis of their experience and specialization and can chat with them.
How to achieve? | As a solution we will develop an application where users will be able to register themselves, search for Lawyers and chat with them. Whereas lawyers will register and can connect with users who needs their service.
User Types and Their Platforms | EndUser | Application
| Admin | Admin Panel
Tech Stack | Application | ReactNative/flutter
| Admin | PHP(Laravel)/Node.js
| Backend (API) | PHP(Laravel)/Node.js/java
| Database | MySQL/MongoDB
| Back-end | PHP (Laravel)

## EndUser_Mobile App
Mobile App Flow for End User
|  | 28 | 16
Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
Splash Screen | The company logo will be visible on the splash screen.
Sign Up / Register Page | Full Name Email id Password and Confirm Password. Terms and Conditions checkbox Option to select between A Lawyer or A User Users will receive an OTP over his/her email id for verification. Option to Sign In - If already registered. Location Access | 2 | 1
Login Page | Email id Password Forgot Password Hyperlink Register - If account does not exists.
Forgot Password | This option would be used by users in case they forgets their password. They need to enter the e-mail Id on which the password reset link would be sent to reset the password.
Home Screen For User | Landing page of the app home screen displaying below sections or details:- Hamburger Menu -Logo of the Application, Find a Lawyer, Notifications, Chat Box, My Account, About Us, Contact Us. Lawyers available in the particular area would be visible Search Bar to search for lawyers using keyword (Name and Specialization) | 4 | 3
Find A Lawyer | This option would be used by user to find a lawyer. Search Field would be displayed on the Application to search Lawyers on the basis of:- Name Location Specialization Lawyers list would be displayed on the basis of search List of all the lawyers would be displayed default on home page with below details:- Lawyer Name Lawyer Profile Image Lawyer Specialization Lawyer Experience View Profile button On clicking the View Profile button, user would be redirected to the Lawyer Detail Page: - Lawyer Name Lawyer Profile Image Lawyer Qualification Lawyer Experience Description about Lawyer Chat Now Note:- To use any option user needs to pay a subscription amount then only it will allow to chat. | 5 | 3
Subscription | User can see the active subscription. User can see the past subscription | 2 | 1
Chat Box | User can access all the chats from here. User can send documents in the chat | 3 | 1
Notification | User can see all the notifications here. | 1 | 1
About Us | This section would describe about the Application with text and images | 1 | 1
Contact Us | This section would have the Contact Us form to submit the query or feedback | 1
My Account | Profile to update the below details:- Name Mobile Number E-mail ID (If changed then the same needs to be verified through OTP) Update Password (Current Password, New Password and Confirm New Password) Sign Out Delete Account | 2 | 1
Home Screen For Lawyer’s | Landing page of the app home screen displaying below sections or details:- Logo of the Application. Hamburger Menu – Lawyer Profile, Subscription, Notifications, Chat Box, My Account, About Us, Contact Us. Latest chats will be displayed on the home screen Note:- To make lawyer profile, lawyer’s needs to pay a subscription amount then only they can create their Lawyer profile | 4 | 3
Lawyer Profile | Lawyer Name Lawyer Profile Image Lawyer Qualification Lawyer Experience Lawyer Specialization Description about Lawyer | 3 | 1

## Admin
Admin Flow
10
Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
Login | • Admin will be able to Login into the admin web panel using their login credentials. The admin will use the following credentials such as: o User Name o Password | 1
User Management | • Admin will be able to manage the User from the backend. • Admin will be able to activate/deactivate the account of the User from the backend | 1
Lawyer Profile Management | • Admin would be able to add, update and delete the Lawyer’s details which are displayed on the Application for end users. | 2
Notification Management | • Admin will be able to view and manage notifications from the backend. | 1
Contact Us Management | • Admin will be able to view and manage contact us queries from the backend. | 1
Subscription Management | • Admin will be able to view subscription from the backend. | 3
Content Management | • Admin will be able to update and add text for About Us • Admin will be able to update and add text for Terms and Condition | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart - Find A Mobile Lawyer | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2023-11-27 | 2024-02-14
[8 empty] | Total Project Effort (in person days) | 64
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 58
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2023-11-27 | 2023-12-08 | 1 | 10 |  | 2023-12-11
2 | UI/UX (EndUser) | 2023-11-28 | 2023-12-11 | 0 | 10 | Design
7 | EndUser_Mobile Application | 2023-12-12 | 2024-01-18 | 1 | 28
11 | API+Admin | 2023-12-12 | 2024-01-23 | 31 | 26
14 | QA Testing | 2023-12-20 | 2024-01-31 | 31 | 31
15 | UAT Testing | 2024-01-10 | 2024-02-06 | 1 | 20
16 | GO-LIVE | 2024-02-08 | 2024-02-14 | 1 | 5
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E12: Kashish: Sum of Total Development Effort Days needs to be entered by TL.