## Important Information
Detailed WBS for Coal Trading App
PROJECT TITLE |  |  | Coal Trading App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Srishti¦¦Rishav
CLIENT NAME |  |  | David
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End user & Admin
Business Need | Business need is that client have a coal mine and he wants to turn it’s half into a tradable commodity, which will be available for end users to buy and sell it while the rates are fluctuating.
How to achieve? | We will provide an app where users will be able to buy and sell coal at the real time rate .An admin panel to maintain all the stocks and rate of the coal.
User Types and Their Platforms | End User | Application
| Admin | Admin Panel
Tech Stack | Application | Flutter/React Native
| Admin | PHP(Laravel)/Node.js
| Backend (API) | PHP(Laravel)/Node.js/java
| Database | MySQL/MongoDB
| Back-end | PHP (Laravel)

## User_Mobile App
Mobile App Flow for User
|  | 46 | 36
Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
● Splash Screen | ▪ The company logo will be visible on the splash screen.
● Sign Up / Register Page | o Users will be able to register on the Application by providing below details:- ▪ Full Name ▪ Email id ▪ Password and Confirm Password. ▪ Terms and Conditions checkbox ▪ Users will receive an OTP over his/her email id for verification. ▪ Option to Sign In - If already registered. | 2 | 1
● Login Page | o Users will be able to Login into the Application using below details:- ▪ Email id ▪ Password ▪ Forgot Password Hyperlink ▪ Register - If account does not exists. | 1 | 1
● Forgot Password | ▪ This option would be used by users in case they forgets their password. ▪ They need to enter the e-mail Id on which the password reset link would be sent to reset the password.
● Home Screen For User | ▪ Landing page of the app home screen displaying below sections or details:- ▪ Hamburger Menu -Logo of the Application, My coal, Notifications, History, My Account, About Us, Contact Us. | 5 | 4
● My Coal | ▪ User can see the purchased coal quantity. ▪ User can see the rate of the purchased coal. | 3 | 2
● View Listed Coal: | ▪ User logs in and sees the list of available coal for investment. ▪ Accesses details like material, stock available, and quality. | 2 | 1
● Select Quantity and Purchase: | ▪ User selects the desired quantity of coal to purchase. ▪ Submits the purchase request. ▪ Payment gateway PayPal/Stripe | 5 | 4
● Backend Price Assignment: | ▪ Admin, from the backend, assigns the price and value to the purchased coal based on quality and minerals. | 2 | 3
● Tokenization Process: | ▪ Coal purchased by the user is tokenized and represented as tradable assets. ▪ User receives a confirmation of successful tokenization. | 6 | 4
● Graph of Current Prices: | ▪ User views a graph displaying the current market prices of the purchased coal. ▪ Prices are determined by the backend value assigned by the admin. | 5 | 3
● Redeem/Return Coal: | ▪ User decides to redeem/return the coal. ▪ The backend calculates the value based on quality and minerals. | 4 | 4
● Profit Calculation: | ▪ User receives money in return for the coal, gaining profit as the value is calculated based on quality. | 2 | 2
● Smart Contract Execution: | ▪ Smart contract handles the tokenization, pricing, and redemption processes securely. | 3 | 2
● Notification | ▪ User can see all the notifications here | 1 | 1
● History | ▪ User can see all the transactions history. | 1 | 1
● About Us | ▪ This section would describe about the Application with text and images. | 1 | 1
● Contact Us | ▪ This section would have the Contact Us form to submit the query or feedback. | 1 | 1
● My Account | ▪ Profile to update the below details:- ▪ Name ▪ Mobile Number ▪ E-mail ID (If changed then the same needs to be verified through OTP) ▪ Update Password (Current Password, New Password and Confirm New Password) ▪ Sign Out ▪ Delete Account | 2 | 1

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
44
Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
● User Management: | ▪ Admin manages user registrations and profiles. ▪ Ensures the security and integrity of user data. | 4
● Coal Listing and Details: | ▪ Admin adds new coal listings with detailed information (material, stock, quality). ▪ Updates existing coal details. | 5
● Price Assignment: | ▪ Admin sets the backend price and value for coal based on quality and minerals. ▪ Ensures fair and transparent pricing. | 3
● Tokenization Management: | ▪ Admin oversees the tokenization process of purchased coal. ▪ Manages the tokenized assets securely. | 5
● Graph Generation: | ▪ Admin inputs backend values for coal, which dynamically generate the graph of current market prices for users. | 6
● Redemption Process: | ▪ Manages the process of users redeeming/returning coal. ▪ Coordinates with the backend calculation of coal value. | 4
● Smart Contract Monitoring: | ▪ Admin monitors and ensures the proper execution of smart contracts. ▪ Resolves any issues related to tokenization, pricing, or redemption. | 5
● Notification Management | ▪ Admin will be able to view and manage notifications from the backend. | 2
● Contact Us Management | ▪ Admin will be able to view and manage contact us queries from the backend. | 1
● Inventory Management | ▪ Admin will be able to view & manage the inventory from the backend. | 5
● Content Management | ▪ Admin will be able to update and add text for About Us ▪ Admin will be able to update and add text for Terms and Condition. | 4

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart - Coal Trading App | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2023-12-18 | 2024-05-13
[8 empty] | Total Project Effort (in person days) | 138
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 106
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2023-12-18 | 2023-12-29 | 1 | 10 |  | 2024-01-03
2 | UI/UX (End User) | 2023-12-19 | 2024-01-03 | 0 | 12 | Design
3 | UI/UX (Admin) | 2023-12-19 | 2023-12-18 | 0 | 0 | Design
4 | Website Design (End User) | 2023-12-19 | 2023-12-18 | 0 | 0 | Design
5 | Website Design (Admin) | 2023-12-19 | 2023-12-18 | 1 | 0 | Design
7 | End User_Mobile Application | 2024-01-04 | 2024-03-07 | 1 | 46
8 | Admin_Mobile Application | 2024-01-05 | 2024-01-04 | 1 | 0
9 | End User_Website | 2024-01-22 | 2024-01-19 | 13 | 0
10 | Admin_Website | 2024-01-23 | 2024-01-22 | 14 | 0
11 | API+Admin | 2024-01-04 | 2024-03-07 | 46 | 80
14 | QA Testing | 2024-01-12 | 2024-05-02 | 80 | 80
15 | UAT Testing | 2024-02-02 | 2024-05-08 | 1 | 69
16 | GO-LIVE | 2024-05-10 | 2024-05-13 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY(WORKDAY(H8,[Lead Days]),1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E18: Kashish: Sum of Total Development Effort Days needs to be entered by TL.