## Important Information
Detailed WBS for Lawyer Connect
PROJECT TITLE |  |  | Lawyer Connect Mobile Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Srishti Singh
CLIENT NAME |  |  | Juan Manuel
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End Users, Lawyers & Admin
Business Need | Business need is to have a platform where users will be able to search for Lawyers on the basis of their experience and specialization and can chat with them.
How to achieve? | As a solution we will develop an application where users will be able to register themselves, search for Lawyers and chat with them. Whereas lawyers will have another app to register and can connect with users who needs their service. An admin panel to manage the whole platform .
User Types and Their Platforms | End user | Application
| Lawyer's | Application
| Admin | Admin Panel
Tech Stack | End user App | Flutter/React Native
| Lawyer's App | Flutter/React Native
| Admin | Angular
| Backend (API) | Node.js/PHP
| Database | MySQL/MongoDB
| Back-end | PHP (Laravel)

## User_Mobile App
Mobile App Flow for User
|  | 28 | 14
Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
Splash Screen | o The company logo will be visible on the splash screen. | 2 | 1
Sign Up | o Users will be able to register on the Application by providing below details:-  Full Name  Email id  Password and Confirm Password.  Terms and Conditions checkbox  Users will receive an OTP over his/her email id for verification.  Option to Sign In - If already registered.  Location Access Social SignUp
Login Page | o Users will be able to Login into the Application using below details:-  Email id  Password  Forgot Password Hyperlink  Register - If account does not exists. Social Login
Forgot Password | o This option would be used by users in case they forgets their password. o They need to enter the e-mail Id on which the password reset link would be sent to reset the password.
Home Screen For User | • Landing page of the app home screen displaying below sections or details:- o Hamburger Menu -Logo of the Application, Find a Lawyer, Notifications, My Queries, My chats, My Account, About Us, Contact Us. o Public forum tab on selecting this user will land to a page where all the questions from different users will be visible. o Lawyers specialization category would be visible from selecting there it will open lawyers eligible in that specialization. o Search Bar to search for lawyers using keyword (Name and Specialization) | 3 | 2
Find A Lawyer | o This option would be used by user to find a lawyer. o Search Field would be displayed on the Application to search Lawyers on the basis of:-  Name  Location  Specialization  Lawyers list would be displayed on the basis of search o List of all the lawyers would be displayed default on Specialization page with below details:-  Lawyer Name  Lawyer Profile Image  Lawyer Specialization  Lawyer Experience  View Profile button o On clicking the View Profile button, user would be redirected to the Lawyer Detail Page: -  Lawyer Name  Lawyer Profile Image  Lawyer Qualification  Lawyer Experience  Description about Lawyer  Chat Now | 8 | 4
Public Forum | o User can see the different questions and answers by lawyers. o User can see post their question on the platform as well which will be answered by lawyer. o Search option with related keywords. | 5 | 3
Chat Box | o User can access all the chats from here. o User can send documents in the chat in form of image or pdf. | 3 | 1
Notification | o User can see all the notifications here. | 2 | 1
About Us | o This section would describe about the Application with text and images. | 2 | 1
Contact Us | o This section would have the Contact Us form to submit the query or feedback. | 1
My Account | o Profile to update the below details:-  Name  Mobile Number  E-mail ID (If changed then the same needs to be verified through OTP)  Update Password (Current Password, New Password and Confirm New Password)  Sign Out  Delete Account | 2 | 1

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## Lawyer_Mobile App
Mobile App Flow for Lawyer
|  | 26 | 11
Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
Splash Screen | o The company logo will be visible on the splash scree. | 2 | 1
Sign Up | o Lawyers will be able to register on the Application by providing below details:-  Full Name  Profile Picture  Email address  Password and Confirm Password.  Terms and Conditions checkbox  Bar ID  Users will receive an OTP over his/her email id for verification.  Option to Sign In - If already registered.  Location Access  Social Sign Up
Login Page | o Lawyers will be able to Login into the Application using below details:-  Email id  Password  Forgot Password Hyperlink  Social login  Register - If account does not exists.
Forgot Password | o This option would be used by lawyers in case they forgets their password. o They need to enter the e-mail Id on which the password reset link would be sent to reset the password.
Home Screen For Lawyer’s | Landing page of the app home screen displaying below sections or details:- • Hamburger Menu–Logo of the Application, Lawyer Profile, Subscription, Notifications, Public Forum, Chat Box, My Account, About Us, Contact Us. • Latest chats will be displayed on the home screen. Note:- To make lawyer profile, lawyer’s needs to pay a subscription amount then only they can create their Lawyer profile. | 3 | 2
Lawyer Profile |  Lawyer Name  Lawyer Profile Image  Lawyer Qualification  Lawyer Experience  Lawyer Specialization  Description about Lawyer | 4 | 1
Subscription | o Lawyer can see the active subscription. o Lawyer can see the past subscription. | 3 | 1
Chat Box | o Lawyer can access all the chats from here. o Lawyer can download the documents in the device. | 3 | 1
Notification | o Lawyer can see all the notifications here. o When user send message. | 2 | 1
Public Forum | o Lawyer can see all questions that are not answered on the platform here and can answer them. o Lawyer can search for any particular keywords to find any question. | 4 | 2
About Us | o This section would describe about the Application with text and images. | 2 | 1
Contact Us | o This section would have the Contact Us form to submit the query or feedback. | 1
My Account | • Profile to update the below details:- o Name o Mobile Number o Profile Image o E-mail ID (If changed then the same needs to be verified through OTP) o Update Password (Current Password, New Password and Confirm New Password) o Sign Out o Delete Account | 2 | 1

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
12
Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
Login | • Admin will be able to Login into the admin web panel using their login credentials. The admin will use the following credentials such as: o User Name o Password | 1
User Management | • Admin will be able to manage the User from the backend. • Admin will be able to activate/deactivate the account of the User from the backend | 1
Lawyer Profile Management | • Admin would be able to add, update and delete the Lawyer’s details which are displayed on the Application for end users. | 2
Public Forum Management | • Admin would be able to see all the questions and answers of the platform and can remove if required. | 3
Notification Management | • Admin will be able to view and manage notifications from the backend. | 1
Contact Us Management | • Admin will be able to view and manage contact us queries from the backend. | 1
Subscription Management | • Admin will be able to view subscription from the backend • Admin will be able to set the subscription amount. | 2
Content Management | • Admin will be able to update and add text for About Us • Admin will be able to update and add text for Terms and Condition | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart - Lawyer Connect Mobile Application | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2023-12-11 | 2024-03-29
[8 empty] | Total Project Effort (in person days) | 107
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 80
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2023-12-11 | 2023-12-22 | 1 | 10 |  | 2023-12-22
2 | UI/UX (End user) | 2023-12-12 | 2023-12-21 | 0 | 8 | Design
3 | UI/UX (Lawyer's) | 2023-12-12 | 2023-12-21 | 0 | 8 | Design
7 | End user_Mobile Application | 2023-12-25 | 2024-01-31 | 1 | 28
8 | Lawyer's_Mobile Application | 2024-02-01 | 2024-03-07 | 28 | 26
11 | API+Admin | 2023-12-25 | 2024-03-07 | 54 | 37
14 | QA Testing | 2024-01-02 | 2024-03-15 | 54 | 54
15 | UAT Testing | 2024-01-23 | 2024-03-21 | 1 | 43
16 | GO-LIVE | 2024-03-25 | 2024-03-29 | 1 | 5
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY(WORKDAY(H8,[Lead Days]),1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E14: Kashish: Sum of Total Development Effort Days needs to be entered by TL.