## Important Information
Detailed WBS of Real Estate Digital Application
PROJECT TITLE |  |  | ReaL Estate Digital Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Rahul Sharma
CLIENT NAME |  |  | Aline Martins de Almeida
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | Users and Admin
Business Need | Client is looking to build a Real Estate Application which would be scalable, reliable and dynamic where she can represent real estate services that creates a positive first impression with the target audience. The Application needs to look credible and build trust with potential users.
How to achieve? | Proposed project comprises the design and development of a Real estate application. There will be 2 panels, User and Admin. User will create an account, view residential and commercial property & request call back and manage profile. Admin will manage all the property from backend.
User Types and Their Platforms | End-Users | User
| Admin | Admin
Tech Stack | Front end | Flutter/React native
| Back-end | PHP/Laravel/Nodejs
| Back-end | PHP (Laravel)

## End-user_Mobile App
Mobile App Flow for End-Useer
TOTAL DAYS |  |  |  | 16 | 30
Actors | Modules | Sub - Modules | Notes | API (in days) | Mobile App Development (in days)
User | Splash screen | Splash screen | • User will be able to view splash screen of the app with company logo and the Application Name
| Sign Up | Sign Up | • The User will be able to sign up on the platform by using their:  First name and last name  Email  Mobile Number  Password  Confirm password  Agree Privacy policy | 1 | 2
| Login | Login | • The User will be able to Login on the platform using their login credentials that they have created during the sign up process. The User can use the following credentials such as the: o Email Address /Mobile number o Password
| Forget Password | Forget Password | • If user forget the password then simply user clicking on forgot password link and where user has to fill the email id. • After entering the email id user will get an OTP on the email that user has to fill into the OTP field.
| Home Menu | Home Menu | • Users will be able to view the promotional banner in the carousel view. • User will be able to select between rent or sale • User will be able to view the different types of services offered in grid view. • Once user clicks the service, they will be moved to the service description screen to view the details. • User will be able to view the customer testimonials in carousel view. | 4 | 8
| Properties Menu | Properties Menu | • Users will be able to view the list of properties available in the platform. • User will view the details like, property name, images, overview in the list view. • Once user clicks the property, they will be moved to the property description screen to view the details. | 2 | 4
| Property Description Screen | Property Description Screen | • User will be able to view the property details. • User will be able to view the property name, overview benefits. • User will be able to view the images. • User will have an option to view the property in 3rd tour. • User will be able to view the address location. • User will be able to shortlist the property. • User will be able to request a call back.  User will enter the name.  User will enter the email address.  User will enter the mobile number.  User will be able to enter the preferred form of contact. (email/phone)  User will be able to select the preferred time for call.  User will enter the description and submit the details. | 3 | 6
| Resources Menu | Resources Menu | • User will be able to view the articles, blogs, e-books and etc., • User will have an option to subscribe the newsletter by entering email address. • User can share the articles, blogs and e-books via third party integration. | 4 | 8
| Hamburger Menu | • Profile | User will be able to view and edit the profile details. (I.e. First name, last name, email address, mobile number. | 1 | 1
|  | • Shortlisted Property | User will be able to view and manage the shortlisted property. | 1 | 0.5
|  | • About Us: | User will be able to view about the company. |  | 0.5
|  | • Privacy Policy: | User will be able to view the privacy policy.
|  | • Terms and conditions | User will be able to view the terms and conditions.
|  | • Logout: | User will be able to logout the application.

## UserType1_Website (hidden)
Website Flow for <UserType1>
TOTAL DAYS |  |  |  | 0 | 0
Actors | Modules | Sub - Modules | Notes | API Development (in days) | Website Development (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for <UserType2>
TOTAL DAYS |  |  |  | 0 | 0
Actors | Modules | Sub - Modules | Notes | API (in days) | Mobile App Development (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
TOTAL DAYS |  |  |  | 0 | 0
Actors | Modules | Sub - Modules | Notes | API Development (in days) | Website Development (in days)

## WebPanel (hidden)
WebPanel Flow
TOTAL DAYS |  |  |  | 0
Actors | Modules | Sub - Modules | Notes | TeacherPanel Development (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
TOTAL DAYS |  |  |  | 0
Actors | Modules | Sub - Modules | Notes | Sub-Admin Development

## Admin
Web Flow for Admin
TOTAL DAYS |  |  |  | 10
Actors | Modules | Sub - Modules | Notes | Development
Admin | User Management | User Management | • Admin will be able to manage all the users from the backend. • Admin will be able to view the user details.(Name, email address, mobile number and orders) • Admin will be able to activate and deactivate any of the users from the platform. | 1
| Property Management | Property Management | • Admin will be able to manage the property from backend. • Admin will be able to add /Edit/ Delete property from backend. • Admin will be able to view/search the list of all property from backend. | 3
| Enquiry Management | Enquiry Management | • Admin will be able to view and manage all the enquiry from the user. • Admin will filter by start date and end date to view the enquiry details. • Admin can download the enquiry details In PDF/Excel. | 3
| Content Management | Content Management | • Admin will be able to manage (Add/View/Edit) the static contents. Following static contents will be managed by the Admin:- o Resources – Blogs, e-book and etc., o Promotional Banner. o Terms of conditions o Privacy policy o About us | 3

## Gantt_Chart Summary
Draftt Gantt Chart - Real Estate Application | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-08 | 2024-03-29
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days) |  |  | Total Project Effort (in person days) | 68
1 | FSD Creation and Approval | 2024-01-08 | 2024-01-19 | 1 | 10 |  | 2024-01-24 | Total Duration (in business days) | 60
2 | UI/UX (End-Users) | 2024-01-09 | 2024-01-24 | 0 | 12 | Design
3 | #REF! | 2024-01-09 | 2024-01-08 | 0 |  | Design
4 | Website Design (End-Users) | 2024-01-09 | 2024-01-08 | 0 |  | Design
5 | #REF! | 2024-01-09 | 2024-01-08 | 1 |  | Design
6 | Dashboard/Web Panel Design | 2024-01-09 | 2024-01-08 | 1 |  | Design
7 | UserType1_Mobile Application | 2024-01-25 | 2024-03-06 | 1 | 30
8 | UserType2_Mobile Application | 2024-01-25 | 2024-01-24 |  | 0
9 | End-Users_Website | 2024-01-24 | 2024-01-23 |  | 0 |  |  |  |  | ;
10 | #REF! | 2024-01-24 | 2024-01-23 |  | 0
11 | API+Admin | 2024-01-25 | 2024-03-07 | 31 | 26
12 | Sub-Admin | 2024-01-24 | 2024-01-23 |  | 0
13 | TeacherPanel | 2024-01-24 | 2024-01-23 |  | 0
14 | QA Testing | 2024-02-02 | 2024-03-15 | 31 | 31
15 | UAT Testing | 2024-02-23 | 2024-03-21 | 1 | 20
16 | GO-LIVE | 2024-03-25 | 2024-03-29 | 1 | 5
Note on E18: ====== ID#AAABDl6aM6s Kashish (2024-01-03 11:25:56) Sum of Total Development Effort Days needs to be entered by TL.