## Important Information
Detailed WBS for GearBook App
PROJECT TITLE |  |  | GearBook App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Chetna Kashyap
CLIENT NAME |  |  | Bob
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End User & Admin
Business Need | Client needs a platform, like if you are going to a new track, you can pick a gear set based on similar tracks, and use them for your driving experience.
How to achieve? | We will develop an application which shows you each Track and Gear combination along with attributes for track size, surface quality, engine, RPM and even notes on performance. Build multiple entries per track to understand how surface affects gear change as the night goes on; then highlight your favorite Gear Set / Track combinations so they are easy to find.
User Types and Their Platforms | End User | Application
| Admin | Admin Panel
Tech Stack | Application | Flutter
| Admin | PHP (Laravel)
| Backend (API) | PHP (Laravel)
| Database | MySql
| Back-end | PHP (Laravel)

## End-users_Mobile App
Mobile App Flow for End Users
|  | 45 | 21 | 0
Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
Splash Screen | • When user open the application screen with company logo and company name appears for 2-3 seconds. | 1
Register Page | • Register with Google. • Register with Apple. • Register using your email. • Terms and conditions tick box | 4 | 1
Login Page | • Login with Google. • Login with Apple. • Login using your email
Tutorial navigator | • After sign up when the users lands on the home screen for the first time, there will be navigator for how to use the application | 5
Home Screen | • Profile icon on the top left corner. • Settings icon on the top right corner. • Search bar in the middle top. • Filter icon • Add a new gear set icon. • List of gears which can be edited or deleted, by swiping left. • Bottom Bar – Gear Book, RPM calculator, Chart, Apps. | 8 | 3
Search Bar | • User can search using different keywords. | 4 | 3
Filters | • When user open the filters, different options like date, track name, track size, track condition, gear ratio, engine. • My favorites. | 3 | 2
Gear setup screen | • Option to add favorite. • Date • Track name • Track size • Surface condition. • Engine • Ring and Pinion • Gear set and ratio • Max rpm –Bar set • Notes • Save to gear book – Button • Clone set up-Button | 3 | 1
RPM Calculator | Target RPM:- • Ring and pinion • Gear set and ratio • Current RPM • Target RPM • Drop down • Save gear set icon Gear Analysis:- • Current Ring and pinion • Current Gear set and ratio • Current RPM • New Gear Set and Ratio • Save Gear Set Button | 6 | 3
Gear Chart | • Drop down on top left. • Chart for 4.11 Rear • Chart for 4.56 Rear • Chart for 4.86 Rear | 5 | 3
App Settings | • My Profile • Email • Race class • Cloud Data Backup Button • Restore Data from the cloud Button • Theme Light And Dark • Tutorial Button. | 6 | 5

## Admin
Admin Flow
|  | 16 | 0
Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
User Management | • List of all registered users. • View user details. • Disable or enable accounts. | 1
Backup management | • Perform manual data backups. • Restore data from previous backups. • Schedule automated backups. | 5
Master's Management | No. of masters is 10 | 10

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart - GearBook App | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-08 | 2024-04-15
[8 empty] | Total Project Effort (in person days) | 82
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 71
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-08 | 2024-01-19 | 1 | 10 |  | 2024-01-19
2 | UI/UX (End User) | 2024-01-09 | 2024-01-08 | 0 | 0 | Design
2 | End User_Mobile Application | 2024-01-22 | 2024-03-22 | 1 | 45
3 | API+Admin | 2024-01-22 | 2024-03-22 | 45 | 37
4 | QA Testing | 2024-01-30 | 2024-04-01 | 45 | 45
5 | UAT Testing | 2024-02-20 | 2024-04-05 | 1 | 34
6 | GO-LIVE | 2024-04-09 | 2024-04-15 | 1 | 5
Note: We have not considered the efforts for design as we will be utilizing your shared design for this project.
Backend Technology - JAVA
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E12: Kashish: Sum of Total Development Effort Days needs to be entered by TL.