## Important Information
Detailed WBS for B2B Inventory Management System
PROJECT TITLE |  |  | Marketplace Website
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Rahul
CLIENT NAME |  |  | Moreno
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End User (Buyer or Seller) and Admin
Business Need | The client wants to develop an information website as a marketplace for buying and selling companies which can provide comprehensive information about each listed company including its category, industry analysis, and region.
How to achieve? | As a solution we are suggesting to develop the website on word Press that will give its cPanel to the client.
User Types and Their Platforms | End User | Website
| Admin | Admin Panel
Tech Stack | Website | Python/Django
| Admin | Python/Django
| Database | PostgreSQL
| Back-end | PHP (Laravel)

## Website
Web App Flow
|  | 19 | 10
Modules | Notes | Web App Development (in days) | API (Node js / PHP (Laravel) (in days)
Header | The header section of the website will contains the following and it will acts as the first point of interaction, offering users a quick overview and facilitating easy navigation to various sections of the site. • Logo • Company Information • Navigation menu o Home Page o Marketplace o Services o About us o Articles/ To know o CTAs  Contact us | 1
Footer | The website footer will located at the bottom of a web page and typically contains essential links, copyright information, and contact details of the company. • Company details o Name o Address o Contact • Quick links o About us o Privacy Policy • Social media links (If any) . | 1
Home Page/logo | • Banner section o The top section of the page can feature a headline, subhead line, a call-to-action (CTA) button, and compelling visuals (images, videos, or sliders). • Hero section o The hero section will conveys the core message of the brand and letting visitors know what the website or business is about. • Call-to-action o Contact Now • Services offered section o This section will give the key reference of services with images, brief descriptions, and CTAs for further exploration. • Articles / To know Section o The section will give a highlights to the articles presented on the platform.
Marketplace Page | The Marketplace page will serve as a virtual space where buyers and sellers can search and post their companies for advertising on the platform. It will also allow buyers to browse through current advertisements of companies available for sale, making it easier for them to find suitable options. Additionally, the platform will allow for sellers to showcase their companies and attract potential buyers. Users can apply the following filters to find the suitable company for themselves. • Category • Industry • Region • Min Price • Max Price | 5 | 3
Filters | Users can apply the following filters to find the suitable company for themselves. • Category • Industry • Region • Min Price • Max Price | 2 | 1
About us | The about us page will offers a concise presentation of key information about the platform and business. It includes details such as the business's approach, experts, partners and frequently asked questions. • About us page will divided in to these different pages or section. o Our Approach o Experts o Partners o Frequently asked questions | 3 | 2
Services Page | The page will outlines the primary offerings or key areas of expertise and services provided by the platform. • Modules • Sell Company • Buy Company | 3 | 2
Articles/To know | The section provide the information where users can access articles and guides that offer valuable insights and tips on the buying or selling process helping them make informed decisions. | 2 | 1
CTAs – Contact Forms | Contact forms section will help the users to reach out to the support team and they can fill the details send them to the team for further processes. | 2 | 1

## Admin
Admin Flow
11
Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
Login | Admin will be able to login using username & password. | 1
Users and content Management | Admin will be able to manage the sellers and Buyers list including contact information. admin can monitor user activities and access logs. admin can Manage and moderate articles, posts, and other content on the platform. they can Control the visibility of content and ensure it complies with platform guidelines. Add, edit, or delete services offered and marketplace listings | 4
Marketplace Management | admin will review and approve/reject company listings posted by sellers. they can manage categories and industries available for selection. admin will be able to monitor and moderate buyer and seller interactions. | 2
FAQs and Documentation: | Admin can manage and update the content on the FAQ and documentation pages from this section | 1
Category management | From this section admin can manage the categories of the contact form | 1
Request management | The section help to process of handling and overseeing incoming requests from users. | 3
Logout | The section will give the option for admin to log out of their accounts.

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Marketplace Website | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-11 | 2024-05-14
[8 empty] | Total Project Effort (in person days) | 55
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 89
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-11 | 2024-01-24 | 1 | 10 |  | 2024-02-01
2 | Website Design (End User) | 2024-01-12 | 2024-02-01 | 0 | 15 | Design
3 | End User_Web App | 2024-02-02 | 2024-02-28 | 1 | 19
4 | API+Admin | 2024-02-02 | 2024-04-30 | 63 | 21
5 | QA Testing | 2024-02-12 | 2024-05-03 | 60 | 60
6 | UAT Testing | 2024-03-04 | 2024-05-09 | 1 | 49
7 | GO-LIVE | 2024-05-13 | 2024-05-14 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])