## Important Information
Detailed WBS for Hotel's Tech Asset Management App
PROJECT TITLE |  |  | Hotel's Tech Asset Management App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Divyika
CLIENT NAME |  |  | Avery
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | Staff, Admin
Business Need | Client needs a platform where staff can sign in to the app and upload data for the project assigned to them. There will be admin and sub-admin. Admin shall be able to manage the dashboards, staff, projects, reports, subadmins, notifications, and content over the mobile app.
How to achieve? | As a solution we suggest to create a mobile app for the staff, where they can login with the credentials provided to them by admin. Staff will be able to upload new data related to the projects allocated to them from admin panel. Staff can also see the previously filled data by them. Admin will be able to manage the dashboard, staff, projects, reports, subadmins, notifications, and content over the mobile app. Subadmin basically be the partners who need to see the data for specific projects and exports the data in particular format. Assumptions: Data export will be in the form of excel, or pdf.
User Types and Their Platforms | Staff | Mobile App
| Sub Admin | Web Panel
| Admin | Web Panel
Tech Stack | Mobile Application | Flutter/ React native
| Sub Admin | HTML CSS/ Angular
| Admin | HTML CSS/ Angular
| Backend (API) | PHP/Node.js
| Database | MySql/Mongo DB
| Back-end | PHP (Laravel)

## Staff_Mobile App
Mobile App Flow for Staff
|  |  | 22 | 9 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
Splash Screen |  | • The launch screen of the Application where staff will be able to view the app’s logo.
Walkthrough Screen |  | Staff will be able to view 3-4 walkthrough screens, which will be helpful for the staff to have an idea about the app. | 1
Authentication | • Sign In | o The Staff will be able to login into the application using the below details: § Email ID § Password o Forgot Password o Clicking on this staff would be redirected to the Forgot Password screen where staff need to enter the below details:- § Email Id (To receive the OTP for verification). § OTP § After the OTP is verified staff would be asked to mention below details in order to change the password:- • New Password • Confirm New Password | 2 | 1
Home Screen |  | • This screen would be the main screen of the application with the following content: Top Bar App Icon Body Project Name Total Data Entered Add New Data Bottom Bar o Home Screen o Data o Account | 3 | 1
Enter Data |  | Staff will be enering data for the project allocated to them: Project Name(auto-filled and non-editable) Room No. Image(upload image/take picture with camera) Mac Address Access Point No. EP Location Submit (Button) This data will be saved over the cloud. | 4 | 2
Data |  | All the data entered previously by the staff will appear here. Record 1 Project Name Room No. Image(View only) Mac Address Access Point No. EP Location Record 2 Record 3 | 5 | 2
Notifications |  | •Staff will receive push and in app notifications for updates or announcement from the admin. | 2 | 1
My Account |  | • Staff will be able to View/Edit their account details. | 2 | 1
Settings |  | • Following details will appear in settings: o Change Password o Static Content § FAQ § Terms & Conditions § About Us | 3 | 1
Logout |  | • Staff will be able to logout of the app, after which they will be redirected to the sign in screen.

## Sub-Admin
Sub-Admin Flow
|  |  | 10 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)
Sign In |  | • Sub-Admin will be able to sign to the web panel with the help of Email ID and Password. • In case sub-admin forgets the password they can recover it using their email ID. Login credentials will be shared by the admin. | 1
Dashboard |  | • Following details will appear on the dashboard:- § Total Data submitted from the app by staff project wise. • Sort • Sub-Admin will have option to sort the dashboard based on:- § Today § This Week § This Month § This Year | 4
Project Management |  | Sub-Admin can manage the project(Add/Edit/Remove) details from here. Sub-Admin can see the data received project wise. Sub-Admin can export the data individually or by multiple selections also. Data can exported in xls or pdf format. | 4
Change Password |  | • Sub-Admin will be able to change their password. | 1
Logout |  | • Sub-Admin will be able logout from the web app, after logout sub-admin will be redirected to the login page.

## Admin
Admin Flow
|  |  | 18 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
Sign In |  | • Admin will be able to sign to the web panel with the help of Email ID and Password. • In case admin forgets the password they can recover it using their email ID. | 1
Dashboard |  | • Following details will appear on the dashboard:- § Total Staff over the Platform § Total Data submitted from the app by staff project wise. • Sort • Admin will have option to sort the dashboard based on:- § Today § This Week § This Month § This Year | 3
Staff Management |  | • Admin will be able to manage the Staff from the backend. • Admin will be able search the Staff profile from the backend. • Admin will be able to see a list of Staff in Grid/Tabular format. • Admin will be able to see the detailed view of the Staff. • Admin will be able to Add/Edit/Delete the Staff. Too add a staff member admin will be required to enter the following details: Email ID Project Name Create Account (After clicking here, a mail with all the login credentials will be sent to the staff members email id.) • Admin will be able to activate/deactivate the account of the Staff from the backend. | 2
Project Management |  | Admin can manage the project(Add/Edit/Remove) details from here. Admin can see the data received project wise. Admin can export the data individually or by multiple selections also. Data can exported in xls or pdf format. | 3
Reports |  | • Following details will appear on the dashboard:- § Total Staff over the Platform § Total Data submitted from the app by staff projectwise • Sort • Admin will have option to sort the dashboard based on:- § Today § This Week § This Month § This Year Admin can export the reports in xls or pdf format. | 4
Sub Admin Management |  | Admin can manage (Add/Edit/Remove) the sub-admin accounts from here. Access for subadmin will be project based so they can see/export the details related to the allocated projects only. | 2
Content Management |  | • Admin will be able to generate and manage the Content from the backend. • Admin will be able to manage the static content from the panel. | 1
Change Password |  | • Admin will be able to change their password. | 1
Push Notification Management |  | • Admin will be able to manage the push notification from the backend. • Admin will be able to send the notifications to the Staff. | 1
Logout |  | • Admin will be able logout from the web app, after logout admin will be redirected to the login page.

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Hotel's Tech Asset Management App | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-17 | 2024-04-01
[8 empty] | Total Project Effort (in person days) | 74
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 54
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-17 | 2024-01-30 | 1 | 10 |  | 2024-02-07
2 | UI/UX (Staff) | 2024-01-18 | 2024-02-07 | 0 | 15 | Design
7 | Staff_Mobile Application | 2024-02-08 | 2024-03-08 | 1 | 22
11 | API+Admin | 2024-02-08 | 2024-02-27 | 14 | 27
12 | Sub-Admin | 2024-02-08 | 2024-02-21 | 1 | 10
14 | QA Testing | 2024-02-16 | 2024-03-21 | 25 | 25
15 | UAT Testing | 2024-03-08 | 2024-03-27 | 1 | 14
16 | GO-LIVE | 2024-03-29 | 2024-04-01 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E13: Kashish: Sum of Total Development Effort Days needs to be entered by TL.