## Important Information
Detailed WBS for Real Estate App
PROJECT TITLE |  |  | Real Estate App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Divyika
CLIENT NAME |  |  | Uwagboe
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End User, Admin
Business Need | Client wants to build a Real Estate Application and from that application users will be able to calculate the ROI based upon any specific property chosen by the user within the application.
User Types and Their Platforms | User | Mobile App
| Admin | Web Panel
Tech Stack | Mobile Application | Flutter/ React native
| Admin | Laravel/ Node js
| Database | MySql/Mongo DB
| Back-end | PHP (Laravel)

## UserType1_Mobile App
Mobile App Flow for User Type 1
|  |  | 25 | 16 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
Splash Screen |  | o This will be the first screen that the users will view after entering the application while the app loads in the background. | 0.5
Authentication |  | • This module consists of the registration and login functionalities.
| • Sign Up / Register | o Users will be able to register using below details and after clicking on register user needs to give answers for few basic things  Full name  Mobile Number / E-mail ID  Password  Confirm Password | 2 | 1
| • OTP Verification | o The users will receive an OTP over their mobile number OR E-mail ID for verification after which the user would be successfully registered on the application.
| • Login | o The users will be able to login into the application using the below details:  Mobile Number / E-mail ID  Password  Checkbox to “Keep me Logged In”.
| • Forgot Password | o A hyperlink present on the authentication screen clicking on which user would be redirected to the Forgot Password screen where user need to enter the below details:-  Mobile Number (To receive the OTP for verification).  OTP o After the OTP is verified user would be asked to mention below details in order to change the password:-  New Password  Confirm New Password
 Advance Listing Features: | • Home Screen: | o User will be able to see the list of all the properties listed within the app. o User will be able to scroll down to the application in order to check all the properties listed within the app. o User will be able to see a search bar on top of the application. o Hamburger Menu  About Us  Privacy Policy  Terms and Conditions o My Profile  Edit Profile  Change Password  Logout  Delete Account o Search Bar o Check all Listing o Notification | 4 | 2
| • Search Bar: | o Users can find properties based on their preferences:  Location and Filters: Users can search for properties by specifying location, price range, property type, and City.  Search Results: The app displays a list of properties that match the user's criteria. | 2 | 2
| • Property Details: | o Users can view detailed information about properties:  High-Quality Images: Users can see multiple images of the property to understand its visual appeal.  Specifications: Detailed property specifications, such as the number of bedrooms, bathrooms, square footage, and more.  Pricing: Clear pricing information, including any additional costs (If Applicable).  ROI: User will be able to calculate the P&L based upon the price of property and ROI for upcoming years. | 4 | 2
| • Calculate Net Profit: | o User will be able to input the appreciation amount manually in a text field. o User will be able to input the cash flow amount manually in the text field. o Mathematical algorithm will calculate the Net Profit. o Formula which will be used in the backend [Net Profit = Appreciation + Cash Flow]  Appreciation: The increase in the property's value over time.  Cash Flow: The positive cash generated by the property (Rental Income - Operating Expenses). | 3 | 1.5
| • Property ROI: | o Loan Repayment  Calculation: The app will calculate and display the projected loan repayment over the specified period based on the user's input of the loan amount, interest rate, and loan duration.  User Input: Users will input details such as loan amount, interest rate, and loan duration. | 3 | 3
|  | o Return on Investment (ROI) Calculation:  Calculation: The app's algorithm will calculate ROI based on the formula: ROI= (Initial Investment/Net Profit) ×100  Components: The calculation considers cash flow, appreciation, and initial investment.  User Input: Users need to input data on initial investment, cash flow, and appreciation rate. Note: If formula get changed by admin, output will not come and it will show an Error. | 3 | 1.5
| • Notifications: | o Users receive notifications to stay informed about:  New Property Listings: Notifications about properties that match their search criteria.  Nearby Property Listing: Notifications about the properties which get listed nearby to the user. | 2 | 2
| • About Us | o The About Us page gives detail about us, why it was created, who it’s for, and what makes the app unique in the industry. | 1 | 0.5
| • Privacy, Terms and Conditions | o Terms and conditions, encompassing service agreements and contracts. o The terms include a privacy policy, securing data protection and defining conduct standards.
| • Log Out | o Clicking on this a pop-up would be displayed as “Are you sure you want to Log Out from the Application?” with Cancel and Sure button.  If user clicks on Cancel button, then the User would remain on the same screen.  If user clicks on Sure button, then the user would be logged out from the Application and would be re-directed to the authentication screen. | 0.5 | 0.5
| • Delete Account | o Clicking on this a pop-up would be displayed as “Are you sure you want to Delete your Account?” with Cancel and Sure button.  If user clicks on Cancel button, then the user would remain on the same screen.  If user clicks on Sure button, then the user would be logged out from the Application and would be re-directed to the authentication screen.

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
|  |  | 7 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
User Management |  | • Admin will be able to manage the users. • Admin will be able to View/search the users. • Admin will be able to delete, activate or deactivate any particular user. | 1
Listing Management |  | • Add, edit, or delete property listings. • View a list of all properties listed within the app. • Manage property details, images, specifications, and pricing | 2
Notification Management |  | • Send notifications to users about new property listings and nearby properties. • View the history of sent notifications. | 2
Content Management |  | • Manage static content such as the About Us page, Privacy Policy, and Terms and Conditions. • Update content on the Welcome Screen. | 1
ROI Management |  | • Admin will be able to change the formula for ROI and Loan Repayment. | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Real Estate App | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-22 | 2024-04-01
[8 empty] | Total Project Effort (in person days) | 60
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 51
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-22 | 2024-02-02 | 1 | 10 |  | 2024-02-07
2 | UI/UX (User) | 2024-01-23 | 2024-02-07 | 0 | 12 | Design
7 | User_Mobile Application | 2024-02-08 | 2024-03-13 | 1 | 25
11 | API+Admin | 2024-02-08 | 2024-02-27 | 14 | 23
14 | QA Testing | 2024-02-16 | 2024-03-21 | 25 | 25
15 | UAT Testing | 2024-03-08 | 2024-03-27 | 1 | 14
16 | GO-LIVE | 2024-03-29 | 2024-04-01 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E12: Kashish: Sum of Total Development Effort Days needs to be entered by TL.