## Important Information
Detailed WBS for Trading Educational App
PROJECT TITLE |  |  | Trading Educational App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Sujitha
CLIENT NAME |  |  | Alicia
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End User, Admin
Business Need | The business need of the client is to develop a trading educational application where users can learn about the trading strategies and practice for the same by the provided contend. Additionally, it will be an MVP of the project, so for now it will be a self-learning application for users.
How to achieve? | The application will provide comprehensive learning experience with demo videos covering the basics of trading. To assess understanding, tests are conducted at the end of each course that help the user’s in-real world trading scenarios.
User Types and Their Platforms | User Type1 | End users
| User Type2 | Admin
Tech Stack | Platform 1 | Flutter / React Native
| Admin | Node.js / PHP (Laravel)
| Backend (API) | Node.js / PHP (Laravel)
| Database | MongoDB / MySql
| Back-end | PHP (Laravel)

## UserType1_Mobile App
Mobile App Flow for User Type 1
|  |  | 25 | 12.5 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
 Splash Screen |  | • This would be launch screen of the application displaying the Logo and Name. | 1
 Register/Login Screen |  | • Users will register or login with their mobile number or Email address. • Once they entered the mobile number/email id, they will receive an OTP on the same for verification. • User needs to enter this OTP on the application for successful login. | 2 | 1
 Home Screen |  | • Landing screen of the application displaying below sections or details:- o Logo of the Business. o Carousel Images. o List of Courses and content. o Search Bar to search for courses/content using keywords. o Notification | 3 | 2
| • Search | o User will be able to search for the courses using keywords o Users can view all the courses o Courses will consist of description and start button. | 2 | 1
| • Courses | o User will be able to view the courses uploaded by Admin o Upon selecting any course, user can view all the details of that course. o User will be able to view educational content such as- • Video lessons • Written materials • Interactive quizzes/questionnaires o These will be content sessions or chapter for each course. o After each session there will be some questions related to the content. o Users can re-read or replay the session to find out their mistakes. o Users can retake the quizzes as well. | 8 | 4
• My Courses |  | This section will give the highlights about the users’ preferred courses in the application such as-
| o Ongoing courses |  User will be able to view ongoing courses and can start from where ever left  User can view the quizzes and view the results | 2 | 1
| o Completed courses |  User will be able to view all the courses that are completed | 1 | 0.5
| o Saved courses |  User can view the courses that saved by the user | 2 | 1
• My Account |  | o Profile Users would be able to add and update the below details:-  Name  Mobile Number  E-mail ID  Mobile Number (If changed then the same needs to be verified through OTP)  Delete Account o Users will be able to access the application policies and company details by this section-  Privacy policy  Terms and conditions  Contact us  About us o Sign Out  The section allow the users to sign out from the application. | 4 | 2

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
|  |  | 13 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
 Login |  | o Admin will be able to Login into the admin web panel using their login credentials. The admin will use the following credentials such as:  Email id  Password | 1
 Dashboard |  | o Quick links for the given features would be given like:-  User Management  Courses Management  Content Management | 2
 User Management |  | o Admin will be able to manage the users from the backend. o Admin will be able to activate/deactivate the account of the users from the backend. | 1.5
 Courses Management |  | o Admin will be able to manage and create the courses of the and all the material under them o Create New Course  Admin can create new courses from this section. When they click on the Create new Course, a blank template will open and the admin can fill in the related details of the course such as- • Course Name/ title, • Course Description, • Related Pictures and Videos, • Quiz questions. • Save in Draft or Publish (buttons) o When courses are made there will be two options to “Save in draft” or “Publish”. o Save in draft option can be used by admin to keep the course into the draft section. o Publish option will make the course available to the application users. | 4.5
|  | o Edit/Update Course  Admin can update any course from this section and that will be save as the new version of that course. Old version also be there with the users list who completed that version of the course and new version will be available for them as a new course | 2
 Content Management |  | o The section allow the admin to manage the content for the application such as-  Carousel images  Privacy policy  Terms and condition  About us  Contact us | 1
Settings |  |  Change Password o Admin will be able to change the password by this section.  Logout o The section allow the admin to logout form the system. | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Trading Educational App | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-20 | 2024-04-02
[8 empty] | Total Project Effort (in person days) | 62.5
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 52
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-22 | 2024-02-02 | 1 | 10 |  | 2024-02-07
2 | UI/UX (User Type1) | 2024-01-23 | 2024-02-07 | 0 | 12 | Design
3 | User Type1_Mobile Application | 2024-02-08 | 2024-03-13 | 1 | 25
4 | API+Admin | 2024-02-08 | 2024-03-14 | 26 | 25.5
5 | QA Testing | 2024-02-16 | 2024-03-22 | 26 | 26
6 | UAT Testing | 2024-03-08 | 2024-03-28 | 1 | 15
7 | GO-LIVE | 2024-04-01 | 2024-04-02 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E12: Kashish: Sum of Total Development Effort Days needs to be entered by TL.