## Important Information
Detailed WBS for Your Freedom App
PROJECT TITLE |  |  | Your Freedom App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Rishav
CLIENT NAME |  |  | Barak
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End User & Admin
Business Need | Client needs an application where end users will be able to post their content other users can see and comment them more of like a replica of X(twitter).
How to achieve? | We will be developing an app where end users will register themselves can post their article or any content , which will be visible to other users and can comment and follow each other, an admin panel to control the overall platform.
User Types and Their Platforms | End User | Application
| Admin | Admin Panel
Tech Stack | Application | Flutter /ReactNative
| Admin | HTML/CSS
| Backend (API) | Node.js / PHP (Laravel)
| Database | MongoDB/MySql
| Back-end | PHP (Laravel)

## UserType1_Mobile App
Mobile App Flow for User Type 1
|  | 38 | 25
Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
Splash Screen | • The launch screen of the Application where users will be able to view the app’s logo.
Sign In | o The Employee will be able to login into the web app using the below details:  Email ID  Password o Forgot Password o Clicking on this Employee would be redirected to the Forgot Password screen where Employee need to enter the below details:-  Social Login  Email ID (To receive the OTP for verification).  OTP  After the OTP is verified Employee would be asked to mention below details in order to change the password:- • New Password • Confirm New Password | 2 | 1
Sign Up | o Users will be able to sign up using below details: -  Full Name  E-Mail ID  Password  Confirm Password  Username  Bio  Profile picture  Accept Terms and Conditions ( Checkbox )  Submit (Button)  Social Sign Up | 1
OTP Verification |  Sign-up process has to be verified through mobile number.
Home Screen: | User is directed to the home screen displaying a personalized timeline. • Timeline showcases tweets from users they follow, including text, images, and videos. •Real-time updates ensure the latest content is visible. | 4 | 2
Tweeting: | User taps on the "Compose" button. •Composes a tweet by entering text, attaching media (photos, videos), and using mentions or hashtags. •Option to add location to the tweet. | 5 | 2
Interacting with Tweets: | User can like a tweet by tapping the heart icon. • User can retweet a tweet, sharing it with their followers. • Commenting on tweets is done by tapping the speech bubble icon. | 6 | 2
Notifications: | User receives push notifications for new followers, likes, retweets, and mentions. • Notifications tab shows a history of these interactions. | 2 | 1
Messaging: | User accesses the messaging feature from the bottom navigation. • Initiates a private conversation by selecting a user and sending text, images, or videos. | 3 | 1
Profile: | User taps on their profile icon to access their profile. • Views and edits personal information, including username, bio, and profile picture. • Views tweets, followers, and following lists. | 2 | 1
Follow/Following: | User explores the "Discover" or "Search" feature to find users to follow. • Follows other users to see their tweets in their timeline. • Accesses "Followers" and "Following" tabs to manage connections. | 2 | 1
Trends | User explores the "Explore" section to discover trending topics and hashtags. • Clicks on a trend to see related tweets and join the conversation. | 3 | 1
Search | User utilizes the search bar to find specific users, tweets, or trending topics. • Search results display relevant accounts, tweets, and hashtags. | 2 | 2
Bookmarks | User bookmarks tweets by tapping on the bookmark icon on a tweet. • Accesses the "Bookmarks" section to view saved tweets. | 3 | 1
Safety Features: | User can report or block other users in case of inappropriate behaviour. • Mute feature allows users to silence notifications from specific accounts. | 3 | 10
Logout | • User can log out of the application.

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
26
Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
User Management: | • Admin can view a list of registered users. • Ability to search for users based on usernames, email addresses, or phone numbers. • View and edit user profiles, including usernames, profile pictures, and bios. • Manually verify or suspend user accounts if necessary. | 1
Content Moderation: | • Admin monitors reported tweets for inappropriate content. • Ability to review and take action on reported tweets (remove, warn users, etc.). • Implement automated content filtering algorithms to flag potentially offensive content. • Set up keyword-based filters to prevent the spread of harmful or abusive content. | 5
Trend Management: | • Admin can curate and manage trending topics. • Review and approve/reject user-generated trends. • Monitor trends for inappropriate or harmful content. | 2
Notification Monitoring: | • Admin receives alerts for unusual or suspicious user activities. • Investigate and take action on potential spam, bots, or other malicious activities. • Monitor and address system-generated notifications to ensure smooth platform operation. | 5
Messaging Oversight: | • Access and review user-reported private messages for inappropriate content. • Take appropriate action, such as warning or suspending accounts involved in harassment or abusive messaging. | 10
Security Features: | • Admin can review and manage security settings and features. • Monitor and update security protocols to protect user data and ensure the platform's integrity. | 2
Compliance and Legal: | • Ensure the platform complies with relevant laws and regulations. • Provide necessary tools for legal requests and investigations | 1
Logout: | • Secure and easy logout from the admin panel with appropriate access controls.

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Your Freedom App | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-22 | 2024-05-15
[8 empty] | Total Project Effort (in person days) | 104
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 83
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-22 | 2024-02-02 | 1 | 10 |  | 2024-02-12
2 | UI/UX (End User) | 2024-01-23 | 2024-02-12 | 0 | 15 | Design
3 | End User_Mobile Application | 2024-02-13 | 2024-04-04 | 1 | 38
4 | API+Admin | 2024-02-13 | 2024-03-01 | 14 | 51
5 | QA Testing | 2024-02-21 | 2024-05-01 | 51 | 51
6 | UAT Testing | 2024-03-13 | 2024-05-07 | 1 | 40
7 | GO-LIVE | 2024-05-09 | 2024-05-15 | 1 | 5
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E12: Kashish: Sum of Total Development Effort Days needs to be entered by TL.