## Important Information
Detailed WBS for Adult Dating Application
PROJECT TITLE |  |  | Adult Dating appplication
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Swaraj
CLIENT NAME |  |  | Paolo Valeri
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End user,Admin
Business Need | The business need is to have dating website platform using which end user can connect with each other.
How to achieve? | We are developing an dating website (18+), using which end users can connect with each other by using the chat and follow functionality on the platform. The users have to get register and buy VIP membership on the platform to avail all of the feature of the website.
User Types and Their Platforms | End User | Website
Tech Stack | Website | Angular/ React.js
| Admin | React.js
| Backend (API) | Node.js
| Database | MongoDB/ Mysql
| Back-end | PHP (Laravel)

## EndUser_Website
Mobile App Flow for User Type 1
|  |  | 35 | 32
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
 Consent Page |  | • This is the consent page where website will ask user permission to go forward to the main content page. • On this Page of website users can view the below o Banners Videos (with Message ‘ Enter (+18) ‘) o Information (text description) o Map View (Pin pointed location by other users for beaches & Cars) o Top VIP users with their profile image and name (On tapping ask user to login/register on the platform) o After tapping enter, website will redirect user to homepage before that they have to sign up on the platform. | 3 | 3
 Sign Up Page |  | • User will be able to sign up on the platform by entering the below details on the platform. o Who are you? (Single/Married/ Couple/ etc.) o Acknowledgement (Ok/ Like it) o Nick name o Locality o Gender & Type o Password o Confirm Password o Email • Once user tap on submit button, they will receive verification link over Email. On tapping the link user will redirect to login screen. | 2 | 1
 Login Page |  | • Login ID (Nickname) • Password | 2 | 1
 Forgot Password |  | • User can reset their password using this feature | 1 | 1
 Home Page (Header) | Home tab | • The Home page with consist of Headers and footers on the platform. • User will be asked to turn on their location before using the platform for better results on the platform (geo localization funtionlity). • All of the pages will carries the search functionality, using which users can search for people, places or articles. • The header will consist of o Announcement o Radar o Exhibitions o Video o Erotic Tales o Holidays o Club Prive o Blog o Carsex o Forum o Become VIP • The additional tabs on the headers will be o Likes o Messages o Notification o User Profile • The Footer of the website will includes o Online Classified o Erotic Tales o Community | 3 | 3
|  Announcements | • This screen will show video content on the platform. • Users will get filter option on the platform. The filters available would be like as specified below o Couple/single/etc. o Location o Provinces o New/Popular/Recent • Based on the filters system will fetches the results. • The result will be come up as user profile with little description, name, image, total click or today upload count & rating on the page. On tapping on any profile users can view the below details for that particular user o Image of User o Name (ID) & Tags o Rating o Interactive Panel for (Like profile, Give Feedback, Keep Notes, add as friend & other {Report and Block}) o Description Box (Announcement Box) o Message (Showing past or new conversation with user) o Latest activity (User friend with who and participate where) o Photos (All the image uploaded content) o Videos (Al the video uploaded content) o Friend List (Total number of friends) o Community Feedback (comments from other users) • The Page will show whether the user is online or offline along with their tag based on the choices. | 5 | 5
|  Radar | • This page will show user all the user around their 60 km or location. • User can apply filter to enhance their search criteria • The filter would be as o Online o VIP o Last minute o Certificate | 2 | 3
|  Videos | • This section will includes the videos content from the whole community. • The content will be distinguished based on their tags and user can search the videos based on tags. • The tags would be o Trending o Most viewed o Stage videos o Group, etc. • User can upload video on the platform using upload video feature on this page of the website. User can manage their uploaded content later on the platform form their profile section on the website. • Based on the selected tags the website will show the results from the community. | 4 | 4
|  Erotic Tales |  Erotic Tales • This section will show the tales shares by other user on the platform. • User can go and view any tales based on their categories. Tales category will be available on page as mentioned below o Classic Collection o LBBTQ Collection o Hard Collection • User can write up their own story under this section by using write story button on the page. • On this page user can view the author of the week with their respective ranking among other users. • User can like, rate or leave a comment on the story shared by the users on the platform. | 4 | 4
|  Blogs | • Users can view the blogs on the platform. • Users can tap on the category based on which they can search specific blogs on the platform. • User can read interviews on the blog section. | 3 | 3
|  Become VIP member | • Users can buy the VIP membership on the platform (User can buy the gold membership under this page and become eligible to use more unique feature on the platform) | 1 | 1
|  User profile | • User can view and setup their profile details using this section. • Additional details that user can manage under this section would be o Account settings o Announcement o Last minute o Holidays o Your photos o Videos o Your Stories o Friend list o Black list o Views o VIP status o Customer Support o Logout | 2 | 2
Home Page (Footers) | o Online Classified | Redirection Links | 1 | 1
| o Erotic Tales |  | 1 | 0
| o Community |  | 1 | 0

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
12
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
 User Management |  | • Admin will be able to manage the user base using this section of the admin panel. • Admin can add or remove any user on the platform using this section of the admin panel. • Admin can view the list of active and deactivated users on the platform. | 3
 Content Management |  | • Admin can view and manage the whole content of the platform using this section of the admin panel. • Admin can validate the content at his end and can remove if needed using this section. | 4
 Payments and membership |  | • Admin can manage the payment overview and membership of user from this section of the admin panel. | 3
 General Management |  | • Users can manage the below details under this section. o Forums o T & C o Privacy Policy o Customer Support & Resolution | 2

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Adult Dating appplication | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-22 | 2024-05-08
[8 empty] | Total Project Effort (in person days) | 87
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 78
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-22 | 2024-02-02 | 1 | 10 |  | 2024-02-02
2 | Website Design (End User) | 2024-01-23 | 2024-02-01 | 0 | 8 | Design
3 | End User_Website | 2024-02-05 | 2024-03-22 | 1 | 35
4 | API+Admin | 2024-02-05 | 2024-03-22 | 35 | 44
5 | QA Testing | 2024-02-13 | 2024-04-29 | 55 | 55
6 | UAT Testing | 2024-03-05 | 2024-05-03 | 1 | 44
7 | GO-LIVE | 2024-05-07 | 2024-05-08 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E12: ====== ID#AAABDBpYOA8 Kashish (2024-01-16 14:05:19) Sum of Total Development Effort Days needs to be entered by TL.