## Important Information
Detailed WBS for Cannabis E-commerce Application
PROJECT TITLE |  |  | Cannabis E-commerce Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Rahul Sharma
CLIENT NAME |  |  | Marc Theiler
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End User & Admin
Business Need | Client is looking for an application where users will be able to view the details of the products provided by the company. User can view and book the products. User will pick up the order from the store. Admin can update the products and view orders from the Panel.
How to achieve? | Using the application, user would view the details of the products and book the same. After booking the products user can collect them from the store by making payment at the store. Admin can update the products will receive details of the order.
User Types and Their Platforms | End User | Application
| Admin | Web Panel
Tech Stack | Application | Flutter / React Native
| Admin | HTML&CSS/ Angular
| Backend (API) | Node.js / PHP (Laravel)
| Database | MongoDB / MySql
| Back-end | PHP (Laravel)

## EndUser_Mobile App
Mobile App Flow for End User
|  |  | 22 | 15
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
Splash Screen |  | • The launch screen of the Application where end users will be able to view the company’s logo.
Authentication |  | • Sign In o The Users will be able to login into the application using the below details: § E-mail ID/Mobile Number § Password o Checkbox to Keep me Logged In • Sign Up / Register (As Customer) o Customers will be able to register using below details: - § First Name & Last Name § E-Mail ID § Mobile Number § Password § Confirm Password § Checkbox for Terms and Conditions • OTP Verification o Sign-up process has to be verified through mobile number | 2 | 1
Home Screen |  | • This screen would contain latest products updated by the Admin on the homescreen • This screen would be the main screen of the application and would comprise of below details: - o Home Screen o Cart o Search Products o My Orders WishList o Settings | 2 | 1
Search |  | • User will be able to search any particular product by using its name through search bar | 2 | 1
Product Categories |  | • User will be able to view the list of different categories of products. • Upon clicking of that particular item would be visible | 1 | 1
| • Particular Item | o User will be able to click on any particular item to see the description, image, and cost of that item. o User will be able to add that particular item into the cart and continue the shopping to purchase more products/items. o As soon as user clicks on “Add to cart” button user will be re-directed to cart screen. | 2 | 1
Cart |  | • User will be able to View/Edit/Delete/Add the list of items he has added in the cart. • User will be able to see the Image, Title, Quantity and Price of the particular item and will also be able to see total number to items in the cart and sub-total amount of all the items in the cart | 2 | 1
| Checkout | • While checking out user will have to complete following steps :- o Step 1:- User needs to select the store from where he will pick up the order. o Step 2:- Once user selected store then user will be able to collect the order from the store after making payment at the store only. | 2 | 1
My Orders |  | • User will be able to view the past and scheduled orders on the application along with product details, amount and contact number • User will be able to view the cancelled, past and scheduled order on the application | 1 | 1
| • Cancelled Order | o User can view all the details of the cancelled order along with product details and history | 1 | 1
| • Past Order | o User can view all the details of the order along with product details and history | 1 | 1
| • Order to be picked | o Users can view all the details of upcoming order with all the details along with date & time o User will have an option to cancel the order | 2 | 2
Settings Icon |  | • Clicking on this user would be redirected to the screen displaying My Account details with below options: - o Profile § Option to view or update the profile settings. o Password § Option to update the password. o Email § Option to view or update the e-mail ID. o Help/FAQ’s § This option would redirect the user to the screen displaying the list of FAQ’s uploaded by the admin. | 3 | 2
Wish list |  | • User will be able to add products in the wish list so they can browse them in future | 1 | 1

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
|  | 10 | 0
Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
Login | • Admin will be able to login using username & password. | 1
User Management | • This section would be used to view, edit or delete the customers. • Admin would be able to enable and disable the customers. • Admin can view size fit of the user selected by the user or scanned by the user | 2
Product Catalogue Management | • Admin will be able to manage the Product Catalogue and their prices from the back end. • Admin will be able to add/delete any product category from the back end. • Admin will be able to list any product under any category from the back end. • Admin will be able to remove already listed product from any category from the back end | 2
Order Management | • Admin will be able to manage the order record from the back end. • Admin will be able to view/search/delete any particular order’s data from the record. • Admin will be able to view order history on the basis of week, month or customized date from the record | 2
Notification Management | • This section would be used by admin panel to push notifications to the front end users. | 2
Content Management | • Admin will be able to manage (Add/View/Edit) the static contents. o About Us o Terms and Conditions. o Privacy Policy | 1
Integration of dutchie pos system in admin for the shop managers.

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart - Cannabis E-commerce Application | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-29 | 2024-04-18
[8 empty] | Total Project Effort (in person days) | 59
[8 empty] | Total Project Effort (in person days) | 59
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 59
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-29 | 2024-02-09 | 1 | 10 |  | 2024-02-14
2 | UI/UX (End User) | 2024-01-30 | 2024-02-14 | 0 | 12 | Design
7 | End User_Mobile Application | 2024-02-15 | 2024-03-15 | 1 | 22
11 | API+Admin | 2024-02-15 | 2024-04-03 | 35 | 25
14 | QA Testing | 2024-02-23 | 2024-04-04 | 30 | 30
15 | UAT Testing | 2024-03-15 | 2024-04-10 | 1 | 19
16 | GO-LIVE | 2024-04-12 | 2024-04-18 | 1 | 5
Formulas:
Start_Date = WORKDAY(H9,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E13: Kashish: Sum of Total Development Effort Days needs to be entered by TL.