## Important Information
Detailed WBS for Asset Management
PROJECT TITLE |  |  | Detailed WBS for Asset Management
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Divyika
CLIENT NAME |  |  | David
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End User (Buyer, Seller) and Admin
Business Need | The business need for the Asset Management Application is to provide a comprehensive solution for efficiently managing assets, facilitating sales and leasing , scheduling inspections, and incorporating various features such as document storage, API integration, and ad network inclusion. This solution aims to streamline asset-related processes and enhance user experience in the sales and marketing domain.
Business Solution | The platform facilitates streamlined management of assets by offering robust features such leasing, and booking for trial. It enhances transactional efficiency, user experience, and marketing efforts, meeting the comprehensive needs of asset-related processes in the sales and marketing domain.
User Types and Their Platforms | User 1 Buyer | Mobile App
| User 2 Seller | Mobile App
Tech Stack | Admin | Web Panel
| Mobile Application | Flutter/ React native
| Admin | Laravel/ Node js
| Database | MySql/Mongo DB
| Back-end | PHP (Laravel)

## UserType1_Mobile App
Mobile App Flow for User Type 1
|  |  | 27.5 | 14 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
 Splash Screen |  | • The launch screen of the Application where end users will be able to view the company’s logo. | 0.5
 Authentication |  | • User will be able to select that he wants to login as Buyers or Sellers • Sign In o The Users will be able to login into the application using the below details:  E-mail ID or Mobile Number  Password or OTP • Forgot Password o Clicking on this user would be redirected to the Forgot Password screen where user need to enter the below details:-  Email ID or Mobile Number (To receive the OTP for verification).  OTP o After the OTP is verified user would be asked to mention below details in order to change the password:-  New Password  Confirm New Password • Sign Up / Register (As Customer) o Customers will be able to register using below details: -  First Name & Last Name  E-Mail ID/Mobile Number  Password  Confirm Password  Checkbox for Terms and Conditions Note: Users (Buyers) will be able to login to the app using Facebook and Google Id. • OTP Verification o Sign-up process has to be verified through mobile number/email ID
 Home Screen |  | • On the home screen buyers will be able to see the list of assets. • Buyers will be able to scroll down the application to see all the listed assets by clicking on “View All” and user will be redirected to Asset Exploration screen. • Buyers will be able to see a banner on the home screen representing the information about co. • Buyers will be able to see notification icon on top left corner. • Buyers will be provided a tab in bottom menu for the list of transactions. • Buyers will be able to track the assets in which they have shown interest by checking the Favourite Assets. • Hamburger Menu o Home o About Us o Privacy Policy o Inquiry Form o My Favourites o Terms and Conditions • My Profile o Edit Profile o Change Password o Logout o Delete Account • Bottom Menu Bar o Home o Asset Exploration o My Profile • In App Chat | 4 | 2
 My Profile: |  | • Profile: - Buyers will be able to click on profile and redirect to profile page. • Buyers will be able to view or edit their details o Name o Email o Phone Number o Change Password • Log out: - Buyers will be able to log out from their account. • Delete Account: - Buyers will be able to delete their account. | 2 | 1
 Inquiry Form |  | • Buyers will be able to fill the inquiry form by typing in the details. • Buyers will be able to provide more brief information related to their inquiry by typing in their comments. | 2 | 1
 My Favourites |  | • Buyers will be able to add the asset in their favourite list. • Buyers will be able to remove the asset from their favourite list. • From My Favourites section buyers can also submit an inquiry form. | 2 | 1
 Asset Listing |  | • Buyers will be able to see the list of all the assets available within the app. • Buyers will be able to see brief information related to asset. • Buyers will be able to click on any particular asset and read detailed information about it. • Information will be available to the buyers in the form listed below: o Discipline : o Available : o Lease Rate ($) : o Option to buy : o Rider Skill : o Shows up to : o USEF # : • User will be able to see the option to schedule the trial. • User will be able to see an option to send message to the seller. • User will be able to check the available for leasing the asset. | 7 | 3.5
 Check Lease Availability |  | • User will be able to click on check lease availability for the asset. • Upon clicking on this button user have to provide: o Start Date o End Date • Once dates has been finalised system will check the availability and if asset is available it will gives a message to the user “AVAILABLE! - Now, let’s schedule a trial”. | 3 | 1.5
 Schedule Trial |  | • User needs to provide Start Date and Time for booking the trial. • User will be able to type in some additional details for schedule a trial. • User needs to provide name of the concerned person who is going to take the trial. (Optional) | 2 | 1
 In App Chat |  | • Buyer will be able to communicate with the seller for scheduling the trial or to do any sort of communication. | 3 | 2
 About Us |  | • The About Us page gives detail about us, why it was created, who it’s for, and what makes the app unique in the industry. | 2 | 1
 Privacy, Terms and Conditions |  | • Terms and conditions, encompassing service agreements and contracts. • The terms include a privacy policy, securing data protection and defining conduct standards.
 Log Out |  | • Clicking on this a pop-up would be displayed as “Are you sure you want to Log Out from the Application?” with Cancel and Sure button. o If user clicks on Cancel button, then the User would remain on the same screen. o If user clicks on Sure button, then the user would be logged out from the Application and would be re-directed to the authentication screen.
 Delete Account |  | • Clicking on this a pop-up would be displayed as “Are you sure you want to Delete your Account?” with Cancel and Sure button. o If user clicks on Cancel button, then the user would remain on the same screen. o If user clicks on Sure button, then the user would be logged out from the Application and would be re-directed to the authentication screen.

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App
Mobile App Flow for User Type 2
|  |  | 18 | 10.5 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
 Splash Screen |  | • The launch screen of the Application where end users will be able to view the company’s logo.
 Authentication |  | • User will be able to select that he wants to login as Buyers or Sellers • Sign In o The Users will be able to login into the application using the below details:  E-mail ID or Mobile Number  Password or OTP • Forgot Password o Clicking on this user would be redirected to the Forgot Password screen where user need to enter the below details:-  Email ID or Mobile Number (To receive the OTP for verification).  OTP o After the OTP is verified user would be asked to mention below details in order to change the password:-  New Password  Confirm New Password • Sign Up / Register (As Customer) o Customers will be able to register using below details: -  First Name & Last Name  E-Mail ID/Mobile Number  Password  Confirm Password  Checkbox for Terms and Conditions Note: Users (Sellers) will be able to login to the app using Facebook and Google Id. • OTP Verification o Sign-up process has to be verified through mobile number/email ID | 2 | 1
 Home Screen |  | • Sellers will be able to view an option to add asset. • Seller will be able to check the listing of all the trial which has been booked for the asset. • Hamburger Menu o Home o About Us o Privacy Policy o Inquiry Form o Terms and Conditions • My Profile o Edit Profile o Change Password o Logout o Delete Account • Bottom Menu Bar o Home o My Asset Listing o Add New Asset o My Profile • In App Chat | 4 | 2
 My Profile: |  | • Profile: - Sellers will be able to click on profile and redirect to profile page. • Sellers will be able to view or edit their details o Name o Email o Phone Number o Change Password • Log out: - Sellers will be able to log out from their account. • Delete Account: - Sellers will be able to delete their account. | 1 | 1
 Inquiry Form |  | • Sellers will be able to check the inquiry forms filled by buyers. • Sellers will be able to revert the users over the mail related to the inquiry. | 2 | 1
 Add New Asset |  | • Sellers will be able to add new asset. • Seller needs to provide basic and detailed information related to adding the asset. • Seller will be able to see a dedicated section for adding a new asset along with a tag line “Tell us a bit about the Horse” • Seller need to fill details mentioned below: o Show Name o Breed o Breed o Size o Gender o Foal Year o Horse USEF# • Seller need to click on next one details are filled. • Seller needs to select the discipline: Hunter/Equation/Jumper • Seller needs to add details about Availability and Pricing • Seller will be able to upload the photos, documents and video for their asset. • Seller needs to provide the address of asset (Address, city, zip code and Unit) | 6 | 3
 In App Chat |  | • Seller will be able to chat with buyer | 2 | 2
 About Us |  | • The About Us page gives detail about us, why it was created, who it’s for, and what makes the app unique in the industry. | 1 | 0.5
 Privacy, Terms and Conditions |  | • Terms and conditions, encompassing service agreements and contracts. • The terms include a privacy policy, securing data protection and defining conduct standards.
 Log Out |  | • Clicking on this a pop-up would be displayed as “Are you sure you want to Log Out from the Application?” with Cancel and Sure button. o If user clicks on Cancel button, then the User would remain on the same screen. o If user clicks on Sure button, then the user would be logged out from the Application and would be re-directed to the authentication screen.
 Delete Account |  | • Clicking on this a pop-up would be displayed as “Are you sure you want to Delete your Account?” with Cancel and Sure button. o If user clicks on Cancel button, then the user would remain on the same screen. o If user clicks on Sure button, then the user would be logged out from the Application and would be re-directed to the authentication screen.

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
|  |  | 9 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
 Dashboard |  | • Overview of the total number of registered buyers and sellers. • Quick statistics on active assets, and inquiries. | 1
 User Management |  | • List of registered buyers and sellers. • User details including name, contact information, and registration date. • Ability to block/unblock users. • Manage user access levels. | 1
 Asset Management |  | • View and manage all listed assets. • Details about each asset including name, type, and status (available, leased, sold). • Edit or remove assets. | 2
 Inquiries Management |  | • Access to all inquiries submitted by buyers. • Ability to respond to inquiries directly from the admin panel. • Archive or delete inquiries. | 2
 Chat Management |  | • Access to in-app chat logs between buyers and sellers. • Ability to monitor and moderate conversations if necessary. | 2
 Content Management |  | • Manage content displayed on the platform, including banners and notifications. • Ability to add, edit, or remove informational pages (About Us, Privacy Policy, Terms and Conditions). | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Detailed WBS for Asset Management | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-29 | 2024-05-30
[8 empty] | Total Project Effort (in person days) | 103
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 89
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-29 | 2024-02-09 | 1 | 10 |  | 2024-02-14
2 | UI/UX (User 1 Buyer) | 2024-01-30 | 2024-02-14 | 0 | 12 | Design
3 | UI/UX (User 2 Seller) | 2024-01-30 | 2024-02-14 | 0 | 12 | Design
7 | User 1 Buyer_Mobile Application | 2024-02-15 | 2024-03-22 | 1 | 27.5
8 | User 2 Seller_Mobile Application | 2024-02-16 | 2024-03-12 | 1 | 18
11 | API+Admin | 2024-02-15 | 2024-03-05 | 14 | 33.5
14 | QA Testing | 2024-02-23 | 2024-05-16 | 60 | 60
15 | UAT Testing | 2024-03-15 | 2024-05-22 | 1 | 49
16 | GO-LIVE | 2024-05-24 | 2024-05-30 | 1 | 5
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY(WORKDAY(H8,[Lead Days]),1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E14: Kashish: Sum of Total Development Effort Days needs to be entered by TL.