## Important Information
Detailed WBS for Supply Chain Management App
PROJECT TITLE |  |  | Supply Chain Management App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Deepak
CLIENT NAME |  |  | Prashant
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | User, Sub-Admin, and Admin
Business Need | Client needs a platform where employee can make purchase orders for requisition and sales order. Employee will send these orders to the admin and it will be shown to the admin and respective sub-admin of the department for approval. Sub-admin shall have access to the portal with all the modules for which admin has shared the access to them. Admin shall have option to manage platform from the backend.
How to achieve? | As a solution we suggest to create a mobile app for the employees, where they can make purchase and sales order by filing out a form. These orders will be sent to the admin and respective sub-admin of the department for approval. Employee can see the status of the sent Purchase and Sale order in their mobile app. Sub-admin will have access to the portal with all the modules for which admin has shared the access to them. Admin will have option to manage users, dashboard, sub-admin, purchase orders, sales orders, reports, and notifications from the backend.
User Types and Their Platforms | User | Mobile Application
| SubAdmin | Web Panel
| Admin | Web Panel
Tech Stack | Mobile Application | React Native/Flutter
| Web App | HTML CSS/ Angular
| Admin | HTML CSS/ Angular
| Backend (API) | PHP/Node.js
| Database | MySQL/MongoDB
| Back-end | PHP (Laravel)

## Employee_Mobile App
Mobile App Flow for Employee
|  |  | 18 | 10
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
Splash Screen |  | The launch screen of the Application where employee will be able to view the app’s logo.
Authentication | Sign In | o The Employee will be able to login into the mobile app using the below details:  Email ID  Password o Forgot Password o Clicking on this Employee would be redirected to the Forgot Password screen where Employee need to enter the below details:-  Email ID (To receive the OTP for verification).  OTP  After the OTP is verified Employee would be asked to mention below details in order to change the password:- • New Password • Confirm New Password Login credentials will be shared with employee by admin over their email ID. | 2 | 1
Home Screen |  | Following details will appear over the homescreen: Total Purchase Orders Submitted Total Sales Orders Submitted Create Purchase Order (Button) Create Sale Order (Button) | 2 | 1
Purchase Orders | Create and Send | Employees will have option to create purchase order, to create one following details will be required: Order ID(Auto-generated, shall be unique) Title Order Type - Purchase Order Product/Item Selection Select from dropdown/list Enter quantity for every odrer Required before Send Onclick, this request will be sent to the admin panel where they can verify and proceed further. | 3 | 2
| View | Employee can see all the purchase orders create by them along with its status. | 2 | 1
Sale Orders | Create and Send | Employees will have option to create sale order, to create one following details will be required: Order ID(Auto-generated, shall be unique) Title Order Type - Sale Order Product/Item Selection Select from dropdown/list Enter quantity for every odrer Need to be sold before Send Onclick, this request will be sent to the admin panel where they can verify and proceed further. | 3 | 2
| View | Employee can see all the sale orders create by them along with its status. | 2 | 1
Notifications |  | Employee will receive notifications for updates or announcement from the admin. | 2 | 1
Profile |  | Employee will be able to View their profile details. | 1 | 1
Change Password |  | Employee will be able to change their password. | 1
Logout |  | Employee will be able to logout of the mobile app, after which they will be redirected to the sign in screen.

## Sub-Admin
Sub-Admin Flow
9
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days)
Sign In |  | • Sub-Admin will be able to sign to the web panel with the help of Email ID and Password. • In case Sub-admin forgets the password they can recover it using their email ID. | 1
Dashboard |  | • Following details will appear on the dashboard:-  Total Employers over the Platform  Total Purchase Orders  Total Sales Orders • Sort • Sub-Admin will have option to sort the dashboard based on:-  Today  This Week  This Month  This Year | 2
Order Management | Purchase Order | Sub-Admin can manage all the purchase orders from here. Sub-Admin will have option to verify(Approve/Reject) the purchase Order. Sub-Admin can send mail to the sellers by entering their email id from here. | 2
| Sale Order | Sub-Admin can manage all the Sale orders from here. Sub-Admin will have option to verify(Approve/Reject) the sale Order. Sub-Admin can send mail to the buyers by entering their email id from here. | 2
Change Password |  | • Sub-Admin will be able to change their password. | 1
Push Notification Management |  | • Sub-Admin will be able to manage the push notification from the backend. • Sub-Admin will be able to send the notifications to the Employee. | 1
Logout |  | • Sub-Admin will be able logout from the web app, after logout admin will be redirected to the login page.

## Admin
Admin Flow
14
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
Sign In |  | • Admin will be able to sign to the web panel with the help of Email ID and Password. • In case admin forgets the password they can recover it using their email ID. | 1
Dashboard |  | • Following details will appear on the dashboard:-  Total Employers over the Platform  Total Purchase Orders  Total Sales Orders • Sort • Admin will have option to sort the dashboard based on:-  Today  This Week  This Month  This Year | 2
Employee Management |  | • Admin will be able to search the Users profile from the backend. • Admin will be able to see a list of Users in Grid/Tabular format. • Admin will be able to see the detailed view of the emoloyee. • Admin will be able to Edit/Delete the employee profile. • Admin will be able to activate/deactivate the account of the Users from the backend. • Admin will be able to create employee account from backend. To create account following details will be required: Name Email ID Mobile Number Department Create and Send Credentials Onclick of create, login credentials will be sent to the employee's email ID, with the help of which they can access the mobile application. | 2
Order Management | Purchase Order | Admin can manage all the purchase orders from here. Admin will have option to verify(Approve/Reject) the purchase Order. Admin can send mail to the sellers by entering their email id from here. | 1
| Sale Order | Admin can manage all the Sale orders from here. Admin will have option to verify(Approve/Reject) the sale Order. Admin can send mail to the buyers by entering their email id from here. | 1
Item Management |  | Admin will be able to manage all the items from the backend. They can add/edit/remove the items from here. At the time of item addtion, admin will be required to enter the following details: Item Name Category(will be set from database at once for now) SQU Image MRP Buying Price All the items which are added from here will only be visible to the employee while they create any sale or purchase order. | 2
Sub Admin Management |  | Admin will be able to manage the subadmin account from here. They can add/edit/remove the subadmin accounts While adding a sub-admin account, admin will be asked to enter the following details: Name Email ID Department Select Access for modules Create and send Credentials (button) Onclick login credentials will be sent to the subadmin's email ID, with the help of which they can access the admin portal with limited access. | 2
Content Management |  | • Admin will be able to generate and manage the Content from the backend. • Admin will be able to manage the static content from the panel. | 1
Change Password |  | • Admin will be able to change their password. | 1
Push Notification Management |  | • Admin will be able to manage the push notification from the backend. • Admin will be able to send the notifications to the Employee. | 1
Logout |  | • Admin will be able logout from the web app, after logout admin will be redirected to the login page.

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Supply Chain Management App | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-15 | 2024-04-03
[8 empty] | Total Project Effort (in person days) | 65
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 58
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-15 | 2024-01-26 | 1 | 10 |  | 2024-02-02
2 | UI/UX (User) | 2024-01-16 | 2024-02-02 | 0 | 14 | Design
7 | User_Mobile Application | 2024-02-05 | 2024-02-28 | 1 | 18
12 | Sub-Admin | 2024-02-05 | 2024-02-15 | 1 | 9
11 | API+Admin | 2024-02-05 | 2024-02-23 | 15 | 24
14 | QA Testing | 2024-02-13 | 2024-03-25 | 30 | 30
15 | UAT Testing | 2024-03-05 | 2024-03-29 | 1 | 19
16 | GO-LIVE | 2024-04-02 | 2024-04-03 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E13: Kashish: Sum of Total Development Effort Days needs to be entered by TL.