## Important Information
Detailed WBS for Food Recipe Mobile App
PROJECT TITLE |  |  | Food Recipe Mobile App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Deepak
CLIENT NAME |  |  | Stephen
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | User
Business Need | Client needs a platform where users can see recipe informations for several dishes. The content shall be same as shown on https://temps-de-cuisson.fr/ They shall also have option to calculate the receipe time online. Users shall have option to start timer and it should beep once the time is done. There should be advertisement integration for monetization of the application.
How to achieve? | As a solution we suggest to create a mobile app for the user, where users can view the information related to different kind of recipe. Users can calculate the time required to cook the recipe with the help of inbuilt "recipe cooking time calculator". Users will have option to start a timer before they start cooking something and once the time is over the device should beep. There will be AdMob integration for monetization of Mobile app by showing ads over the app. The Application will be in french language only. The content shall be same as shown on https://temps-de-cuisson.fr/ Following website will be followed for recipe cooking time calculation : https://cooking-times.com/cooking-time-calculator/
User Types and Their Platforms | User | Mobile Application
Tech Stack | Mobile Application | React Native/Flutter
| Backend (API) | PHP/Node.js
| Database | MySQL/MongoDB
| Back-end | PHP (Laravel)

## UserType1_Mobile App
Mobile App Flow for User
|  |  | 41 | 20
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
Splash Screen |  | The launch screen of the Application where end users will be able to view the app’s logo.
Walkthrough Screen |  | User will be able to view 3-4 walkthrough screens, which will be helpful for them to have an idea about the app. | 1
Homescreen |  | Over home screen there will be some content as per the following website. https://temps-de-cuisson.fr/ | 1
Explore | Search | User will be able to search any recipe by its name. | 2
| Seacrh Result | Search result will appear with the following details Name of Recipe Read more (button) After clicking here user will be redirected to the recipe detail screen. | 1
Egg |  | Inside Egg there will be multiple categories, and every category will have separate page. Categories: Boiled Egg, Hard Egg, Poched Egg. | 2
Vegetables |  | Inside Vegetables there will be multiple categories, and every category will have separate page. Categories: Artichoke, White asparagus, Green asparagus, Eggplant, Beetroot, Wheat, Broccoli, Butternut, Cardons, Carrot, Celery branch,, Celeriac, Chestnut, Pumpkin, White cabbage, Chinese cabbage, Brussels sprouts, Cauliflower, Kale, Romanesco cabbage, reen cabbage, Zucchini, Endive, Spinach, Fennel, Beans, Broken broad beans, Green Flageolet, Fries, Butter beans, Coconut beans, Bullion beans, Red beans, Tarbes bean, Flat beans or "glutes", Green beans, Quinoa, Blonde lenses, Coral lentils, Green lentils, But, Brown, Turnip, Parsnip, Yam, Peas, Potato, Chickpeas, Leeks, Split peas, Pumpkin, Rice, Salsify, Semolina, Tomato, Jerusalem artichoke | 4
Meats |  | Inside Meats there will be multiple categories, and every category will have separate page. Categories: Chicken wings, Andouillette, Hog spider, Chicken breast, White sausage, Bib, Kobe beef, Black pudding, Meatball, BBQ beef skewer, Quail, Can, Rack of lamb, Rack of pork, Obermois or Alsatian, cervelass, Brains pork lamb veal, Capon, Kid, Goose confit, Cockerel, Prime rib, Pork chop, Veal chop, Pork crepinette, Turkey leg, Turkey, Pork loin, Entrecote, Lamb shoulder, Pork cutlet, Veal cutlet, Snails, Pheasant, Ribeye, Pork filet mignon, Veal fillet , Foie gras, Leg of lamb, Chicken thigh, Pork knuckle, Pork cheeks, Beef tongue, Rabbit, Duck breast, Merguez, Pork ham nuts, Nuggets, Marrow bones, Pallet pig, Veal paupiette, Turkey paupiette, Piglet, Oxtail, Sweetbread, Lamb kidneys, veal kidney, Roast lamb, Roast beef, Capon roast, Roasted turkey, Roast pork, Roast veal, pork roll, Rümsteak, Saddle of lamba, Montbéliard sausage, Morteau sausage, Strasbourg sausage, Toulouse sausage, Vaudois sausage, Lamb shank, Steak, Chopped steak, Head of veal, Beef tournedos, Pork ribs (Ribs) | 5
Pisces |  | Inside Pisces there will be multiple categories, and every category will have separate page. Categories: Skate wing, Spider crab, Bar, Periwinkles, Cod, Sea bream, Lobster, Langoustine, Lotte, Octopus, Mussels, Scorpionfish, Red mullet, Saint Jacques, Salmon, Sardine, Tuna, Oilcake , Turbot, Trout | 5
Cooking Methods |  | Inside Cooking Methods there will be multiple categories, and every category will have separate page. Categories: Philips airfryer, Cooking in water, Clickchef steam cooking, Low temperalure cooking, Baking, Seb pressure cooker, cooking time, Steam cooking, Steam cooking, Cooking to heart, Steam cooking time, monsieur cuisine connect, Clipsominute perfecta, Sous vide cooking, Barbecue cooking, Actifry cooking, Babycook cooking, babycook nesooking, Cookeo, Convenient steam cooker, Nutribaby cooking, Advent baking, Webber barbecue cooking, Companion Moulinex, Click&cook Moulinex, Clipso plus SEB, Clipso One Seb, Magimix cook Expert, Sterilization of jars, Nutricook Delise SEB, cooking, Cooking Vitacuisine seb, DUROMATIC cooking, How to measure withoutascales and measuringcup?, Camembert cooking, Golden mount In the Oven, Pizza cooking time, Tea brewing time, Cooking pasta (pasta), Cooking apple pie | 5
Div |  | Inside Div there will be multiple categories, and every category will have separate page. Categories: Camembert cooking, Golden mount In the Oven, Pizza cooking time, Tea brewing time, Cooking pasta (pasta), Cooking apple pie | 4
Cooking Time Calculator |  | Following website will be followed for recipe cooking time calculation : https://cooking-times.com/cooking-time-calculator/ **Code and logic for calculation will be provided by the client | 6
Stopwatch/Timer |  | Users will have option to start a timer before they start cooking something and once the time is over the device should beep. | 2
Advertisement |  | There will be AdMob integration for monetization of Mobile app by showing ads over the app. | 2
Static Content |  | About Us App Version | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Food Recipe Mobile App | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-17 | 2024-04-09
[8 empty] | Total Project Effort (in person days) | 77
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 60
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-17 | 2024-01-30 | 1 | 10 |  | 2024-02-08
2 | UI/UX (User) | 2024-01-18 | 2024-02-08 | 0 | 16 | Design
7 | User_Mobile Application | 2024-02-09 | 2024-04-05 | 1 | 41
11 | API | 2024-02-06 | 2024-02-23 | 17 | 20
14 | QA Testing | 2024-02-19 | 2024-03-29 | 30 | 30
15 | UAT Testing | 2024-03-11 | 2024-04-04 | 1 | 15
16 | GO-LIVE | 2024-04-08 | 2024-04-09 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E12: Kashish: Sum of Total Development Effort Days needs to be entered by TL.