## Important Information
Detailed WBS for E-commerce App
PROJECT TITLE |  |  | E-commerce App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Deepak
CLIENT NAME |  |  | Alexis
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End User, Drivers & Admin
Business Need | Client is looking for an application where users will be able to view the details of the products provided by the company. User can view and book the products. User will receive the order and then use it. User can view the order status. Drivers will have their app to where they can view different orders to deliver. Admin can update the products and view orders from the Panel.
How to achieve? | Using the application, user would view the details of the products and book the same. Drivers to have their own platform where they can view details of the orders and deliver the product to user’s address. Admin can update the products will receive details of the order and assign Drivers to the same.
User Types and Their Platforms | End User | Application
| Driver | Application
| Admin | Web Panel
Tech Stack | Application | Flutter / React Native
| Admin | HTML&CSS/ Angular
| Backend (API) | Node.js / PHP (Laravel)
| Database | MongoDB / MySql
| Back-end | PHP (Laravel)

## UserType1_Mobile App
Mobile App Flow for User Type 1
|  |  | 24 | 18
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
Ø Splash Screen |  | • The launch screen of the Application where end users will be able to view the company’s logo.
Ø Authentication |  | • Sign In o The Users will be able to login into the application using the below details: § E-mail ID/Mobile Number § Password o Checkbox to Keep me Logged In • Sign Up / Register (As Customer) o Customers will be able to register using below details: - § First Name & Last Name § E-Mail ID § Mobile Number § Password § Confirm Password § Checkbox for Terms and Conditions • OTP Verification o Sign-up process has to be verified through mobile number | 2 | 1
Ø Home Screen |  | • This screen would contain latest products updated by the Admin on the homescreen • This screen would be the main screen of the application and would comprise of below details: - o Home Screen o Cart o Search Products o My Orders o Settings | 2 | 2
Ø Search |  | • User will be able to search any particular product by using its name through search bar | 2 | 1
Ø Product Categories |  | • User will be able to view the list of different categories of products. • Upon clicking of that particular item would be visible | 2 | 1
| • Particular Item | o User will be able to click on any particular item to see the description, image, and cost of that item. o User will be able to add that particular item into the cart and continue the shopping to purchase more products/items. o As soon as user clicks on “Add to cart” button user will be re-directed to cart screen. | 2 | 2
Ø Cart |  | • User will be able to View/Edit/Delete/Add the list of items he has added in the cart. • User will be able to see the Image, Title, Quantity and Price of the particular item and will also be able to see total number to items in the cart and sub-total amount of all the items in the cart | 2 | 2
| Ø Checkout/Payment | • While checking out user will have to complete following steps :- o Step 1:- User will have to add address first. User will also be able to use already saved address. It will be a mandatory step. o Step 2:- Once user will have added or selected address then user will be able to make the payment | 3 | 2
Ø My Orders |  | • User will be able to view the past and scheduled orders on the application along with product details, amount and contact number • User will be able to view the cancelled, past and scheduled order on the application | 1 | 1
| • Cancelled Order | o User can view all the details of the cancelled order along with product details and history | 1 | 1
| • Past Order | o User can view all the details of the order along with product details and history | 2 | 1
| • Order In-transit | o Users can view all the details of upcoming order with all the details along with date & time o User will have option to cancel the order and refund will be initiated for the same outside the platform o If the cancellation is done by product, user will have option to get refund or get another product for the same amount. o If user select another product, he can view the list of products in the same location within available time and book the same. o If cancellation is done by the user, then user rating might get reduced based on the reason mentioned Note: - The status of the order will be maintained from the backend | 3 | 2
Ø Settings Icon |  | • Clicking on this user would be redirected to the screen displaying My Account details with below options: - o Profile § Option to view or update the profile settings. o Password § Option to update the password. o Email § Option to view or update the e-mail ID. o Addresses § Option to view or update the address. o My Cards § Option to view, add or delete the saved payment cards. o Help/FAQ’s § This option would redirect the user to the screen displaying the list of FAQ’s uploaded by the admin. | 2 | 2

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App
Mobile App Flow for User Type 2
|  |  | 10 | 7
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
Ø Splash Screen |  | • The launch screen of the Application where end users will be able to view the company’s logo.
Ø Authentication |  | • Sign In o Drivers will be able to login into the application using the below details: § E-mail ID or Mobile Number § Password or OTP • Forgot Password o Clicking on this Drivers would be redirected to the Forgot Password screen where user need to enter the below details:- § Email ID/Mobile Number (To receive the OTP for verification). § OTP o After the OTP is verified Drivers would be asked to mention below details in order to change the password:- § New Password § Confirm New Password Note:- Credentials will be provided by Admin to the Drivers | 1.5 | 1
Ø Home Screen |  | • Drivers have option to see other sections which are listed on application are as below:- o My Orders o Notifications o Account | 1.5 | 1
Ø My Orders |  | • Drivers will be able to view the list of orders assigned • Upon clicking of that, Drivers will view the map details along with the address location of the user where the card is to be delivered • Drivers can mark the status as delivered • Drivers can also view the delivered orders in a separate section called Past Orders Note:- if the order has been cancelled, driver will be notified and the cancelled order will be visible on the list view | 3 | 2
Ø Notifications |  | • Drivers will receive different notifications on the platform | 2 | 1
Ø Settings Icon |  | • Clicking on this user would be redirected to the screen displaying My Account details with below options: - o Profile § Option to view profile settings. o Password § Option to update the password. | 2 | 2

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
16
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
Ø Login |  | • Admin will be able to login using username & password
Ø User Management |  | • This section would be used to view, edit or delete the customers. • Admin would be able to enable and disable the customers. • Admin can view size fit of the user selected by the user or scanned by the user | 2
Ø Drivers Management |  | • This section would be used to view, edit or delete the customers. • Admin would be able to enable and disable the customers. • Admin will be able to create credentials for Driver and share with them Admin will assign | 2
Ø Product Catalogue Management |  | • Admin will be able to manage the Product Catalogue and their prices from the back end. • Admin will be able to add/delete any product category from the back end. • Admin will be able to list any product under any category from the back end. • Admin will be able to remove already listed product from any category from the back end | 3
Ø Transaction Management |  | • Admin will be able to search and view transaction history on the basis of week, month or customized date from the record • All the returns would be managed by the Admin and refund will be made from Admin only Note:- Stripe connect would be used for automation of the payment method | 2
Ø Order Management |  | • Admin will be able to manage the order record from the back end. • Admin will be able to view/search/delete any particular order’s data from the record. • Admin will be able to view order history on the basis of week, month or customized date from the record • Admin will be able to assign the drivers to the order | 3
Ø Notification Management |  | • This section would be used by admin panel to push notifications to the front end users. | 2
Ø Content Management |  | • Admin will be able to manage (Add/View/Edit) the static contents. o About Us o Terms and Conditions. o Privacy Policy | 2

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -E-commerce App | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-22 | 2024-05-13
[8 empty] | Total Project Effort (in person days) | 93
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 81
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-22 | 2024-02-02 | 1 | 10 |  | 2024-02-02
2 | UI/UX (End User) | 2024-01-23 | 2024-02-02 | 0 | 9 | Design
3 | UI/UX (Driver) | 2024-01-23 | 2024-02-02 | 0 | 9 | Design
7 | End User_Mobile Application | 2024-02-05 | 2024-03-07 | 1 | 24
8 | Driver_Mobile Application | 2024-02-26 | 2024-03-08 | 15 | 10
11 | API+Admin | 2024-02-05 | 2024-04-19 | 55 | 41
14 | QA Testing | 2024-02-13 | 2024-04-29 | 55 | 55
15 | UAT Testing | 2024-03-05 | 2024-05-03 | 1 | 44
16 | GO-LIVE | 2024-05-07 | 2024-05-13 | 1 | 5
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY(WORKDAY(H8,[Lead Days]),1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E14: Kashish: Sum of Total Development Effort Days needs to be entered by TL.