## Important Information
Detailed WBS for Container Inspection
PROJECT TITLE |  |  | Container Inspection
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Swaraj
CLIENT NAME |  |  | David
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End user, Admin
Business Need | The client is seeking an application for their business that allows drivers to inspect and provide feedback on containers before delivery. They can take photos and submit a reports of damaged parts.
How to achieve? | The platform would streamline the inspection process by providing a centralized system for users, they can easily fill out the inspection form and attach pictures of any damages or issues they find during the inspection process.
User Types and Their Platforms | User Type1 | Mobile app, webpage
| Admin | Webpanel
Tech Stack | Mobile APP | React Navtive/Flutter
| WEBPAGE | HTML/CSS
| Admin | Node.js / PHP (Laravel)
| Backend (API) | Node.js / PHP (Laravel)
| Database | MongoDB / MySql
| Back-end | PHP (Laravel)

## Mobile App
Mobile App Flow for User Type 1
|  |  | 27 | 9.5 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
 Splash Screen |  | • The launch screen of the Application where end users will be able to view the company’s logo.
 Select Language |  | • The application will be available in four languages; users will select the preferred language from this screen. • The following languages will be available for users-  English  German  Portuguese  Spanish | 1 | 0.5
 Authentication • Sign In |  |  Admin will create the users profile by his admin panel and will sent their credentials and app link to the users.  The Users will be able to login into the application using the below details: o User Name o Password | 1 | 1
 Home page |  | • Home page of the users providing quick access to essential features and information related to container inspections. • It typically includes shortcuts or navigational elements for Inspection Start, Inspection History, and Settings. | 2 | 1
 Notification |  | • Users will get the reminders and any notification from the admin in this section. | 1 | 1
 Inspection start (button) | • Container details | This module allows users to initiate a new container inspection.  Container Number – o Suggestion search functionality help the users to fill the container details. Users start typing the container number, the search will suggest the similar container number in the search box; users can select the container number to fill the section. o In case of QR Scan available on the container this section will not need to fill by the users.  Trip start Location -  Trip end Location -  Trip Type – dropdown option to select “Plenty or Empty”  Date – Calendar to select the date  Time – Option to fill the time | 5 | 2
| • Check list form |  A form where users can mark off items on a checklist related to the container's condition, safety, and compliance. | 3 | 1
| • Capture images |  Users will use the device camera to capture images of the container exterior and interior.  Users will be able to include multiple image uploads. | 2
 History of Inspections |  |  This section allows users to view the list or summary of past inspections they have conducted.  There will be search or filter for inspections based on date, container. | 3 | 1
|  Filter- | o Container Number o Date | 2 | 1
 Settings Icon |  | • Clicking on this user would be redirected to the screen displaying My Profile details with below options: -  Profile o Clicking on this user would be redirected to the screen displaying user’s profile details where they can view or update the details.  Language o Users can select and update the language preference by this section of the application.  Password o User will have the option to update the password. o Password change notification will be sent to admin.  Logout o Users can logout of the application by this section. | 7 | 1

## Webpage
Webpage Flow for <UserType1>
|  |  | 15 | 0 | 0
Modules | Sub - Modules | Notes | Webpage Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
 Select Language |  | • Users will select the preferred language from this screen. • The following languages will be available for users-  English  German  French  Russian  Spanish | 2
 Person details |  | • Name – Users will fill their name in this section • Contact Number – Users have to fill their contact details in this section. | 2
 Inspection detail |  | • The section allow users to input or entering information like container identification number, type, and other relevant details.  Container Number – o Suggestion search functionality help the users to fill the container details. Users start typing the container number, the search will suggest the similar container number in the search box; users can select the container number to fill the section. o In case of QR Scan available on the container this section will not need to fill by the users.  Trip start Location -  Trip end Location -  Trip Type – dropdown option to select “Plenty or Empty”  Date – Calendar to select the date  Time – Option to fill the time | 5
| • Check list form |  A form where users can mark off items on a checklist related to the container's condition, safety, and compliance. | 3
| • Upload images |  Users will be able to include multiple image to upload in the section, such as- internal side, external side and roof top of the container. | 2
| • Submit Button |  After filling the all details users can submit the form by clicking the submit button and the saved form will be sent to the admin. | 1

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
|  |  | 11 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
 Admin Login |  | • Admin will be able to login using their unique email address and password. | 0.5
 Inspections Details |  | • Admin will get the submitted inspected form from the users in this section of the panel. • Admin will have the access to the detailed information about each inspection such as- o Container details, o Checklist form submitted by users o Images uploaded o Video added in the form o Inspection history of the same container. | 2
 User Management |  | • Admin will create the users by this section of the panel. • This section would be used to view, edit or delete the users. | 2
| • Add User |  Admin will create the user account by filling the following details- • User Name • Password • Address • Contact info | 2
| . • Share |  After create the users’ credentials admin can send them to the users to their email id.  With their login credentials, users will also get the application link to install it. | 1
 Container Management |  | • Admin will be able to add the container details by this section. • This section would be used to add, view, edit or delete the containers. • Each container inspection history will be visible to the admin.  The container inspection history will have the following details- • Inspection date • Inspection time • Inspection done by- (User name) • Checklist form • Attached images • Uploaded video | 2
 Notification Management |  | • This section would be used by admin to push notifications to the front end users. • Admin can send the alerts and any notification by this section of the panel. | 1
 Logout |  | • Admin will be able to logout from the panel. | 0.5

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Container Inspection | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2023-01-29 | 2023-05-03
[8 empty] | Total Project Effort (in person days) | 84.5
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 68
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2023-01-30 | 2023-02-10 | 1 | 10 |  | 2023-02-15
2 | UI/UX (User Type1) | 2023-01-31 | 2023-02-15 | 0 | 12 | Design
4 | Website Design (User Type1) | 2023-01-31 | 2023-02-13 | 0 | 10 | Design
7 | User Type1_Mobile Application | 2023-02-16 | 2023-03-24 | 1 | 27
9 | User Type1_Website | 2023-02-16 | 2023-03-08 | 1 | 15
11 | API+Admin | 2023-02-16 | 2023-04-14 | 42 | 20.5
14 | QA Testing | 2023-02-24 | 2023-04-24 | 42 | 42
15 | UAT Testing | 2023-03-17 | 2023-04-28 | 1 | 31
16 | GO-LIVE | 2023-05-02 | 2023-05-03 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E14: Kashish: Sum of Total Development Effort Days needs to be entered by TL.