## Important Information
Detailed WBS for Fitness Studio Booking App
PROJECT TITLE |  |  | Fitness Studio Booking App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Akansha
CLIENT NAME |  |  | Yacouba Traore
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End Users, Admin
Business Need | The client's business needs to design and develop a fitness studio app enabling users to seamlessly book and pay for cycling or yoga classes online. The app features a comprehensive list of classes, instructors, and available classes’ slots, along with search functionality based on time, and instructor
How to achieve? | The proposed application is designed to meet the business need of providing a comprehensive platform for users to class bookings and online payments, offering targeted promotions to drive new user sign-ups and app downloads.
User Types and Their Platforms | End User | Mobile Application
| Admin | Webpanel
Tech Stack | Mobile Application | Flutter / React Native
| Admin | Node.js / PHP (Laravel)
| Backend (API) | Node.js / PHP (Laravel)
| Database | MongoDB / MySql
| Back-end | PHP (Laravel)

## End User
Mobile App Flow for User Type 1
|  |  | 36 | 20 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
 Splash Screen |  | • This would be launch screen of the application displaying the brand Logo and Name. | 1
• Sign In |  | o The Users will be able to login into the application using the below details: • E-mail ID or Mobile Number or social media. • Password or OTP | 0.5 | 0.5
| • Forgot Password | o Clicking on this user would be redirected to the Forgot Password screen where user need to enter the below details:- • Mobile Number (To receive the OTP for verification). • OTP o After the OTP is verified user would be asked to mention below details in order to change the password:- • New Password • Confirm New Password | 1 | 0.5
• Sign Up / Register |  | o Users will be able to register using below details: - • First Name & Last Name • E-Mail ID & Mobile Number • Password • Confirm Password • Checkbox for Terms and Conditions | 0.5 | 0.5
 Profile Setup Page |  | • Users can create their profile by adding their basic details into the application such as- o Name o Image o Email address o Phone Number o Address • User can select the “Later” option for creating the profile. | 1 | 0.5
 Home Screen |  | • Home screen will display the relevant information like upcoming classes, and promotions. • The home screen displaying below sections or details:- o Logo of the Business. o Carousel Images managed by the admin. o List of classes by their instructor’s details and timings. o Search & Filter o Notifications | 4 | 2
 Search and Filter |  | • Users can browse through the class schedule to view available cycling sessions. • Users will be able to search the classes by entering the instructor name | 2 | 1
 Class Details |  | • Clicking on a specific class, users will redirect to its detail page. • The classes detail page provided the information such as - o Class overview o Instructor name o Class timings o location o Status - Available slots or No Available Slots o Book Now (Button) • Users can book the classes on the platform by clicking the book now button. | 6 | 2
 Book a Class |  | • Users can select a class and book a slot based on their preferred time and instructors. • User can select payment mode and pay for the same. • User will pay the amount in advance by using the in-app payment system or integrated payment gateway. • Users can also cancel or reschedule their bookings. • Cancel/Reschedule Booking o Users can cancel or reschedule the booking. o If user cancel the booking, they will get the refund amount for the same. o In case of reschedule, users will redirect to the booking process again and amount will be carry forward this time so they don’t have to pay again. | 8 | 5
 Notifications |  | • This icon would be displayed on the top-left side of the application. • This section would display the list of all the notifications that have been received by the user. • The notifications would be In-App as well as Push-Notifications • The user would receive notifications for below scenario:- o When the class booking is confirmed. o Reminder for the booked classes. o Any notification sent by admin. | 3 | 2
 My Account | • My Bookings | o User will be able to view the past and scheduled bookings on the application along with class’s details. o Past Bookings • The section allow the users to view at the past booking. | 3 | 2
| o Scheduled Bookings | • Users can view all the details of upcoming bookings with all the details along with date & time. • User will have option to cancel the booking. • User can select another timing for the class and book the same. | 2.5 | 1.5
| • My Profile | o Users would be able to view and update the below details:- • Name • Image • Address • Phone number • Email address | 1 | 1
|  | o Delete Account o Users will be able to access the application policies and company details by this section- o Privacy policy o Refund Policy o Terms and conditions o Contact us o About us | 2 | 1
| • Sign Out | o Users will be logout form the application by this section | 0.5 | 0.5

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
|  |  | 17 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
 Login |  | o Admin will be able to Login into the admin web panel using their login credentials. The admin will use the following credentials such as:  Email id  Password | 1
 User Management |  | o Admin will be able to view the list of all application users in this section. o Admin will be able to activate/deactivate the account from the admin panel. | 2
 Instructors Management |  | o Admin can create the instructors by this section o Admin will be able to manage the instructors from the backend. | 1
 Classes Management |  | o Admin will be able to add the classes by this section of the platform. o Admin will be able to remove or edit any class details.  Add Class • Class overview • Class days • Timing/session • Slots • Instructor Name • Status - available or out of stock | 4
 Bookings/Transactions Management |  | o Admin can view the booking on the platform along with details of the users. o Admin can share the refund status to the user once the amount has been transferred from the Admin side. | 3.5
 Content Management |  | o Admin will be able to manage Carousel Images for mobile o Admin will be able to update and add text for privacy policy o Admin will be able to update and add text for refund policy o Admin will be able to update and add text for About Us o Admin will be able to update and add text for Terms and Condition. | 2.5
 Notification Settings |  | o Admin will be able to add the notification content form this section of the platform. o Admin will be able to set the reminder for the users form this section. | 2
 Change Password |  | o Admin will be able to change the password by this section. . | 0.5
 Logout |  | o The section allow the admin to logout form the system | 0.5

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Fitness Studio Booking App | [7 empty] | Development Start Date | Development End Date
[8 empty] | 44962 | 2023-05-01
[8 empty] | Total Project Effort (in person days) | 83
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 61
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2023-02-06 | 2023-02-17 | 1 | 10 |  | 2023-02-20
2 | UI/UX (End User ) | 2023-02-07 | 2023-02-20 | 0 | 10 | Design
7 | End User _Mobile Application | 2023-02-21 | 2023-04-11 | 1 | 36
11 | API+Admin | 2023-02-21 | 2023-04-12 | 37 | 37
14 | QA Testing | 2023-03-01 | 2023-04-20 | 37 | 37
15 | UAT Testing | 2023-03-22 | 2023-04-26 | 1 | 26
16 | GO-LIVE | 2023-04-28 | 2023-05-01 | 1 | 2
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E12: Kashish: Sum of Total Development Effort Days needs to be entered by TL.