## Important Information
Detailed WBS for Fitness Application
PROJECT TITLE |  |  | Fitness Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Akansha
CLIENT NAME |  |  | Rapheal
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End User
Business Need | The client seeks an iOS Fitness App for a smooth training experience, emphasizing the utilization of iOS features for enhanced user interaction. Key requirements involve implementing spoken commands for app control and integrating admin tracking for user activity monitoring, contributing to app optimization.
How to achieve? | The integration of iOS features, for spoken commands for real-time tracking, enhances user interaction, ensuring a seamless training experience.
User Types and Their Platforms | End User | Mobile application
| Admin | Web panel
Tech Stack | Mobile Application | React Native/Flutter
| Admin | Laravel/ Node js
| Backend (API) | Laravel/ Node js
| Database | MySql/Mongo DB
| Back-end | PHP (Laravel)

## UserType1_Mobile App
Mobile App Flow for User Type 1
|  |  | 72 | 54 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
 Splash Screen |  | • The launch screen of the Application where end users will be able to view the company’s logo. | 0 | 0
• Sign In |  |  The Users will be able to login into the application using the below details: o E-mail ID/Mobile Number o Password | 1 | 1
• Sign Up / Register (As User) |  |  Users will be able to register using below details: - o First Name & Last Name o E-Mail ID / Mobile Number o Password o Confirm Password o Checkbox for Terms and Conditions | 1 | 0
• OTP Verification |  |  Sign-up process has to be verified through entered email id/Mobile number. | 0 | 0
 Preference Selection |  | • Multiple screens where user will be able to select their fitness goals and preferences such as:-  Lose Weight  Maintain Weight  Gain Weight  Manage Stress  Gain Muscle • Activity level  Not Active  Active  Very Active | 2 | 2
 Medical Form |  | • A screens that would comprise of details that would be provided by the user to get the details of the medical history & records of the user such as:-  Age  Gender  Height  Weight  Medications  Health Conditions | 2 | 2
• Voice command tutorial |  |  At first as a new users; users find the tutorial video on using voice commands for app workout control. | 2 | 1
• Dashboard/Homepage |  |  The personalized workout recommendations on the home screen dashboard help users easily access tailored exercise routines based on their preferences and goals. | 4 | 3
• Add Workout Machine |  |  Users will be able to add their workout machine of choice to the app.  Users can give the any name to the machine. | 3 | 3
 Start workout |  | • User press the option to start workout and the application allow the system to take the users commands for the next steps | 4 | 3
• Select Machine |  |  Users command the application to select the workout machine, e.g., "Select the Machine A." | 3 | 2
• Counting Steps |  |  Users vocally indicate the start of counting to the application, e.g., "Start counting."  Users will count their steps aloud while the application notes down the count in real-time.  The real-time tracking of steps allows the app to accurately measure and record the user's progress throughout their workout. | 7 | 5
 Time Gap Consideration |  | o Its recognizing that different exercises may have varying durations and step frequencies, the feature accommodates time gaps between step counts. o This will help users to focus on their exercises without the need to provide step counts frequently. | 7 | 6
• Exercise Completion |  |  After completing the set or exercise for the particular machine, User commands to stop counting, e.g., "Stop counting."  Application records the step count for the specific exercise/machine. | 5 | 3
• Machine Change: |  |  Users command the application to change the workout machine, e.g., "Switch to Machine B."  The application updates the exercise type and prompts the user to start counting for the new exercise. | 4 | 2
• Repeat Cycle |  |  Users go through the cycle of starting, counting, and stopping for each selected workout machine. | 3 | 2
• Finish Workout |  |  After completing all exercises, users command the application to finish the workout, e.g., "Finish workout." | 4 | 3
• Real-time Feedback |  |  The application provides real-time feedback on each exercise, summarizing step counts, sets, and overall performance. | 6 | 5
• Workout Summary |  |  Users can review a detailed summary of the entire workout, including step counts and sets for each exercise. | 2 | 2
 Settings | • Profile |  Clicking on this user would be redirected to the screen displaying user’s profile details where they can view or update the details  Users will be able to adjust settings, preferences, or voice command sensitivity in the application settings. | 5 | 4
| • Workout machines |  Users will be able to add more machines into the system and can delete the existing machines details. . | 3 | 2
| • Feedback |  This section would allow users to submit the feedback to the admin regarding the mobile application. | 2 | 1
| • Password |  Users will have to option to update the password. | 1 | 1
| • Logout: |  Users can log out securely when done with the session | 1 | 1

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
|  |  | 12 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
 Admin Login |  | • Admin will be able to login using their unique email address and password. | 1
 User Management |  | • This section would be used to view, edit or delete the users. • Admin would be able to enable and disable the customers. • Admin would be able to see the activities & progress of the users. | 5
 Content Management |  | • Admin will be able to manage (Add/View/Edit) the static contents.  About Us  Terms and Conditions.  Privacy Policy | 1
 Customer Support |  | • Providing customer support and assistance to users experiencing issues or inquiries. • Addressing technical problems or concerns raised by users. | 3
 Change Password |  | • Admin will be able to change the password by this section. | 1
 Logout |  | • The section allow the admin to logout form the system. | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Fitness Application | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-28 | 2024-06-25
[8 empty] | Total Project Effort (in person days) | 148
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 107
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-29 | 2024-02-09 | 1 | 10 |  | 2024-02-12
2 | UI/UX (End User) | 2024-01-30 | 2024-02-12 | 0 | 10 | Design
3 | End User_Mobile Application | 2024-02-13 | 2024-05-22 | 1 | 72
4 | API+Admin | 2024-02-13 | 2024-06-03 | 80 | 66
5 | QA Testing | 2024-02-21 | 2024-06-11 | 80 | 62
6 | UAT Testing | 2024-03-13 | 2024-06-17 | 72 | 72
7 | GO-LIVE | 2024-06-19 | 2024-06-25 | 1 | 5
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Note on E12: Kashish: Sum of Total Development Effort Days needs to be entered by TL.