## Important Information
Detailed WBS for Transportation Booking
PROJECT TITLE |  |  | Transportation Booking
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Bharati
CLIENT NAME |  |  | Iris
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End User & Admin
Business Need | Client is looking for an applications for booking transportation, where user can book the transportation vehicle for the same. Users will be able to view the list of transport on the basis of current location and view the availability for transportation. Admin will have their own flow of application where they can view the upcoming bookings by the user. Admin can also cancel the upcoming bookings and tell the reason for the same.
How to achieve? | Over this platform we will provide users to register and view the list of availability for booking transport. User can book the transport by paying for the estimated amount for the duration. User can also cancel the booking and enter the reason for the same. Transport, upon booking user will receive the confirmation via notification that the booking has been made. Admin can also cancel the scheduled booking.
User Types and Their Platforms | End User | Application
| Admin | Web Panel
Tech Stack | Application | Flutter / React Native
| Admin | HTML & CSS/ Angular
| Backend (API) | Node.js / PHP (Laravel)
| Database | MongoDB / MySql
| Back-end | PHP (Laravel)

## UserType1_Mobile App
Mobile App Flow for User Type 1
|  |  | 39 | 33 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)
 Splash Screen |  | • The launch screen of the Application where end users will be able to view the company’s logo.
 Authentication |  | • Sign In o The Users will be able to login into the application using the below details:  E-mail ID or Mobile Number  Password or OTP • Forgot Password o Clicking on this user would be redirected to the Forgot Password screen where user need to enter the below details:-  Email ID or Mobile Number (To receive the OTP for verification).  OTP o After the OTP is verified user would be asked to mention below details in order to change the password:-  New Password  Confirm New Password • Sign Up / Register (As Customer) o Customers will be able to register using below details: -  First Name & Last Name  E-Mail ID/Mobile Number  Password  Confirm Password  Checkbox for Terms and Conditions • OTP Verification o Sign-up process has to be verified through mobile number/email ID | 2 | 2
 Home Screen |  | • This screen would be the main screen of the application containing past bookings and list of available slots • This screen would comprise of below details: - o Search Transport o My Bookings o Notification o Settings Note:- If the service is on-going, users will view the current service on home screen | 3 | 2
 Search Transport |  | • User will be able to search from the categories of the repairs such as:- | 2 | 2
| • Pick-up Location | o The location access feature on the application will detect user’s current location. o User will be able to enter their pick-up location manually if it’s different from the current one. o Users can also select location by placing the pin icon on the map. o User will be able to view and access the location address suggested by map. | 4 | 3
| • Drop-off Destination | o User will be able to type and enter the drop-off destination address manually in the application. o User will be able to view the location address suggested by the map. o Users can also select location from the saved destinations. o User will be able to add multiple drop-off points. | 4 | 3
| • View Preferred Taxi | o User can view the details of seats in the vehicle o User will be able to view the following details:  Users will be able to view price estimates.  Users will be able to view driver details like Name of driver, UIN no., Picture of driver, No. of rides completed, Vehicle name and o User will be able to view the taxis available along with its slots, and user will click on Book Now | 3 | 3
| o Book Now |  User will view the details of the transport along with the calendar for availability  User will select the date and time of booking on calendar | 3 | 3
| Payment |  User can select payment mode and pay for the same  User will pay the amount in advance Note: - In case of cancellation by the user, they will get refund and that would be done through the Admin. | 4 | 3
 My Bookings |  | • User will be able to view the past and scheduled bookings on the application along with transport details, amount, vehicle details and contact number • User will be able to view the cancelled, past and scheduled bookings on the application | 2 | 2
| • Cancelled Bookings | o User can view all the details of the cancelled booking along with transport details and history | 1 | 1
| • Past Bookings | o User can view all the details of the booking along with transport details and history | 2 | 1
| • Scheduled Bookings | o Users can view all the details of upcoming bookings with all the details along with date & time o User will have option to cancel the booking and enter the reason for the same o Refund will be initiated for the same from the Admin o If the cancellation is done by transport, user will have option to get refund or get another transport for the same amount. o If user select another transport, user will get next available slots for booking otherwise refund | 3 | 3
 On Going Service |  | • User can view the current booking along with details • User can also view the details of the transport for the current booking along with the amount paid | 2 | 2
 Notification |  | • The notification would be on engagement and transaction basis. | 2 | 2
 Settings |  | • Clicking on this user would be redirected to the screen displaying My Account details with below options: - o Password  Option to update the password. o Email  Option to view or update the e-mail ID | 2 | 1

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
|  |  | 14 | 0
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days) | Admin Development (JAVA) (in days)
Login |  | Admin will be able to login using username & password
 Dashboard |  | • Quick links for the given features would be given like:- o User Management o Bookings Management o Transactions Management o Availability & Pricing o Content Management | 1
 User Management |  | • Admin will be able to manage the users from the backend. • Admin will be able to activate/deactivate the account of the users from the backend. | 2
 Transaction Management |  | • Admin can view all the transactions done by the users on the platform • For cancellations, admin will directly refund the amount to the user in their bank account Note:- Stripe connect will be integrated for the automation process of refund amount | 3
 Availability & Pricing |  | • Admin can set the availability of the given day, week and month by selecting what time they are available for service • Admin can set the pricing on the basis of per hour | 3
 Bookings Management |  | • Cancelled Bookings o Admin can view all the details of the cancelled booking along with user details and reason mentioned • Past Bookings o Admin can view all the details of the booking • Scheduled Bookings o Admin can view all the details of upcoming bookings with all the details along with date & time o Admin will have option to cancel the booking and enter reason for the same • On Going Service o Admin can view the current booking along with details of the user | 3
 Notification Management |  | • Admin can send push notifications to the users from the backend | 1
 Content Management |  | • Admin will be able to manage (Add/View/Edit) the static contents. o Terms and Conditions o Privacy Policy | 1

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -Transportation Booking | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-01-08 | 2024-04-23
[8 empty] | Total Project Effort (in person days) | 98
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 77
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Duration (days)
1 | FSD Creation and Approval | 2024-01-08 | 2024-01-19 | 1 | 10 |  | 2024-01-24
2 | UI/UX (End User ) | 2024-01-09 | 2024-01-24 | 0 | 12 | Design
3 | End User _Mobile Application | 2024-01-25 | 2024-03-19 | 1 | 39
4 | API+Admin | 2024-01-25 | 2024-04-01 | 48 | 47
5 | QA Testing | 2024-02-02 | 2024-04-09 | 48 | 48
6 | UAT Testing | 2024-02-23 | 2024-04-15 | 1 | 37
7 | GO-LIVE | 2024-04-17 | 2024-04-23 | 1 | 5
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)
Duration (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E12: Kashish: Sum of Total Development Effort Days needs to be entered by TL.