## Important Information
Detailed WBS for <Project Name>
PROJECT TITLE |  |  | Task Management App
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Akansha
CLIENT NAME |  |  | Saba
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | End User, Admin
Business Need | the Client' purpose of the development of the Task Management App is to enhance efficiency, productivity, and collaboration within construction projects of her company. users will be bale to add the comments and input in to the checklist or the tasks and real time updates will be capture in the tasks.
How to achieve? | The platform will assist user to providing real-time updates and facilitating collaboration among team members in construction projects. Its accessibility via mobile and web apps ensures seamless coordination, promoting efficiency and productivity.
User Types and Their Platforms | End User | Mobile application, web panel
| Admin | Web Panel
Tech Stack | Mobile Application | React Native / Flutter
| Admin | Node.js / PHP (Laravel)
| Backend (API) | Node.js / PHP (Laravel)
| Database | MongoDB / MySql
| Back-end | PHP (Laravel)

## End User_Mobile App
Mobile App Flow for User Type 1
|  |  | 18 | 9
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
 Splash screen |  | • User will be able to view splash screen of the app with company logo. | 0.5
 Login |  | • The User will be able to Login on the platform using their login credentials that they have created by the admin and shared to them. The User can use the following credentials such as the: o Email id o Password | 0.3 | 0.2
 Forget Password |  | • If user forget the password then simply user clicking on forgot password link and where user has to fill the email id. • After entering the email id user will get an OTP on the email that user has to fill into the OTP field. • After filling the OTP user redirect to create new password screen where user can recreate the password. | 0.6 | 0.3
 Home Screen |  | • User will be able to see a summary of their tasks, including the number of tasks pending, in progress, or completed. • Users have quick access buttons or links to navigate directly to their task list or checklist screens. • Users can view their profile information, including their name, role, and contact details, ensuring accurate identification and personalization within the app. • User will be able to view a sidebar or hamburger menu that will provides easy access to other app functionalities • Hamburger Menu o My Profile o Notification settings o Change Password o Contact Us o Delete Account o Logout | 3 | 1.4
 Notification |  | • The notification allow user to view important alerts, updates, or messages. • All users will get the alerts when there will be any kind of activity related to the task. Such as – o When user done or completed the task o When user add the comment. o When admin change the task stage o When admin add any new task o When user update the task and checklists. | 2 | 1
 Search |  | • User will be able to search any particular task or job by using its name through search bar. | 1 | 1
 Task List |  | • The task list section presents users with a comprehensive overview of all tasks. • Every task listed in the task list section includes essential details such as the o Task title o Date (Task added date) o Deadline (Task Deadline date) o Stage/Level o Current status. (Ongoing/completed) • Stage and status indicators provide users with visual cues to track the progress of their tasks at a glance. • Every task listed in the task list section is clickable, allowing users to access detailed task information and page. | 3 | 1
 Task detail Page |  | • The task detail page within the application provides users with comprehensive information specific to an individual task. o Name and title of the task o Description o Stage o Client details o Location o Task checklists  Job name  Job details  Job comments  Status (open/closed) | 3 | 1
 Checklist Section |  | • All the users will be able to access and view checklists of each task but only accessed users will be able to edit and add their comments on the task sheet. • Accessed users will be able to mark them to be completed from their mobile phones. • Users can simply tap on checklist items to indicate that the corresponding task requirements have been fulfilled or completed. • Accessed Users will be able to add the comments on the each task. • As users mark checklist items as completed or add comment, the app provides real-time updates to reflect the changes in the checklist status. | 2.5 | 1.5
 My account | • Profile | o User will be able to add and update their profile details such as-  Name  image  Designation  Location  Address | 1 | 0.5
| • Password | o Users will be able to change their password from this section. | 0.3 | 0.3
| • Notification | o Users will be able to manage the notification settings via this section. | 0.5 | 0.5
| • Logout | o Users will be able to log out of the App. | 0.3 | 0.3

## UserType1_Website (hidden)
Website Flow for <UserType1>
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days)

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)

## UserType2_Website (hidden)
Website Flow for <UserType2>
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days)

## WebPanel (hidden)
WebPanel Flow
0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days)

## Admin
Admin Flow
6
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
 Admin Login |  | • Admin will be able to login using their unique email address and password. | 0.3
 User Management |  | • Admin will create the users account form the admin panel. • Admin will assign a role to every user with view and Editor Access. • There will be different role such as- Supervisors, Managers and staff. • After creating the users account they can share them the credentials to their mail ids. • The admin accesses the user management section to manage user accounts, roles, and permissions. • User will be able to deactivate the user’s accounts. | 1
 Task Management |  | • The admin manages tasks by creating, editing, the tasks to users based on project requirements. • Functions include adding new tasks, updating task details (e.g., title, description, and deadline), and tracking task progress. | 1
 Checklist Management: |  | • The admin oversees the creation and management of checklists associated with tasks. • Functions include creating checklist for different construction stages, editing checklist items, assigning checklists to tasks, and monitoring checklist completion status. | 1.3
 Notification Settings |  | • The admin configures notification settings for the application, determining which types of notifications are sent to users and under what conditions. • Functions include enabling/disabling notifications for task updates, checklist completions, new task assignments, etc. | 1
 Listing Management |  | • Admin will be able to add the list fields from this section. • Such as – adding field option in checklist fields and task details fields. • The section serves the purpose of organizing and maintaining a structured listings associated with the tasks. | 1
 Change Password |  | o Admin will be able to change the password by this section. | 0.2
 Logout |  | o The section allow the admin to logout form the system. | 0.2

## Gantt_Chart Summary
Draft Project Schedule
[9 empty] | Development Start Date | Development End Date
Draft Gantt Chart -Task Management App | [8 empty] | 2024-02-15 | 2024-03-15
[9 empty] | Total Project Effort (in person days) | 36
[9 empty] | Total Duration (in business days) | 22
Sl. No. | Tasks | Start_Date | End_Date | Duration (days) | Component (Design Page and API) Numbers
1 | FSD Creation and Approval | 2024-02-15 | 2024-02-19 | 3 | 0 |  |  | 2024-02-19
2 | UI/UX (End User) | 2024-02-15 | 2024-02-19 | 3 | 15 | No of Screen Designs | Design
7 | End User_Mobile Application | 2024-02-20 | 2024-03-14 | 18 |  | No of Components
11 | API | 2024-02-20 | 2024-03-04 | 9 | 32 | No of API's
12 | Admin | 2024-02-20 | 2024-02-28 | 6 |  | No of Admin Component
14 | QA Testing | 2024-02-20 | 2024-03-15 | 18 | 0
15 | UAT Testing | 2024-02-21 | 2024-03-18 | 18 | 0
16 | GO-LIVE | 2024-03-19 | 2024-03-20 | 2 | 0
Formulas:
Start_Date = WORKDAY([Start_Date, row above],1,)
Start_Date = WORKDAY([End_Date, row above],1,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Duration (days)],),-1,)