## Important Information
Detailed WBS for The Best Sandwiches Website and Application v1.0
PROJECT TITLE |  |  | The Best Sandwiches Website and Application
BUSINESS DEVELOPMENT EXECUTIVE |  |  | Akanksha
CLIENT NAME |  |  | Marielyn
This is a work breakdown structure, which focuses on creating a project schedule that is broken down into stages.
User Types | Users & Admin
Business Need | To have a platform where ends users can view menu items (Foods or beverages), they will order any Foods or Beverages on the platform.
How to achieve? | As a solution, we will design and develop an application and website that will fulfill the need of end users where they can register and view menu items (Foods or beverages) with the following (Item Name, Image, Menu type, Prices & Descriptions) details & they can order any Foods or beverages on the platform.
User Types and Their Platforms | Users | Mobile Application & Website
| Service Providers | Web-based panel
| Admin | Web-based panel
Tech Stack | Front-end | Flutter/ React Native
| Website Front end | React js
| Back-end | Node js
| Database | MySQL/ Mongo DB
| Back-end | PHP (Laravel)

## Users_Mobile App
Mobile App Flow for Users
|  |  | 16 | 16
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days)
Authentication | Ø Sign-up | • Users will be able to signup on the platform, Users will have to enter the below details on the application. o Users Name  Users will have to enter the user first and last name on the platform. o Email address  The Users will get the option to sign up on the platform using their Email Address. o Phone Number  The Users will get the option to sign up on the platform using their Email Address. o Password  Users will be able to create the password for their account, the Users can create the password in Characters, Special characters, Upper case, Lower case, Numbers on the platform. | 1 | 1
| Ø Login | • Users will able to log in on the platform using the login credentials on the application. o User Name o Password | 1 | 1
| Ø Forgot Password | • When Users click on the reset option they will get a code on the registered Email ID, after that they will be able to create a new password. | 1 | 0
Ø Home Screen |  | • Users will be able to view the below options on the home screen. o Home o Menu o Search o My Cart o Notifications o My Account | 1 | 1
| Ø Search | • Users will be able to search Foods and Beverages by keyword on the application. | 1 | 2
| Ø Menu | • Users can view listed Food menu with the below details on the app. o Listed Foods and Beverages o Food and Beverages Name and Images o Food and Beverages Price o Description o Add to Cart • Users will be able to add the Foods and Beverages into the Cart. | 4 | 4
| Ø My Cart | • Users will be able to view all the foods and beverages that they have added into the cart on the app. • Users will be able to add or remove the foods or beverages from the cart. • Users can increase or decrease the quantity of the added foods or beverages from the cart. | 2 | 2
| Ø Checkout | • User will be able to check out from the cart by completing the following steps:- • Users will be able to add delivery address on the application. • Users will be able to add and apply Promo Code or Gift cards at the time of checkout on the application. • User will be able to place order via Debit card, Credit card and PayPal on the application. • After completion of the payment, users will get an order confirmation message “You have successfully place the order”. | 2 | 2
| Ø Notifications | • Users will receive the below types of notifications on the app. o Order Booked Notifications o Order On the way Notifications o Order Delivered Notifications o New Updates Notifications | 1 | 1
| Ø My Account | • Profile: - Users will be able to view/edit their profile details: - Name, Email and Phone Number. • Change password: - Users will be able to change their password. • Manage Address: - Users will be able to manage the address on the app. • My Orders: - User will be able to view the all orders history on the app. • Payment Method: - Users will be able to manage the payment method (add or remove) Credit card, Debit Card and PayPal details on the application. • Help Center: - If users will face any issue, Users will be able to Help Center with team by Email. • Logout: - Users will be able to logout from the application. • Delete Account: - Users will be able to delete their account from the application. | 2 | 2

## UserType2_Mobile App (hidden)
Mobile App Flow for User Type 2
|  |  | 0 | 0 | 0
Modules | Sub - Modules | Notes | Mobile App Development (in days) | API (Node js / PHP (Laravel) (in days) | API (JAVA) (in days)

## Users_Website
Website Flow for Users
|  |  | 18 | 7
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days)
Ø Home Page |  | • Users will be able to view the below options on the home page. o Home o Search o Menu (View Different Types of Menu) o My Account (Displayed After login) o Catering o About us • Users can view the below options in the footer menu. o Location and Contact Us o Social Media Icons | 1 | 0
| Ø Search | • Users will be able to search Foods and Beverages by keyword on the platform. | 1 | 0
| Menu | • Users can view listed Food menu with the below details on the platform. o Listed Foods and Beverages o Food and Beverages Name and Images o Food and Beverages Price o Description o Add to Cart • Users will be able to add the Foods and Beverages into the Cart. | 2 | 0
| Ø My Cart | • Users will be able to view all the foods and beverages that they have added into the cart on the platform. • Users will be able to add or remove the foods or beverages from the cart. • Users can increase or decrease the quantity of the added foods or beverages from the cart. | 2 | 1
| Ø Checkout | • User will be able to check out from the cart by completing the following steps:- • Users will be able to add delivery address on the platform. • Users will be able to add and apply Promo Code or Gift cards at the time of checkout on the application. • User will be able to place order via Debit card, Credit card and PayPal on the platform. • After completion of the payment, users will get an order confirmation message “You have successfully place the order”. • Note- For ordering the food, users need to signup or login on the platform. | 2 | 1
Authentication | Ø Sign-up | • Users will be able to signup on the platform, Users will have to enter the below details on the platform. o Users Name  Users will have to enter the user first and last name on the platform. o Phone Number  The Users will get the option to sign up on the platform using their Email Address. o Email address  The Users will get the option to sign up on the platform using their Email Address. o Password  Users will be able to create the password for their account, the Users can create the password in Characters, Special characters, Upper case, Lower case, Numbers on the platform. | 1 | 0
| Ø Login | • Users will able to log in on the platform using the login credentials on the platform. o User Name o Password | 1 | 0
| Ø Forgot Password | • When Users click on the reset option they will get a code on the registered Email ID, after that they will be able to create a new password. | 1 | 0
| Ø My Account | • Profile: - Users will be able to view or edit their details like- Name, Email, Phone Number, Birth date, and gender. • Change password: - Users will be able to change his password. • Orders: - Users will be able to view all the orders (Past and Upcoming) on the platform. • Manage Address: - Users will be able to manage the address on the platform. • Manage Payment Method- Users will be able to manage payment mode on the platform. • Help Centre: - If Users will face any issue, Users will be able to Help Center with team by Email. • Logout: - Users will be able to logout from the platform. | 3 | 1
| Ø Catering | • If the user is looking for lunch at the office, party, or special private event, they can request it by adding the below details. o Name o Email o Phone o Enter your message | 1 | 1
| Ø About Us | • Users will be able to view the content regarding the services of the company. • Users will be able to view the information about the services. | 1 | 1
| Ø Location and Contact Us | • Users can view map view location on the platform. • If Users will face any issue, users will be able to connect with team by adding the below details. o Contact number o Email ID o Address • Users can also send the message to the organization by adding the below details. o Name o Email address o Add Message | 1 | 1
| Ø Social Media Icons |  Users will be able to view below Social Media Icons on the website.  Facebook, Twitter, YouTube and Instagram  When Users will click any social media icons they will be redirect to Social Media page, where can view the details. | 1 | 1

## Service Providers_Website (hidden)
Website Flow for Service Providers
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Website Development (in days) | API (Node js / PHP (Laravel) (in days)
| Ø Sign-up | • Service Providers will be able to signup on the platform, Service Providers will have to enter the below details on the platform. o Service Providers Name  Service Providers will have to enter the user first and last name on the platform. o Phone Number  The Service Providers will get the option to add their phone number. o Email address  The Service Providers will get the option to sign up on the platform using their Email Address. o Password  Service Providers can create the password in Characters, Special characters, Upper case, Lower case, Numbers on the platform. o Business Name  Service Providers need to add their business name. o Website (Optional)  Service Providers need to add their Website URL. o Users need to add the below detail for set-up their profile o What services do you offer?  Choose your primary and up to 3 related service types  What's your team size?  Business location (Online Service Only)  Which software are you currently using?  How did you hear about this platform?
| Ø Choose language | • After the registration users get an option to choose app language (English and Arabic) on the platform.
| Ø Login | • Service Providers will able to log in on the platform using the login credentials on the platform. o User Name o Password
| Ø Forgot Password | • When Service Providers click on the reset option they will get a code on the registered Email ID, after that they will be able to create a new password.
Ø Dashboard |  | • Service Providers will be able to view the below options on the dashboard. o Home o Calendar o Clients o Catalogue o Team o Report o Business Setting o Online Profile o Search o Notification o My Account
| Ø Home | • Service Providers can view the below analytics data on the dashboard. o Recent Sales o Upcoming Appointments o Appointments activity o Today's next appointments o Top services o Top team member
| Ø Calendar | • Service Providers can view self and team member’s calendar according to the date and time. • Service Providers can also manage new appointment, blocked time, new sale and new payment method.
| Ø Clients | • Service Providers will be able to view clients data with the below details o Client Name and Email o Mobile number o Reviews o Sales o Created Date • Service Providers can find the Client by keyword and also apply the following filters- gender and client group. • Service Providers can add new clients by adding the following details- First name, Last name, Mobile number, and email address, Gender, Date of birth, Year, Client info, and Address. • Service Providers will also change the order, download CSV and download excel.
| Ø Catalogue | • Service Providers will be able to manage the services and their details. o Service Type o Service Name o Service Price and Duration • Service Providers can also manage (add, remove and edit) service and category. • Service Providers can manage the Gift cards. • Service Providers will also change the order, download CSV and download excel.
| Ø Team | • Service Providers will be able to view and manage the team members. o Listed team member with the following details Name, Contact, Email, and Ratings o Search Team Member by keywords and filters (Active, Archived and All) • Service Providers will also perform the following actions- Edit Team Profile, View Calendar, View Scheduled shifts and Add time off. • Service Providers will be able to add new team member by adding the following details First Name, Last Name, Email, Phone number, Job title and Employment details (Start and End date), they will also manage the Workspace (Services and Location) and Commission. • Service Providers will be able to view and manage team members Scheduled shifts according to the calendar. • Service Providers will also change the order, download CSV and download excel.
| Ø Reporting and analytics | • Service Providers will be able to view the following Reporting and analytics- All, Sales, Finance, Appointments, Team and Clients.
| Ø Business Settings | • Service Providers will be able to view and manage the below settings of the Business. o Account setup- Business details, Billing details and invoices, Text messages, Locations, Online booking, Resources, and Business closed periods. o Clients- Client notifications, Referral sources, and Cancellation reasons o Services – Services menu o Sales- Receipt sequencing Templates, Taxes, Receipt template, Taxes, Service charges, Tips, Payment types, Gift cards and upselling. o Team- Team members, Scheduled shifts, Permissions and Commissions
| Ø Search | • Service Providers will be able to search appointments and clients by keyword on the platform.
| Ø Notifications | • Service Providers will receive below in-app notifications on the application. o New Booking o Service Reminder o New Update
| Ø My Account | • Profile: - Service Providers can view the following details - Name, location, review, appointments and about me. • Change password: - Service Providers will be able to change his password. • Review: - View star ratings and reviews left by clients after their visit. • Settings: - Service Providers will be able to view or edit the below details. o Personal Information- Name, Email and Phone Number. o Security- Change Password o Social Logins o Delete Account • Workspace- Service Providers will be able to manage the workspace settings (Calendar sync, Workspace notifications and Delete Workspace) on the platform. • Help Centre: - If Users will face any issue, Users will be able to Help Center with team by Email. • Change Language: - Service Providers choose their preferred app language (English and Arabic). • Logout: - Service Providers will be able to logout from the application.

## WebPanel (hidden)
WebPanel Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | WebPanel Development (Node.js/PHP(Laravel) (in days) | WebPanel Development (JAVA) (in days)

## Sub-Admin (hidden)
Sub-Admin Flow
|  |  | 0 | 0
Modules | Sub - Modules | Notes | Sub-Admin Development (Node.js/PHP(Laravel) (in days) | Sub-Admin Development (JAVA) (in days)

## Admin
Admin Flow
16
Modules | Sub - Modules | Notes | Admin Development (Node.js/PHP(Laravel) (in days)
Admin |  Users Management | • Admin will be able to manage Users from the admin panel. • Admin will be able to View/Delete/Add any particular Users from the admin panel. | 2
| Ø Manage Restaurant Menu | • Admin will be able to manage Restaurant Menu from the admin panel. • Admin will be able to manage the Restaurant Branches, Admin will add or remove the branches with their Food menu from the admin panel. • Admin will be able to add/remove/edit the Food menu, Food/Beverages price, images and descriptions from the admin panel. | 3
| Ø Manage Coupons | • Admin will be able to manage Coupons from the admin panel. • Admin will be able to create Coupons and share it with the users from the admin panel. | 2
| Ø Manage Orders and Catering Request | • Admin will be able to manage and view user’s orders and Catering Request from the website. • Admin will be able to accept or reject the users order on the website. | 3
|  Notification Management | • Admin will be able to manage share the update with the users via notifications from the admin panel. | 2
| Help center | • Admin can manage and view all the issues of the users, admin can provide the resolution to the users based on the issues. | 2
|  Content Management | • Manage About Us • Manage Terms and Conditions • Manage FAQ, Images and Content Note: All the third party API’s that are required in development would be provided by Marielyn. | 2

## Gantt_Chart Summary
Backend Technology - Node.js / PHP (Laravel)
Draft Gantt Chart -The Best Sandwiches Website and Application | [7 empty] | Development Start Date | Development End Date
[8 empty] | 2024-02-13 | 2024-05-13
[8 empty] | Total Project Effort (in person days) | 89
Backend Technology - Node.js / PHP (Laravel) | [7 empty] | Total Duration (in business days) | 65
Sl. No. | Tasks | Start_Date | End_Date | Lead Days | Effort Days (days)
1 | FSD Creation and Approval | 2024-02-13 | 2024-02-26 | 1 | 10 |  | 2024-02-26
2 | UI/UX (Users) | 2024-02-14 | 2024-02-23 | 0 | 8 | Design
3 | Website Design (Users) | 2024-02-14 | 2024-02-23 | 0 | 8 | Design
4 | Users_Mobile Application | 2024-02-27 | 2024-03-19 | 1 | 16
5 | Users_Website | 2024-02-27 | 2024-03-21 | 1 | 18
6 | API+Admin | 2024-02-27 | 2024-04-19 | 39 | 39
7 | QA Testing | 2024-03-06 | 2024-04-29 | 39 | 39
8 | UAT Testing | 2024-03-27 | 2024-05-03 | 1 | 28
9 | GO-LIVE | 2024-05-07 | 2024-05-13 | 1 | 5
Formulas:
Start_Date = WORKDAY(H8,[Lead Days],)
Start_Date = WORKDAY([Start_Date, row above],15,)
End_Date = WORKDAY(WORKDAY([Start_Date],[Effort Days (days)],),-1)
End_Date = WORKDAY(WORKDAY([Start_Date],[Effort Days (days)],),-1,)
Effort Days (days) = NETWORKDAYS([Start_Date],[End_Date])
Note on E14: ====== ID#AAAA8gmjM1g Kashish (2023-11-09 07:10:56) Sum of Total Development Effort Days needs to be entered by TL.

## Tools-timeline (hidden)
|  | Total Timeline for the Not Included Features | 107
S.No | Tools to integrate | Description | Reference Link/Platform | Time required to integrate on platfrom (in Days) | Already Included in Description | Cost Calculator
1 | Interactive Whiteboard | Similar to zoom and we would be integrating with the platform. | https://explaineverything.com/ | 30 | Yes | https://explaineverything.com/pricing/
2 | Screen Sharing | Enable tutors to share their screens to show presentations, software applications, simulations, or multimedia content related to the subject being taught. Example on a tool to be used: Zoom SDK provides screen sharing capabilities for real-time collaboration | https://developers.zoom.us/docs/meeting-sdk/web/ |  | Yes | Zoom SDK Pricing, Plans & More - 2023
3 | Document Sharing | Allow for the sharing of documents, textbooks, worksheets, and other learning materials in various formats (PDF, Word, PowerPoint). Example on a tool to be used: Google Drive API enables seamless document sharing and collaboration | https://developers.google.com/drive/api/guides/about-sdk |  | Yes
4 | Video Conferencing | Integrate high-quality video conferencing capabilities for face-to-face communication between tutors and students. Ensure stable audio and video transmission. Example on a tool to be used: Jitsi Meet API offers an open-source video conferencing solution. | Jitsi API ¦ How to Add Video Meetings to Your Site & App |  | Yes
5 | Recording and Playback | Provide the option to record tutoring sessions so that students can revisit lessons later for revision or in case they missed a session. Example on a tool to be used: OpenVidu provides recording and playback functionality for video sessions. | https://docs.openvidu.io/en/stable/reference-docs/REST-API/ |  | Yes
6 | Math Equation Editor | Include a math equation editor tool that simplifies the process of writing and formatting mathematical equations and formulas. Example on a tool to be used: MathJax is a library for rendering mathematical equations beautifully | https://www.mathjax.org/ | 15 | No | NO RUNNING COST AS PER THE INFORMATION
7 | Virtual Labs | For subjects like biology and chemistry, consider integrating virtual lab environments where students can perform experiments online, observe results, and learn scientific concepts. Example on a tool to be used: PhET Interactive Simulations offers free interactive math and science simulations | https://phet.colorado.edu/ | 45 | No | NO RUNNING COST AS PER THE INFORMATION
8 | Simulations | Include interactive simulations and models to help students visualize complex scientific principles in subjects like physics and chemistry. Example on a tool to be used: Wolfram Alpha API can be used for creating interactive simulations. | https://products.wolframalpha.com/api |  | No | https://products.wolframalpha.com/api/pricing
9 | Math Solver | Incorporate a math solver tool that students can use to input equations and receive step-by-step solutions and explanations. Example on a tool to be used: Wolfram Alpha API also provides math solving capabilities | https://products.wolframalpha.com/api | 15 | No | https://www.wizalpha.com/wapricing
10 | Quiz and Assessment Builder | Enable tutors to create quizzes, tests, and assignments, and allow students to complete them online. Provide instant grading and feedback. Example on a tool to be used: Quizlet API allows for quiz and flashcard creation. | Quizlet API allows for quiz and flashcard creation | 20 | Yes | https://quizlet.com/upgrade/plus/group
11 | Discussion Forums | Add discussion forums or chat rooms where students can ask questions, discuss topics, and collaborate with peers. Example on a tool to be used: Discourse API can be used to create discussion forums | https://docs.discourse.org/ | 10 | Yes | Discourse pricing ¦ Discourse - Civilized Discussion
12 | Content Library | Create a repository of educational resources, including video lessons, ebooks, articles, and reference materials, organized by subject and topic. Example on a tool to be used: Khan Academy API provides access to a vast library of educational content | https://support.khanacademy.org/hc/en-us/community/posts/14523004478861-New-Khan-API | 5 | No | NA
13 | Progress Tracking | Implement a feature that allows tutors and students to track progress, set learning goals, and review past achievements. Example on a tool to be used: Edmodo API offers features for progress tracking and goal setting | https://www.edmodo.com/ | 5 | Part of the progress tracking is included | https://www.godaddy.com/en-in/domainsearch/find?domainToCheck=edmodo.com&isc=GPPTCOM&itc=parkedpage_landers&key=parkweb&tmskey=dpp_dbs&utm_campaign=x_dom-broker_parkedpages_x_x_invest_b_001&utm_medium=parkedpages&utm_source=godaddy
14 | Adaptive Learning | Integrate adaptive learning algorithms that tailor the learning experience to each student's level and pace, offering personalized content and challenges. Example on a tool to be used: Adaptemy is an adaptive learning platform with an API for integration. | https://www.adaptemy.com/ | 5 | Yes | NA
15 | Peer Tutoring | Facilitate peer-to-peer tutoring by connecting students who excel in a particular subject with those who need help. Example on a tool to be used: Piazza API can be used to create a collaborative learning environment. | https://piazza.com/ | 5 | No | https://support.piazza.com/support/solutions/articles/48001161300-paid-model-for-piazza-q-a
16 | AI-Based Recommendations | Use artificial intelligence to recommend additional learning resources, exercises, or courses based on the student's performance and interests. Example on a tool to be used: Turi Create is a machine learning framework for building recommendation systems. | https://apple.github.io/turicreate/docs/api/ | NA |  | NA
17 | Content Annotation | Allow tutors and students to annotate on shared documents or whiteboards to highlight key points during the lesson. Example on a tool to be used: PDF.js allows for document annotation and highlighting. | https://mozilla.github.io/pdf.js/ | 7 | No | NA
18 | Digital Homework Submission | Enable students to submit assignments and homework digitally, and provide tools for tutors to provide feedback and corrections. Example on a tool to be used: Google Classroom API facilitates digital assignment submission | https://developers.google.com/classroom/reference/rest | 12 | Yes | https://www.trustradius.com/products/google-classroom/pricing
19 | Parental Monitoring | Include features that allow parents to monitor their child's progress and schedule sessions on their behalf, especially for younger students. Example on a tool to be used: Schoology API includes features for parental access and monitoring | Schoology API includes features for parental access and monitoring | 5 | No | NA
20 | Accessibility Features | Ensure the platform is accessible to all users, including those with disabilities, by providing features like screen readers and captioning. Example on a tool to be used: A11y API is a library for implementing accessibility features like screen readers | A11yWatch: Web Accessibility API | 10 | No | https://a11ywatch.com/pricing